## b2win
Buyer | Project | SWBS | Cont Supp | Item | Linked SPN | Description | Original SMOS Qty | Remaining SMOS Qty | In Yard Due Date | Lead time | Planned Order Date | UOM | Cust Item On Hand | Cust Item On Order | Cust Item Shortage | On Hold | Entered On Date | Last Mod Date | Last Price | Expected Amount | Compare To Project | Most Recent Order Date
8018 | 473 | 610 |  | 610-00-00002 | SRV525-032200005 | SRVC, FIRE EXTINGUISHERS, FI | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-08-03 | 2017-10-27 | 0 | 0
8018 | 473 | 982 |  | 982-01-00140 | SRV300-012000005 | CLEANING OF LINENS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-10-04 | 2017-10-27 | 532 | 532 | 471 | 2017-10-04
8018 | 473 | 992 |  | 992-01-VS004 |  | VSR, MISC. SCAFFOLDING PARTS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | DOL | 0 | 0 | 1 | No | 2017-07-24 | 2017-10-27 | 1 | 1 | 475 | 2017-07-26
8019 | 473 | 167 |  | 167-01-00449 | 611208-000000002 | COVER, MH, FL, 15 X 18 | 5 | 3 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 3 | No | 2014-03-10 | 2017-10-27 | 0 | 0
8019 | 473 | 180 |  | 180-24-7026B | SRV521-030900572 | SRVC, TO PROVIDE BEARING STU | 1 | 1 | 2014-02-28 | 123 | 2013-10-28 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8019 | 473 | 180 |  | 180-94-00002 | SRV521-030900782 | SEAL MNT PLATE, BHD 45 | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2013-12-04 | 2017-10-27 | 406.25 | 812.5 | 481 | 2017-10-05
8019 | 473 | 180 |  | 180-96-00003 | SRV521-030900783 | SEAL MNT PLATE, BHD 54 & BHD | 6 | 5 | 2014-01-20 | 17 | 2014-01-03 | EA | 0 | 0 | 5 | No | 2013-12-04 | 2017-10-27 | 4320 | 21600
8019 | 473 | 180 |  | 180-96-00004 | SRV521-030900803 | MAIN LUBE OIL PUMP BOLTING | 1 | 1 | 2014-06-24 | 123 | 2014-02-21 | EA | 0 | 0 | 1 | No | 2014-09-16 | 2017-10-27 | 180 | 180 | 479 | 2016-09-28
8019 | 473 | 201 |  | 201-A1-00001 | 180433-000000006 | BASE, MOUNTING GUARD | 16 | 16 | 2014-04-17 | 42 | 2014-03-06 | EA | 0 | 0 | 16 | No | 2014-12-12 | 2017-10-27 | 0 | 0
8019 | 473 | 244 |  | 244-01-00001 | 750430000200-001 | LOCATING PIN, 5 X 2 DIA., ST | 4 | 4 | 2014-10-23 | 14 | 2014-10-09 | EA | 0 | 0 | 4 | No | 2016-01-20 | 2017-10-27 | 0 | 0 | 120 | 2010-10-08
8019 | 473 | 512 |  | 512-01-00015 | SRV527-030500001 | HVAC PENETRATION SLEEVE FABR | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | EA | 0 | 0 | 1 | No | 2013-06-19 | 2017-10-27 | 1645 | 1645 | 479 | 2017-05-11
8019 | 473 | 612 |  | 612-02-0S6BA | 180201-000000002 | SUB ASSEMBLY S6BA HINGE BRAC | 48 | 48 | 2014-12-02 | 123 | 2014-08-01 | EA | 0 | 0 | 48 | No | 2013-12-06 | 2017-10-27 | 0 | 0 | 481 | 2017-04-17
8019 | 473 | 612 |  | 612-02-0S6FA | 180201-000000004 | SUB ASSEMBLY S6FA HINGE BRAC | 12 | 12 | 2014-12-02 | 123 | 2014-08-01 | EA | 0 | 0 | 12 | No | 2013-12-06 | 2017-10-27 | 0 | 0 | 481 | 2017-04-17
8019 | 473 | 612 |  | 612-02-0S6KA | 724315450100-001 | SUB ASSY S6KA BRACKET | 4 | 4 | 2015-02-19 | 14 | 2015-02-05 | EA | 0 | 0 | 4 | No | 2016-07-05 | 2017-10-27 | 0 | 0 | 481 | 2017-04-17
8019 | 473 | 665 |  | 665-01-087AD | 780800-000000020 | VERTICAL RETAINING BRACKET | 13 | 0 | 2014-08-18 | 0 | 2014-08-18 | EA | 0 | 13 | 13 | No | 2017-02-28 | 2017-10-27 | 0 | 0
8019 | 473 | 671 |  | 671-91-000S7 | 761146110000-001 | AFFF PAIL STOWAGE - FABRICAT | 1 | 1 | 2014-08-25 | 56 | 2014-06-30 | EA | 0 | 0 | 1 | No | 2017-01-09 | 2017-10-27 | 700 | 700 | 477 | 2017-06-22
8019 | 473 | 671 |  | 671-98-00S26 | 780200020000-001 | JBPDS REFRIGERATOR ENCLOSURE | 1 | 1 | 2015-07-03 | 123 | 2015-03-02 | EA | 0 | 0 | 1 | No | 2017-08-18 | 2017-10-27 | 0 | 0
8019 | 473 | 995 |  | 995-01-00023 | SRV521-032200358 | VENDOR SERVICES TO PLUTCHAK | 4 | 4 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 4 | No | 2015-06-12 | 2017-10-27 | 111.5 | 446 | 471 | 2014-03-19
8019 | 473 | 127 |  | 127-01-53301-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-03-11 | 60 | 2015-01-10 | LO | 0 | 0 | 1 | No | 2013-09-18 | 2017-10-27 | 0 | 0 | 481 | 2017-05-16
8019 | 473 | 127 |  | 127-01-53301-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-11 | 60 | 2015-01-10 | EA | 0 | 0 | 1 | No | 2013-09-18 | 2017-10-27 | 0 | 0 | 465 | 2011-12-09
8019 | 473 | 127 |  | 127-01-53301-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-03-11 | 123 | 2014-11-08 | LO | 0 | 0 | 1 | No | 2013-09-18 | 2017-10-27 | 0 | 0 | 481 | 2017-05-16
8019 | 473 | 161 |  | 161-02-SEGAB-L47 | -L47 | GOVERNMENT INSPECTION | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 485 | 2017-10-25
8019 | 473 | 161 |  | 161-02-SEGAB-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-06-11 | 123 | 2014-02-08 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 485 | 2017-08-22
8019 | 473 | 259 |  | 259-05-00052-800 | 602810-000000002 | GUIDE LINER PADS W/FASTENERS | 2 | 2 | 2014-03-14 | 42 | 2014-01-31 | LO | 0 | 0 | 2 | No | 2014-12-19 | 2017-10-27 | 0 | 0 | 485 | 2017-08-11
8019 | 473 | 259 |  | 259-05-22009-S00 | -S00 | PIPE SADDLE ASSY,321 CRES, 7 | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 225.14 | 450.28
8019 | 473 | 259 |  | 259-05-22009-S01 | -S00 | PIPE SADDLE ASSY,321 CRES, 7 | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 225.14 | 450.28
8019 | 473 | 259 |  | 259-05-22015-S00 | 80A202-000000004 | ANCHOR FDN ASSY, W/3" IPS, | 1 | 1 | 2014-03-07 | 30 | 2014-02-05 | EA | 0 | 0 | 1 | No | 2017-06-21 | 2017-10-27 | 92.61 | 92.61
8019 | 473 | 259 |  | 259-05-22015-S01 | 80A202-000000004 | ANCHOR FDN ASSY, W/3" IPS, | 1 | 1 | 2014-03-07 | 30 | 2014-02-05 | EA | 0 | 0 | 1 | No | 2017-06-21 | 2017-10-27 | 92.61 | 92.61
8019 | 473 | 259 |  | 259-05-22024-S00 | -S00 | CLAMP, PIPE, 13-1/4" DIA, SS | 1 | 1 | 2014-09-15 | 56 | 2014-07-21 | EA | 0 | 0 | 1 | No | 2017-06-21 | 2017-10-27 | 396.77 | 396.77
8019 | 473 | 259 |  | 259-05-22031-S01 | -S00 | ANCHOR FDN ASSY, W/3" IPS | 2 | 2 | 2014-03-07 | 30 | 2014-02-05 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 107.46 | 214.92
8019 | 473 | 259 |  | 259-05-22032-S00 | -S00 | HOT HANGER ASSEMBLY, 3X3X1/4 | 1 | 1 | 2014-03-07 | 30 | 2014-02-05 | EA | 0 | 0 | 1 | No | 2017-06-21 | 2017-10-27 | 92.06 | 92.06
8019 | 473 | 259 |  | 259-05-22033-S00 | -S00 | ANCHOR FDN ASSY, W/4" IPS, | 1 | 1 | 2014-03-07 | 30 | 2014-02-05 | EA | 0 | 0 | 1 | No | 2017-06-21 | 2017-10-27 | 89.26 | 89.26
8019 | 473 | 259 |  | 259-05-SP001-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP001-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0
8019 | 473 | 259 |  | 259-05-SP002-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP002-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP002-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0
8019 | 473 | 259 |  | 259-05-SP003-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-14 | 60 | 2014-01-13 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP003-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-03-14 | 60 | 2014-01-13 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP003-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-03-14 | 123 | 2013-11-11 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0
8019 | 473 | 259 |  | 259-05-SP004-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-14 | 60 | 2014-01-13 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP004-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-03-14 | 60 | 2014-01-13 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-07-16
8019 | 473 | 259 |  | 259-05-SP004-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-03-14 | 123 | 2013-11-11 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0
8019 | 473 | 259 |  | 259-07-00900-800 | 604010-000000003 | GUIDE LINER PADS W/FASTENERS | 4 | 0 | 2014-06-04 | 42 | 2014-04-23 | LO | 0 | 3 | 3 | No | 2014-12-19 | 2017-10-27 | 0 | 0
8019 | 473 | 259 |  | 259-07-00902-800 | 604010-000000002 | GUIDE LINER PADS W/FASTENERS | 2 | 2 | 2014-11-26 | 42 | 2014-10-15 | LO | 0 | 0 | 2 | No | 2014-12-19 | 2017-10-27 | 0 | 0 | 485 | 2017-08-11
8019 | 473 | 512 |  | 512-01-00015-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-01-27 | 123 | 2013-09-26 | LO | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0 | 465 | 2011-11-07
8019 | 473 | 512 |  | 512-01-LV999-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | LO | 0 | 0 | 1 | No | 2014-05-21 | 2017-10-27 | 0 | 0 | 465 | 2012-12-07
8019 | 473 | 512 |  | 512-01-LV999-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | LO | 0 | 0 | 1 | No | 2014-05-21 | 2017-10-27 | 0 | 0 | 481 | 2016-08-15
8019 | 473 | 551 |  | 551-01-E0002-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-05-07 | 60 | 2015-03-08 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8019 | 473 | 551 |  | 551-01-E0003-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-01-23 | 60 | 2014-11-24 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8019 | 473 | 551 |  | 551-01-E0003-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-01-23 | 60 | 2014-11-24 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8019 | 473 | 551 |  | 551-01-E0003-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2015-01-23 | 60 | 2014-11-24 | LO | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 471 | 2013-04-16
8019 | 473 | 551 |  | 551-01-E0004-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-05-07 | 60 | 2015-03-08 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8019 | 473 | 551 |  | 551-01-E0004-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2015-05-07 | 60 | 2015-03-08 | LO | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 471 | 2013-04-16
8019 | 473 | 551 |  | 551-01-E0005-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-05-07 | 60 | 2015-03-08 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8019 | 473 | 551 |  | 551-01-E0005-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2015-05-07 | 60 | 2015-03-08 | LO | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 471 | 2013-04-16
8019 | 473 | 551 |  | 551-01-E0006-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8019 | 473 | 551 |  | 551-01-E0013-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 481 | 2016-02-04
8019 | 473 | 551 |  | 551-01-E0013-R01 | SRV300-032800009 | VENDOR CLAIM, INSPECTION, SC | 1 | 1 | 2016-11-14 | 123 | 2016-07-14 | EA | 0 | 0 | 1 | No | 2016-11-14 | 2016-11-14 | 0 | 0
8019 | 473 | 581 |  | 581-01-00009-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-02-26 | 60 | 2014-12-28 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2015-08-19
8019 | 473 | 582 |  | 582-01-00100-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-02-26 | 60 | 2014-12-28 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2015-08-19
8019 | 473 | 582 |  | 582-01-00100-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-02-26 | 123 | 2014-10-26 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2015-08-19
8019 | 473 | 582 |  | 582-01-00102-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-02-26 | 60 | 2014-12-28 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2015-08-19
8019 | 473 | 582 |  | 582-01-00102-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-02-26 | 123 | 2014-10-26 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2015-08-19
8019 | 473 | 582 |  | 582-01-S0001-800 | 700022-000000004 | INSERT PLATE, 70MM, EH-36, L | 1 | 1 | 2015-02-26 | 123 | 2014-10-26 | EA | 0 | 0 | 1 | No | 2015-03-27 | 2017-10-27 | 0 | 0 | 467 | 2013-03-20
8019 | 473 | 612 |  | 612-01-90002-R01 | -R00 | REWORK, REPAIR PENDANTS & HE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-08-30 | 2017-10-27 | 0 | 0
8019 | 473 | 612 |  | 612-02-90001-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2015-02-11 | 2017-10-27 | 0 | 0 | 481 | 2017-04-17
8019 | 473 | 612 |  | 612-02-90002-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2015-02-12 | 2017-10-27 | 0 | 0 | 481 | 2017-04-17
8019 | 473 | 613 |  | 613-01-000S9-800 | 715204190000-001 | BOLT, EYE, 3/4-10UNC, 4-5/8" | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 46.09 | 92.18 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-000S9-801 | 710330690000-004 | NUT, HEX, 3/4-10UNC-2B, CRES | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 24.28 | 48.56 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-000S9-802 | 710830200049-001 | WASHER, FLAT, 3/4", CRES 316 | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 4.9 | 9.8 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-000S9-803 | 711204420000-002 | PIN, CLEVIS, 5/8 X 1-3/4" CR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 14.44 | 28.88 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-000S9-804 | 711204420000-003 | PIN, COTTER, 3/32 X 1-1/4" | 4 | 4 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 4 | No | 2017-07-03 | 2017-10-27 | 3.42 | 13.68 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-000S9-805 | 711330000000-001 | PIN, HINGE, FAB, 1", CRES 31 | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2017-07-03 | 2017-10-27 | 31.96 | 31.96 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-00S13-800 | 715204190000-001 | BOLT, EYE, 3/4-10UNC, 4-5/8" | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 46.09 | 92.18 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-00S13-801 | 710330690000-004 | NUT, HEX, 3/4-10UNC-2B, CRES | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 24.28 | 48.56 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-00S13-802 | 710830200049-001 | WASHER, FLAT, 3/4", CRES 316 | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 4.9 | 9.8 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-00S13-803 | 711204420000-002 | PIN, CLEVIS, 5/8 X 1-3/4" CR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2017-07-03 | 2017-10-27 | 14.44 | 28.88 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-00S13-804 | 711204420000-003 | PIN, COTTER, 3/32 X 1-1/4" | 4 | 4 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 4 | No | 2017-07-03 | 2017-10-27 | 3.42 | 13.68 | 483 | 2017-08-28
8019 | 473 | 613 |  | 613-01-00S13-805 | 711330000000-001 | PIN, HINGE, FAB, 1", CRES 31 | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2017-07-03 | 2017-10-27 | 31.96 | 31.96 | 483 | 2017-08-28
8019 | 473 | 637 |  | 637-97-00S78-S00 | -S00 | SHELF, PRINTER, FABRICATE | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-10 | 2017-10-27 | 460 | 460
8021 | 473 | 008 |  | 008-01-00001 | SRV300-010200001 | SERVICES, MODULE DELIVERY IA | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2015-11-11 | 2017-10-27 | 54000 | 54000 | 471 | 2013-12-11
8021 | 473 | 042 |  | 042-01-00003 | SRV520-031900001 | SRVC, PHOTOGRAPHY, CLOSE-OUT | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2016-04-14 | 2017-10-27 | 3600 | 3600 | 469 | 2017-04-17
8021 | 473 | 042 |  | 042-01-00061 | SRV520-012000101 | CLEANING SERVICES FOR LCS | 7 | 7 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 7 | No | 2014-03-19 | 2017-10-27 | 995 | 6965 | 467 | 2016-06-02
8021 | 473 | 243 |  | 243-00-00002 | SRV524-030900008 | SERVICE, IN-PLACE MACHINING | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-05-24 | 2017-10-27 | 22796.74 | 22796.74 | 465 | 2015-01-29
8021 | 473 | 243 |  | 243-99-000A1 | SRV524-030900009 | SERVICES, MACHINING, SHAFTIN | 1 | 1 | 2014-04-17 | 60 | 2014-02-16 | EA | 0 | 0 | 1 | No | 2013-11-20 | 2017-10-27 | 400 | 400 | 450 | 2009-11-03
8021 | 473 | 244 |  | 244-01-MS005 | SRV524-030900010 | SERVICES, MACHINING, IAW PTS | 1 | 1 | 2014-04-17 | 60 | 2014-02-16 | EA | 0 | 0 | 1 | No | 2013-11-20 | 2017-10-27 | 1 | 1 | 469 | 2017-08-28
8021 | 473 | 247 |  | 247-01-000S1 | SRV524-030900011 | SPACER, SHAFT, THRUST, MACHI | 4 | 4 | 2014-11-26 | 123 | 2014-07-26 | LO | 0 | 0 | 4 | No | 2013-11-22 | 2017-10-27 | 1 | 4 | 477 | 2017-08-10
8021 | 473 | 549 |  | 549-01-00900 | 240206000001-001 | OIL, ENGINE, MIL SYM 2190 TE | 2 | 1 | 2015-07-16 | 15 | 2015-07-01 | EA | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 888.02 | 888.02
8021 | 473 | 549 |  | 549-01-10002 | 240900000300-001 | GREASE, NLGI GRADE 2, SHELL | 4 | 4 | 2015-07-16 | 45 | 2015-06-01 | EA | 0 | 0 | 4 | No | 2013-11-21 | 2017-10-27 | 3.9 | 15.6 | 466 | 2016-02-26
8021 | 473 | 549 |  | 549-01-10003 | 240911000301-001 | GREASE, MIL-G-24139, MINERAL | 2 | 2 | 2015-07-16 | 10 | 2015-07-06 | EA | 0 | 0 | 2 | No | 2013-11-21 | 2017-10-27 | 6.41 | 12.82 | 469 | 2015-10-01
8021 | 473 | 549 |  | 549-01-10004 | 240800000001-001 | LUBRICANT, WIRE ROPE, MIL-PR | 3 | 3 | 2015-07-16 | 45 | 2015-06-01 | EA | 0 | 0 | 3 | No | 2013-11-21 | 2017-10-27 | 418.62 | 1255.86 | 467 | 2014-03-28
8021 | 473 | 549 |  | 549-01-10005 | 240206000001-005 | OIL, ENG, MIL SYM 2190, 55 G | 1 | 1 | 2015-01-12 | 15 | 2014-12-28 | EA | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 415.25 | 415.25 | 471 | 2016-10-05
8021 | 473 | 549 |  | 549-01-20002 | 240306000000-001 | COOLANT ADDITIVE, NALCO | 3 | 3 | 2015-01-12 | 45 | 2014-11-28 | EA | 2 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 352.46 | 352.46 | 469 | 2016-09-08
8021 | 473 | 549 |  | 549-01-20003 | 240206000000-005 | OIL, LUBRICATING, MIL-PRF- | 5 | 5 | 2015-01-12 | 60 | 2014-11-13 | GL | 0 | 0 | 5 | No | 2013-11-21 | 2017-10-27 | 13.7195 | 68.5975 | 450 | 2012-06-11
8021 | 473 | 549 |  | 549-01-20005 | 240223000000-001 | GOVERNOR OIL, 312-30W, MPDE | 2 | 2 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 2 | No | 2015-12-09 | 2017-10-27 | 704.24 | 1408.48 | 467 | 2015-12-11
8021 | 473 | 549 |  | 549-01-20021 | 240206000000-001 | OIL, LUBRICATING, MIL-PRF- | 3 | 3 | 2014-01-20 | 45 | 2013-12-06 | EA | 0 | 3 | 3 | No | 2013-11-21 | 2017-10-27 | 53.9084 | 161.7252 | 471 | 2017-03-14
8021 | 473 | 549 |  | 549-01-20022 | 240206000000-002 | OIL, LUBRICATING, SAE 20/30, | 1 | 1 | 2014-11-26 | 45 | 2014-10-12 | EA | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 72.89 | 72.89 | 465 | 2014-03-26
8021 | 473 | 549 |  | 549-01-20024 | 241321000000-001 | DETERGENT, GT WATER WASH, | 2 | 2 | 2014-11-26 | 45 | 2014-10-12 | EA | 0 | 0 | 2 | No | 2013-11-21 | 2017-10-27 | 208 | 416 | 465 | 2015-04-09
8021 | 473 | 549 |  | 549-01-20025 | 240321000000-001 | COOLANT,GAS TURBINE ESS AMSO | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | DR | 0 | 0 | 1 | No | 2016-02-10 | 2017-10-27 | 1506.12 | 1506.12 | 471 | 2016-05-18
8021 | 473 | 549 |  | 549-01-20041 | 240202000000-008 | OIL, HYDRAULIC, ISO VG 32, S | 4300 | 4300 | 2014-11-26 | 10 | 2014-11-16 | EA | 0 | 0 | 4300 | No | 2013-11-21 | 2017-10-27 | 5.95 | 25585 | 450 | 2011-03-02
8021 | 473 | 549 |  | 549-01-20041 | 240202000000-008 | OIL, HYDRAULIC, ISO VG 32, S | 4300 | 4300 | 2014-11-26 | 10 | 2014-11-16 | EA | 0 | 0 | 4300 | No | 2013-11-21 | 2017-10-27 | 5.95 | 25585 | 450 | 2011-03-02
8021 | 473 | 549 |  | 549-01-20042 | 240206000001-002 | OIL, ENGINE, MIL SYM 2190 TE | 11200 | 700 | 2014-01-20 | 15 | 2014-01-05 | GL | 550 | 0 | 150 | No | 2015-06-12 | 2017-10-27 | 8.04 | 1206
8021 | 473 | 549 |  | 549-01-20081 | 240900000300-002 | GREASE, DOD-G-24508, | 1 | 1 | 2015-01-30 | 45 | 2014-12-16 | EA | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 0 | 0 | 467 | 2017-01-25
8021 | 473 | 549 |  | 549-01-30003 | 240307000000-002 | ANTIFREEZE, ETHYLENE GLYCOL | 25 | 25 | 2015-01-12 | 45 | 2014-11-28 | EA | 0 | 0 | 25 | No | 2013-11-21 | 2017-10-27 | 211.76 | 5294 | 471 | 2016-08-09
8021 | 473 | 549 |  | 549-01-30005 | 240206000000-006 | OIL, ENGINE LUBRICATING, MOB | 330 | 110 | 2014-01-20 | 15 | 2014-01-05 | GL | 0 | 0 | 110 | No | 2015-02-10 | 2017-10-27 | 11.5152 | 1266.672 | 471 | 2017-02-03
8021 | 473 | 549 |  | 549-01-40001 | 240906010000-001 | LUBRICANT, ISOFLEX TOPAS NCA | 2 | 2 | 2014-11-06 | 45 | 2014-09-22 | EA | 0 | 0 | 2 | No | 2013-11-21 | 2017-10-27 | 127.6 | 255.2 | 450 | 2011-02-23
8021 | 473 | 549 |  | 549-01-40002 | 240922010301-001 | GREASE, MIL-G-21164, | 1 | 1 | 2014-11-06 | 45 | 2014-09-22 | EA | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 52.74 | 52.74 | 465 | 2014-03-26
8021 | 473 | 549 |  | 549-01-50001 | 240905000300-002 | GREASE, NLGI GRADE 2, LITHIU | 10 | 10 | 2015-01-30 | 30 | 2014-12-31 | EA | 0 | 0 | 10 | No | 2013-11-21 | 2017-10-27 | 3.52 | 35.2 | 450 | 2011-02-23
8021 | 473 | 549 |  | 549-01-50002 | 240900000100-001 | GREASE, CHEVRON SRI NO. 2 | 10 | 10 | 2015-02-19 | 30 | 2015-01-20 | EA | 0 | 0 | 10 | No | 2013-11-21 | 2017-10-27 | 42.41 | 424.1 | 465 | 2014-03-26
8021 | 473 | 549 |  | 549-01-50027 | 240211000000-002 | OIL, COMPRESSOR, MINERAL, SA | 10 | 10 | 2014-11-06 | 0 | 2014-11-06 | GL | 0 | 0 | 10 | No | 2013-11-21 | 2017-10-27 | 16.77 | 167.7 | 469 | 2016-02-03
8021 | 473 | 549 |  | 549-01-50029 | 240922000000-001 | GREASE, MOLYKOTE LONGTERM | 2 | 2 | 2015-01-30 | 60 | 2014-12-01 | GL | 0 | 0 | 2 | No | 2013-11-21 | 2017-10-27 | 20.97 | 41.94 | 467 | 2014-10-02
8021 | 473 | 549 |  | 549-01-50031 | 240203000000-001 | OIL, GEAR, SAE 50 | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | GL | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 17.278 | 17.278 | 465 | 2014-03-28
8021 | 473 | 549 |  | 549-01-50032 | 240905000000-001 | GREASE, MOBILUX EP 111 | 5 | 5 | 2015-01-30 | 60 | 2014-12-01 | GL | 0 | 0 | 5 | No | 2013-11-21 | 2017-10-27 | 19.07 | 95.35 | 467 | 2014-03-28
8021 | 473 | 549 |  | 549-01-50033 | 240905000000-002 | GREASE, MOBILGREASE XHP 461 | 1 | 1 | 2015-01-30 | 60 | 2014-12-01 | GL | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 28.3 | 28.3 | 467 | 2014-03-26
8021 | 473 | 549 |  | 549-01-50034 | 240203010000-001 | OIL, GEAR LUBRICANT, SYNTHET | 4 | 4 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 4 | No | 2013-11-21 | 2017-10-27 | 38.1 | 152.4 | 467 | 2014-03-26
8021 | 473 | 549 |  | 549-01-50035 | 240206000001-003 | OIL, ENG, MIL SYM 2190, 1 GA | 5 | 5 | 2015-01-12 | 15 | 2014-12-28 | EA | 0 | 0 | 5 | No | 2013-11-21 | 2017-10-27 | 54.73 | 273.65 | 465 | 2014-03-28
8021 | 473 | 549 |  | 549-01-50037 | 240914000300-001 | GREASE, NLGI GRADE 2, LITHIU | 4 | 4 | 2015-01-30 | 30 | 2014-12-31 | EA | 0 | 0 | 4 | No | 2013-11-21 | 2017-10-27 | 28.39 | 113.56 | 465 | 2014-03-28
8021 | 473 | 549 |  | 549-01-50038 | 240203010000-005 | OIL, GEAR LUBRICANT, SYNTHET | 15 | 5 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 5 | No | 2015-06-22 | 2017-10-27 | 39.72 | 198.6
8021 | 473 | 549 |  | 549-01-50045 | 240913000300-002 | GREASE, MULTIPURPOSE, NLGI G | 1 | 1 | 2015-01-30 | 123 | 2014-09-29 | EA | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 0 | 0 | 467 | 2016-09-08
8021 | 473 | 549 |  | 549-01-50046 | 240202000000-003 | OIL, HYDRAULIC, ISO VG 46 | 2 | 2 | 2015-01-12 | 123 | 2014-09-11 | GL | 0 | 0 | 2 | No | 2013-11-21 | 2017-10-27 | 10.62 | 21.24 | 467 | 2014-03-26
8021 | 473 | 549 |  | 549-01-50061 | 240911000301-001 | GREASE, MIL-G-24139, MINERAL | 2 | 2 | 2015-01-30 | 10 | 2015-01-20 | EA | 0 | 0 | 2 | No | 2013-11-21 | 2017-10-27 | 53.61 | 107.22 | 467 | 2014-03-26
8021 | 473 | 549 |  | 549-01-50063 | 240203000000-002 | OIL, GEAR LUBRICANT, 80W-90, | 38 | 38 | 2015-02-19 | 123 | 2014-10-19 | EA | 0 | 0 | 38 | No | 2013-11-21 | 2017-10-27 | 53.52 | 2033.76 | 475 | 2017-07-17
8021 | 473 | 549 |  | 549-01-50065 | 240203000000-003 | OIL, GEAR LUBRICANT, 80W-90, | 10 | 10 | 2015-02-19 | 10 | 2015-02-09 | EA | 0 | 0 | 10 | No | 2013-11-21 | 2017-10-27 | 4.4442 | 44.442 | 471 | 2016-02-15
8021 | 473 | 549 |  | 549-01-50066 | 240905000100-001 | GREASE, CITGO PREMIUM | 2 | 2 | 2014-09-29 | 123 | 2014-05-29 | EA | 0 | 0 | 2 | No | 2013-11-21 | 2017-10-27 | 2.876 | 5.752 | 467 | 2014-03-26
8021 | 473 | 549 |  | 549-01-50071 | 240203000000-004 | OIL, GEAR LUBRICANT, 80W-90, | 16 | 16 | 2015-02-19 | 123 | 2014-10-19 | EA | 0 | 0 | 16 | No | 2013-11-21 | 2017-10-27 | 4.43 | 70.88 | 467 | 2014-03-28
8021 | 473 | 549 |  | 549-01-60041 | 240206000001-004 | OIL, ENGINE, MIL SYM 2190-TE | 3 | 3 | 2015-01-12 | 15 | 2014-12-28 | GL | 0 | 0 | 3 | No | 2013-11-21 | 2017-10-27 | 54.73 | 164.19 | 467 | 2014-03-26
8021 | 473 | 830 |  | 830-01-00004 | SRV520-031200036 | SRVC, ZODIAC AEROSPACE PROVI | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-02-08 | 2017-10-27 | 340000 | 340000 | 325 | 2017-05-10
8021 | 473 | 982 |  | 982-01-00001 | 240420-000000001 | DIESEL FUEL, #2, FOR BDT, BS | 300000 | 224880.5 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 2 | 224878.5 | No | 2016-04-27 | 2017-10-27 | 300 | 67463550
8021 | 473 | 982 |  | 982-01-00108 | SRV300-021800002 | TUG SERVICES, TO ASSIST LCS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-10-17 | 2017-10-27 | 1 | 1 | 330 | 2017-10-17
8021 | 473 | 982 |  | 982-01-00119 | SRV300-011000003 | PEPSI, BAG IN A BOX FOR SEA | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-09-11 | 2017-10-27 | 1 | 1 | 471 | 2017-09-19
8021 | 473 | 982 |  | 982-01-00123 | SRV300-011000002 | FOOD FOR SEA TRIALS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-10-12 | 2017-10-27 | 1 | 1 | 471 | 2017-10-12
8021 | 473 | 982 |  | 982-01-VS001 | -VSR | VSR, CLEAN & SANITIZE GALLEY | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-10-18 | 2017-10-27 | 1 | 1 | 471 | 2017-10-19
8021 | 473 | 984 |  | 984-01-VS001 | -VSR | VSR, TEST, HYDRO, FUEL HOSES | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-10-13 | 2017-10-27 | 0 | 0
8021 | 473 | 986 |  | 986-01-00585 | TEST00-000001039 | SMOKE DETECTOR TESTER, AEROS | 10 | 10 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 10 | No | 2015-10-27 | 2017-10-27 | 20.23 | 202.3 | 465 | 2015-08-26
8021 | 473 | 986 |  | 986-01-00674 | SRV656-032800001 | FIRE EXTINGUISHER/CHECK-RECE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-09-11 | 2017-10-27 | 1 | 1 | 471 | 2017-10-10
8021 | 473 | 992 |  | 992-01-00044 | SRV525-032800002 | VENDOR SERVICE: MOVE EXCLUSI | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 1 | 1 | 471 | 2017-10-11
8021 | 473 | 996 |  | 996-99-FLAGS | SRV533-012000001 | CLEANING, LAUNCH FLAGS/BANNE | 1 | 1 | 2014-09-29 | 123 | 2014-05-29 | LO | 0 | 0 | 1 | No | 2016-02-02 | 2017-10-27 | 300 | 300 | 471 | 2016-02-04
8021 | 473 | 184 |  | 184-01-00001-809 | SRV521-030800009 | 3" X 3" ALIGNMENT BENCHMARK, | 2 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 650 | 650
8022 | 473 | 512 |  | 512-01-00001 | 680100-000000007 | UNIT HEATERS | 1 | 1 | 2014-08-18 | 60 | 2014-06-19 | LO | 0 | 0 | 1 | No | 2013-10-09 | 2017-10-27 | 0 | 0 | 465 | 2011-11-07
8022 | 473 | 512 |  | 512-01-00003 | 680400-000000006 | VANEAXIAL AND TUBEAXIAL FAN, | 1 | 1 | 2014-08-18 | 90 | 2014-05-20 | LO | 0 | 0 | 1 | No | 2013-10-09 | 2017-10-27 | 0 | 0 | 465 | 2011-11-07
8022 | 473 | 512 |  | 512-01-00005 | 681400-000000001 | DUCT AND GRAVITY COOLING COI | 1 | 1 | 2014-08-18 | 84 | 2014-05-26 | EA | 0 | 0 | 1 | No | 2013-10-09 | 2017-10-27 | 0 | 0 | 465 | 2011-11-07
8022 | 473 | 512 |  | 512-01-00008 | 680400-000000007 | CENTRIFUGAL FAN IAW PTS | 1 | 1 | 2014-08-18 | 185 | 2014-02-14 | EA | 0 | 0 | 1 | No | 2013-04-22 | 2017-10-27 | 53269 | 53269 | 120 | 2014-04-01
8022 | 473 | 512 |  | 512-01-00026 | 681100-000000001 | HVAC ADDITIONAL COMPONENTS I | 1 | 1 | 2014-08-18 | 105 | 2014-05-05 | EA | 0 | 0 | 1 | No | 2013-10-10 | 2017-10-27 | 7000 | 7000 | 650 | 2014-03-31
8022 | 473 | 512 |  | 512-01-00065 | SRV527-031500013 | IMECO COST INCREASE OF INCOR | 1 | 1 | 2014-01-27 | 123 | 2013-09-26 | LO | 0 | 0 | 1 | No | 2014-08-14 | 2017-10-27 | 5330 | 5330 | 465 | 2014-07-22
8022 | 473 | 512 |  | 512-01-00075 | -S00 | SRVC, INCORPORATE CF 2381 | 1 | 1 | 2014-07-22 | 123 | 2014-03-21 | EA | 0 | 0 | 1 | No | 2017-04-13 | 2017-10-27 | 12192 | 12192 | 403 | 2007-10-29
8022 | 473 | 512 |  | 512-01-00076 | SRV527-031500024 | INCORP CF 1759, ALARM, LINT | 1 | 1 | 2014-02-24 | 123 | 2013-10-24 | EA | 0 | 0 | 1 | No | 2017-06-08 | 2017-10-27 | 7103 | 7103 | 403 | 2007-10-18
8022 | 473 | 512 |  | 512-88-05187 | 606500-000000013 | VALVE, CHILL WATER BALANCING | 3 | 2 | 2014-07-22 | 180 | 2014-01-23 | EA | 0 | 0 | 2 | No | 2013-10-09 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-88-05204 | 606500-000000018 | VALVE, CHILL WATER CONTROL | 3 | 1 | 2014-07-22 | 96 | 2014-04-17 | EA | 0 | 0 | 1 | No | 2014-07-25 | 2017-10-27 | 0 | 0
8022 | 473 | 604 |  | 604-01-006LP | 727611000000-001 | PADLOCK, BRASS, 1-1/2" | 6 | 6 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 6 | No | 2017-10-20 | 2017-10-27 | 0 | 0
8022 | 473 | 610 |  | 610-00-00001 | SRV525-032200002 | SRVC, FIRE EXTINGUISHERS, FI | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2016-08-11 | 2017-10-27 | 752 | 752 | 471 | 2017-04-18
8022 | 473 | 624 |  | 624-01-00023 | 610300-000000018 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00023 | 610300-000000018 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00024 | 610300-000000019 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00025 | 610300-000000020 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00026 | 610300-000000021 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00027 | 610300-000000022 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00029 | 610300-000000023 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00030 | 610300-000000024 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00055 | 610300-000000025 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00056 | 610300-000000026 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00057 | 610300-000000027 | DOOR, JOINER, COUNTER BALANC | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 624 |  | 624-01-00072 | 610328-000000001 | DOOR, JOINER, MODULAR, IAW P | 1 | 1 | 2014-01-20 | 112 | 2013-09-30 | EA | 0 | 0 | 1 | No | 2016-04-12 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 635 |  | 635-00-V0004 | SRV525-030600100 | SERVICE PROVIDE LABOR INSTAL | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2014-08-15 | 2017-10-27 | 0 | 0 | 465 | 2014-12-01
8022 | 473 | 635 |  | 635-00-V001B | SRV525-011100002 | MOD TO CONTRACT, EXERCISE OP | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-05-07 | 2017-10-27 | 1 | 1 | 475 | 2015-10-09
8022 | 473 | 637 |  | 637-00-V0005 | SRV525-031400003 | SERVICES, SUBCONTRACT LABOR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2013-06-10 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-00-V0008 | SRV525-030400002 | SERVICE, SUBCONTRACTOR, JOIN | 1 | 1 | 2014-08-04 | 123 | 2014-04-03 | EA | 0 | 0 | 1 | No | 2015-09-09 | 2017-10-27 | 487000 | 487000 | 485 | 2016-12-12
8022 | 473 | 637 |  | 637-00-V0010 | SRV525-031100019 | CONTRACT MOD, INCORP CF 2470 | 1 | 1 | 2014-07-22 | 123 | 2014-03-21 | LO | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-01-AWR01 | SRV520-032200001 | JOINER SYSTEM AUTHORIZED WOR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-07-09 | 2017-10-27 | 2655.12 | 2655.12 | 477 | 2017-10-12
8022 | 473 | 637 |  | 637-94-0001A | 780411-000000001 | STOWAGE SHELF | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2014-04-29 | 2017-10-27 | 393.44 | 786.88 | 467 | 2013-10-17
8022 | 473 | 637 |  | 637-94-00022 | 102002-000000001 | SHEATHING, 18 GA, CRES 304 | 5 | 0 | 2014-06-04 | 240 | 2013-10-07 | EA | 0 | 5 | 5 | No | 2015-04-15 | 2017-10-27 | 79.99 | 399.95 | 450 | 2009-07-01
8022 | 473 | 637 |  | 637-94-00023 | 110300-000000001 | CHANNEL, 20 FEET LONG | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-09 | 2017-10-27 | 20.18 | 20.18 | 423 | 2009-01-15
8022 | 473 | 637 |  | 637-94-00024 | 671200-000000001 | TAPE, DBL SIDED, .045 X 1 X | 1 | 0 | 2014-06-04 | 240 | 2013-10-07 | EA | 0 | 1 | 1 | No | 2015-04-15 | 2017-10-27 | 63.98 | 63.98 | 403 | 2007-08-23
8022 | 473 | 637 |  | 637-94-00028 | 728601-000000001 | HAMMER-ON BEAM CLAMP, STEEL | 20 | 20 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 20 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-00033 | 704300-000000018 | TIE-DOWN, BLACK STRAP, POLYP | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-0004R | 100400-000000008 | PLATE, CLOSURE, 12 GA, STEEL | 2 | 2 | 2014-06-04 | 180 | 2013-12-06 | EA | 0 | 0 | 2 | No | 2016-02-12 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-0005A | 180301-000000005 | DECK COAMING | 15 | 15 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 15 | No | 2014-09-09 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-0008B | 180120-000000002 | FDN, TOWEL DISPENSER | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-12 | 2017-10-27 | 30.07 | 30.07 | 465 | 2013-03-08
8022 | 473 | 637 |  | 637-94-0008C | 180120-000000001 | FDN, SOAP DISPENSER | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-09 | 2017-10-27 | 85.14 | 85.14 | 467 | 2013-10-17
8022 | 473 | 637 |  | 637-94-000S1 | 090300-000000013 | CURTAIN PLATE ASSEMBLY | 3 | 3 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 3 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S2 | 090300-000000014 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S3 | 090300-000000015 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S4 | 090300-000000016 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S5 | 090300-000000017 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S6 | 090300-000000018 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S7 | 090300-000000019 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S8 | 090300-000000020 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-000S9 | 090300-000000021 | CURTAIN PLATE ASSEMBLY | 7 | 7 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 7 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-0011A | 180117-000000002 | FDN, MOP/BROOM RACK | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2014-09-09 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-0026A | 090200-000000012 | CORNER ANGLE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-09 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-0026B | 090200-000000013 | HANGER, TOP SHOE | 9 | 9 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 9 | No | 2014-09-09 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-0026C | 090200-000000014 | HANGER, TOP SHOE | 6 | 6 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 6 | No | 2014-09-09 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-00S11 | 090300-000000023 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-00S12 | 090300-000000024 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-00S14 | 727500-000000001 | MOP/BROOM RACK TOP BRACKET | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-00S15 | 727500-000000002 | MOP/BROOM RACK BOTTOM BRACKE | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-94-00S16 | 780806-000000002 | BUCKET STOWAGE | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-09 | 2017-10-27 | 116.7 | 116.7 | 467 | 2013-10-17
8022 | 473 | 637 |  | 637-95-00S24 | SRV525-030500001 | BHD INSERT, SHOCK POCKET, FA | 1 | 1 | 2014-07-22 | 123 | 2014-03-21 | EA | 0 | 0 | 1 | No | 2016-04-11 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-95-00S25 | SRV525-030500002 | BHD INSERT, SHOCK POCKET, FA | 1 | 1 | 2014-07-22 | 123 | 2014-03-21 | EA | 0 | 0 | 1 | No | 2016-04-11 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-97-00S76 | 610400-000000003 | LOCK BOX, DEADBOLT, ALUMINUM | 1 | 0 | 2015-01-12 | 112 | 2014-09-22 | EA | 0 | 1 | 1 | No | 2017-01-19 | 2017-10-27 | 0 | 0
8022 | 473 | 640 |  | 640-02-00004 | 741900-000000002 | CHAIR, COMPUTER, NAVY SHIPBO | 1 | 0 | 2014-01-20 | 0 | 2014-01-20 | EA | 0 | 1 | 1 | No | 2015-09-04 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00006 | 740200-000000001 | BOOK CASE, SECTIONAL, IAW S3 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00012 | 742000-000000001 | BULLETIN BOARD, TYPE A, BHD | 6 | 6 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 6 | No | 2015-12-15 | 2017-10-27 | 1320 | 7920 | 465 | 2015-08-31
8022 | 473 | 640 |  | 640-02-00023 | 740200-000000006 | TABLE, LOUNGE, END, ALUMINUM | 2 | 2 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 2 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00028 | 740200-000000007 | TABLE, COFFEE, TYPE I | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00030 | 740200-000000008 | SOFA, LOUNGE, 2 SEAT, IAW NA | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00030 | 740200-000000008 | SOFA, LOUNGE, 2 SEAT, IAW NA | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00037 | 742300-000000001 | TABLE, CREW MESS, OUTRIGGER | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00039 | 742300-000000002 | TABLE, CREW MESS, OUTRIGGER | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.03 | 450 | 2009-05-27
8022 | 473 | 640 |  | 640-02-00052 | 740200-000000012 | RACK, MAGAZINE, TYPE B, ALUM | 2 | 2 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 2 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00059 | 742100-000000001 | TRASH CAN, 32 GALLON CAPACIT | 1 | 0 | 2014-01-20 | 0 | 2014-01-20 | EA | 0 | 1 | 1 | No | 2015-09-04 | 2017-10-27 | 127.3 | 127.3 | 450 | 2010-07-07
8022 | 473 | 640 |  | 640-02-00061 | 740200-000000002 | CABINET, LIBRARY, IAW MIL-PR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00072 | 741100-000000001 | MAILBOX, IAW NAVSEC 805-1629 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00078 | 741900-000000004 | CHAIR, STACKING, SFC NO B-3C | 16 | 0 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 16 | 16 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.16 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00083 | 740200-000000014 | BULLETIN BOARD, TYPE B, BHD | 2 | 2 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 2 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00088 | 740200-000000015 | LOCKER, TABLE, ALUMINUM | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00089 | 740200-000000017 | LOCKER, TABLE LEAF, ALUMINUM | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00090 | 742300-000000003 | TABLE, ROUND, 30" DIAMETER | 2 | 2 | 2014-01-20 | 0 | 2014-01-20 | EA | 0 | 0 | 2 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00092 | 740200-000000020 | TABLE, EXTENSION, ALUMINUM | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00093 | 740200-000000019 | TABLE, SOLID TOP, SIZE 1, LA | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00095 | 742300-000000021 | TABLE, EXTENSION, ALUMINUM | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00096 | 742300-000000005 | TABLE, CREW MESS, OUTRIGGER | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-0009S | 741900-000000005 | CHAIR TIE-DOWN ASSY W/STL BA | 32 | 32 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 32 | No | 2014-10-28 | 2017-10-27 | 78 | 2496 | 450 | 2009-04-02
8022 | 473 | 640 |  | 640-02-00103 | 742300-000000022 | CABINET, NAPKIN, ALUMINUM | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00104 | 740200-000000003 | LOCKER, RELIGIOUS LITERATURE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00117 | 740500-000000001 | LAMP, TABLE | 2 | 0 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 2 | 2 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00123 | 742300-000000006 | TABLE, WRITING, W/DRAWER, IA | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00147 | 740200-000000004 | CABINET, ENTERTAINMENT, ALUM | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0 | 0
8022 | 473 | 640 |  | 640-02-0017L | 742300-000000007 | DESK, FLAT TOP, SINGLE PEDES | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-0030A | 742300-000000024 | SOFA, LOUNGE, 2-SEAT | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-0036A | 741900-000000006 | CHAIR, ARM, TYPE 1, CLASS 1 | 16 | 0 | 2014-01-20 | 0 | 2014-01-20 | EA | 0 | 16 | 16 | No | 2015-09-04 | 2017-10-27 | 0.01 | 0.16 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-0134A | 742000-000000002 | BOARD, DRY ERASE, PORTABLE | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 644 |  | 644-00-V0001 | 735312-000000001 | MATERIAL SUPPLY, SANITARY MO | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2014-08-15 | 2017-10-27 | 0 | 0 | 467 | 2012-05-24
8022 | 473 | 644 |  | 644-00-V0005 | SRV525-030400003 | SRVC, SUBCONTRACT, APPLY EPO | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-03-20 | 2017-10-27 | 3600 | 3600 | 467 | 2015-06-11
8022 | 473 | 644 |  | 644-01-00020 | 733001-000000004 | LAVATORY, OVAL COMPT WASHUP | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-08-14 | 2017-10-27 | 0 | 0 | 450 | 2009-05-19
8022 | 473 | 644 |  | 644-01-00022 | 733001-000000005 | DRAIN FTG, CHRME PL STAMPED | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-08-14 | 2017-10-27 | 0 | 0 | 450 | 2009-05-19
8022 | 473 | 644 |  | 644-01-00023 | 735712-000000001 | SOAP DISPENSER, LIQUID TANK | 8 | 8 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 8 | No | 2014-04-29 | 2017-10-27 | 31.11 | 248.88 | 450 | 2012-01-17
8022 | 473 | 644 |  | 644-01-00024 | 733001-000000006 | TOWEL BAR, SURFACE MTD RND | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-08-14 | 2017-10-27 | 0 | 0 | 450 | 2009-05-19
8022 | 473 | 644 |  | 644-01-00025 | 731701-000000001 | WATER COOLER | 5 | 5 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 1 | 5 | No | 2014-05-11 | 2017-10-27 | 807.69 | 4038.45 | 450 | 2009-07-09
8022 | 473 | 644 |  | 644-01-00030 | 090104-000000001 | BI-METALLIC PAD, 1" W X 6" L | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-01-21 | 2017-10-27 | 23.8 | 23.8 | 469 | 2013-03-22
8022 | 473 | 644 |  | 644-01-00033 | 733001-000000001 | FAUCET, SERVICE SINK | 1 | 1 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 91.44 | 91.44 | 450 | 2009-07-20
8022 | 473 | 644 |  | 644-01-00034 | 732001-000000001 | TOWEL DISPENSER, BRADLEY | 1 | 1 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 43.04 | 43.04 | 450 | 2012-01-17
8022 | 473 | 644 |  | 644-01-00036 | 733001-000000010 | SPOUT, CHROME PLATED, 10-3/4 | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-08-14 | 2017-10-27 | 0 | 0 | 450 | 2010-06-30
8022 | 473 | 644 |  | 644-01-00037 | 733001-000000008 | FOOT PEDAL VALVE, CHROME PLT | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-08-14 | 2017-10-27 | 538.36 | 538.36 | 469 | 2016-01-18
8022 | 473 | 664 |  | 664-02-00145 | 780800-000000006 | PORTABLE SUB-PUMP STOWAGE | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-05-05 | 2017-10-27 | 325 | 650 | 467 | 2012-11-30
8022 | 473 | 664 |  | 664-02-00162 | 704100-000000007 | STRAP, 24-1/4" OVERALL LG, P | 2 | 0 | 2014-09-29 | 30 | 2014-08-30 | EA | 0 | 2 | 2 | No | 2016-02-17 | 2017-10-27 | 7.16 | 14.32 | 467 | 2016-01-26
8022 | 473 | 664 |  | 664-02-0091K | 723100-000000007 | BACK-UP, TIE-DOWN STAPLE, CR | 1 | 1 | 2014-07-29 | 180 | 2014-01-30 | EA | 0 | 0 | 1 | No | 2016-02-17 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-02-00S19 | 100401-000000019 | PLATE PATCH, HINGED, SIZE 1, | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 66.57 | 266.28 | 467 | 2012-08-22
8022 | 473 | 664 |  | 664-02-00S20 | 100401-000000020 | PLATE PATCH, HINGED, SIZE 2, | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 74.69 | 298.76 | 467 | 2012-08-22
8022 | 473 | 664 |  | 664-02-00S21 | 100401-000000021 | PLATE PATCH, HINGED, SIZE 3, | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 82.53 | 330.12 | 467 | 2012-08-22
8022 | 473 | 664 |  | 664-02-00S26 | 780802-000000010 | ENCLOSURE, P-100 PUMP | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-05-05 | 2017-10-27 | 7330 | 7330 | 467 | 2013-02-27
8022 | 473 | 664 |  | 664-02-00S51 | 725401-000000006 | DECK CLIP, P-100 PUMP STOWAG | 4 | 4 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 4 | No | 2014-09-19 | 2017-10-27 | 54.67 | 218.68 | 467 | 2012-02-27
8022 | 473 | 664 |  | 664-02-00S56 | 180100-000000065 | STOWAGE ASSY, SUBMERSIBLE PU | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-19 | 2017-10-27 | 355.89 | 355.89 | 467 | 2012-08-22
8022 | 473 | 664 |  | 664-02-00S59 | 780802-000000005 | RACK, STOWAGE, BATTLE HELMET | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 305.55 | 305.55 | 467 | 2012-08-22
8022 | 473 | 664 |  | 664-02-00S70 | 090300-000000042 | BOX PATCH, SIZE 1, SUPPLIED | 1 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 1 | 1 | No | 2014-08-28 | 2017-10-27 | 382.12 | 382.12 | 465 | 2013-01-04
8022 | 473 | 664 |  | 664-02-00S71 | 780802-000000012 | BOX PATCH, SIZE 2, SUPPLIED | 1 | 0 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 1 | 1 | No | 2014-08-28 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-02-00S72 | 090300-000000039 | BOX PATCH, SIZE 3, DWG NO. | 1 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 1 | 1 | No | 2014-05-12 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-02-00S85 | 780409-000000004 | STWG, PLATE PATCH, 1/4", ALU | 2 | 2 | 2014-12-09 | 180 | 2014-06-12 | EA | 0 | 0 | 2 | No | 2016-02-17 | 2017-10-27 | 546.35 | 1092.7 | 467 | 2016-01-22
8022 | 473 | 664 |  | 664-02-00S86 | 780409-000000005 | STWG, JUBILEE PATCH, 1/4", A | 2 | 2 | 2014-12-09 | 180 | 2014-06-12 | EA | 0 | 0 | 2 | No | 2016-02-17 | 2017-10-27 | 487.67 | 975.34 | 467 | 2016-01-22
8022 | 473 | 664 |  | 664-02-00S90 | 180100-000000454 | FDN, SCBA, A36 STL ANGLE | 1 | 1 | 2014-06-18 | 14 | 2014-06-04 | EA | 0 | 0 | 1 | No | 2017-08-01 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-02-00S90 | 180100-000000454 | FDN, SCBA, A36 STL ANGLE | 1 | 1 | 2014-06-18 | 14 | 2014-06-04 | EA | 0 | 0 | 1 | No | 2017-08-01 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-02-0S25A | 780807-000000003 | STOWAGE, ASSY, EDUCTOR | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-09-19 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-02-0S42A | 780807-000000004 | STOWAGE, ASSY, EDUCTOR | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-09-19 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-05-V0002 | SRV525-031100020 | CONTRACT MOD, INCORP CF 2007 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-08-22 | 2017-10-27 | 0 | 0
8022 | 473 | 671 |  | 671-94-00016 | 712430480033-003 | WELD STUDS | 22 | 22 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 22 | No | 2014-09-08 | 2017-10-27 | 9.67 | 212.74 | 465 | 2012-04-10
8022 | 473 | 671 |  | 671-94-0001E | 180100-000000050 | CLIP, DRY ERASE BOARD | 4 | 4 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 0 | 4 | No | 2014-09-08 | 2017-10-27 | 3.27 | 13.08 | 467 | 2012-08-28
8022 | 473 | 671 |  | 671-94-0004N | 180100-000000054 | BRACKET, LITTER LOWER STWG | 1 | 1 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 0 | 1 | No | 2014-08-28 | 2017-10-27 | 22.28 | 22.28 | 467 | 2012-08-28
8022 | 473 | 671 |  | 671-94-000S4 | 180100-000000110 | FDN FEXT | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-09-08 | 2017-10-27 | 207.13 | 414.26 | 467 | 2012-08-28
8022 | 473 | 671 |  | 671-94-000S5 | 180100-000000111 | STAPLE ASSEMBLY | 18 | 15 | 2014-01-20 | 123 | 2013-09-19 | EA | 1 | 0 | 14 | No | 2014-09-08 | 2017-10-27 | 25.12 | 351.68 | 465 | 2015-02-12
8022 | 473 | 671 |  | 671-94-000S6 | 180100-000000112 | BRACKET, LITTER STOWAGE | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2014-09-08 | 2017-10-27 | 41.92 | 125.76 | 467 | 2012-08-28
8022 | 473 | 671 |  | 671-94-000S7 | 180100-000000113 | STOWAGE MEDICAL LOCKER | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 296.63 | 296.63 | 467 | 2012-08-28
8022 | 473 | 671 |  | 671-94-000S8 | 180100-000000114 | STAPLE ASSEMBLY | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-09-08 | 2017-10-27 | 18.05 | 36.1 | 467 | 2012-08-28
8022 | 473 | 671 |  | 671-94-0033A | 180100-000000294 | FND, FEXT | 2 | 2 | 2014-01-20 | 21 | 2013-12-30 | EA | 0 | 0 | 2 | No | 2014-09-08 | 2017-10-27 | 30.28 | 60.56 | 465 | 2013-01-11
8022 | 473 | 671 |  | 671-94-0033B | SRV523-030500036 | BACKING PLATE, FAB FROM 3/8" | 12 | 12 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 12 | No | 2014-05-11 | 2017-10-27 | 13.93 | 167.16 | 465 | 2013-04-17
8022 | 473 | 671 |  | 671-94-0040A | 180100-000000415 | MOUNTING PLATE, SUPPLIED BY | 2 | 2 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 2 | No | 2014-05-16 | 2017-10-27 | 43.16 | 86.32 | 465 | 2015-01-26
8022 | 473 | 671 |  | 671-97-00S71 | 780103-000000005 | AFFF (4) PAIL STOWAGE, ALUM | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-11-02 | 2017-10-27 | 0 | 0
8022 | 473 | 671 |  | 671-98-007AB | 704300-000000067 | GUSSET, SHORE POWER CABLE HO | 4 | 4 | 2015-09-04 | 112 | 2015-05-15 | EA | 0 | 0 | 4 | No | 2016-03-21 | 2017-10-27 | 0 | 0
8022 | 473 | 671 |  | 671-98-00S27 | 780200020000-002 | JBPDS REFRIGERATOR LOCK BAR | 1 | 1 | 2015-07-03 | 123 | 2015-03-02 | EA | 0 | 0 | 1 | No | 2017-08-18 | 2017-10-27 | 0 | 0
8022 | 473 | 712 |  | 712-03-00S10 | 780000020000-004 | AECM STWG RACK PART 1 OF 2, | 1 | 1 | 2015-04-13 | 120 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2017-02-06 | 2017-10-27 | 2804 | 2804 | 450 | 2009-10-09
8022 | 473 | 712 |  | 712-03-00S11 | 780000020000-005 | AECM STWG RACK PART 2 OF 2, | 1 | 1 | 2015-04-13 | 120 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2017-02-06 | 2017-10-27 | 222.58 | 222.58 | 450 | 2009-09-03
8022 | 473 | 712 |  | 712-03-00S12 | 780000020000-006 | EMPTY AECM DISPENSER STWG, | 1 | 1 | 2015-04-13 | 120 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2017-02-06 | 2017-10-27 | 1450 | 1450 | 403 | 2006-07-20
8022 | 473 | 982 |  | 982-01-00030 | SRV520-012400001 | LOAD BANK, 28 VDC FOR HELO | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-11-28 | 2017-10-27 | 1 | 1 | 471 | 2016-12-01
8022 | 473 | 986 |  | 986-99-PLPRT | TEST00-000001011 | PULPES TEST WASTE DISPOSAL | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-10-20 | 2017-10-27 | 1826.19 | 1826.19 | 465 | 2015-12-03
8022 | 473 | 992 |  | 992-01-40001 | SRV515-012900010 | SERVICES TO MOVE LCS-13 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2015-04-01 | 2017-10-27 | 30091 | 30091 | 475 | 2015-07-06
8022 | 473 | 243 |  | 243-01-00001-R03 | -R00 | REWORK, INSPECT WATER JET | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-06-15 | 2017-10-27 | 0 | 0
8022 | 473 | 262 |  | 262-01-VS001-R01 | ARCHIVE | SRVC, FLUSH LUBE OIL | 1 | 1 | 2017-03-24 | 123 | 2016-11-21 | LO | 0 | 0 | 1 | No | 2017-03-24 | 2017-03-24 | 0 | 0
8022 | 473 | 512 |  | 512-01-00008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-18 | 60 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 465 | 2011-11-07
8022 | 473 | 512 |  | 512-01-00014-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0 | 465 | 2011-12-15
8022 | 473 | 512 |  | 512-01-00015-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-00F24-S00 | -S00 | SRVC, FAN, FDN MODS, CF 2263 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-10 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0F32B-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0V07B-S00 | -S00 | DAMPER, SHUT OFF, MANUAL, 9" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0V08B-S00 | -S00 | DAMPER, SHUT OFF, MANUAL, 10 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0V30B-S00 | -S00 | DAMPER, SHUT OFF, MANUAL 9X9 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0V31B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 16" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0V33B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 45X2 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0V37B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 45X2 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-0V86B-S00 | -S00 | DAMPER, SHUT OFF, MANUAL, 14 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-SH005-S00 | -S00 | EXPEDITE FEE FOR DAMPERS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-12 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V0005-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | LO | 0 | 0 | 1 | No | 2014-05-21 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0006-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0009-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0010-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0011-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0012-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0013-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0014-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0015-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0019-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0020-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0021-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0022-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2014-05-21 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0023-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2014-05-21 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0024-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0024-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0025-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0027-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0028-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0029-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0032-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0034-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0035-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0036-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0038-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0039-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0040-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0041-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0043-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0044-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0045-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0046-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0047-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0048-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0049-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0050-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0051-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0052-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0053-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0054-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 467 | 2011-08-09
8022 | 473 | 512 |  | 512-01-V0055-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0056-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0057-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0058-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0059-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0060-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0061-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0062-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-06-04 | 60 | 2014-04-05 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0063-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0064-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0065-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-06-04 | 60 | 2014-04-05 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0066-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-06-04 | 60 | 2014-04-05 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0067-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-06-04 | 60 | 2014-04-05 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0068-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-06-04 | 60 | 2014-04-05 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0069-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0070-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0072-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0073-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0076-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0077-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0082-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0083-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0084-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0085-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2014-05-22 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0091-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0092-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-07-22 | 60 | 2014-05-23 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0093-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0094-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0121-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0121-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0124-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0126-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0127-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0128-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-07-22 | 60 | 2014-05-23 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0129-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0135-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-07 | 60 | 2014-01-06 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0136-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-07 | 60 | 2014-01-06 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0137-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-03-07 | 60 | 2014-01-06 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0138-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0145-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0149-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-27 | 60 | 2013-11-28 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0150-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0151-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0160-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0162-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0163-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0164-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V0165-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8022 | 473 | 512 |  | 512-01-V105B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 17X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V112B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 16" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V113B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 16" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V114B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 16" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V115B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 32X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V116B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 32X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V117B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 40X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V118B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 40X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V119B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 38X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V120B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 32X2 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V147B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 10X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V148B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 14X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V152B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 16 X | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V153B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 15X6 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V154B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 15X6 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V155B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 20" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V156B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 20" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V157B-S00 | -S00 | DAMPER, SHUT OFF, MANUAL, 5" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V158B-S00 | -S00 | DAMPER, SHUT OFF, MANUAL, 5" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V159B-S00 | -S00 | DAMPER, SHUT OFF, MANUAL, 5" | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-01-V167B-S00 | -S00 | DAMPER, SHUT OFF, AUTO, 20X1 | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-26 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-88-00344-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-22 | 60 | 2014-05-23 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0
8022 | 473 | 512 |  | 512-88-00344-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-07-22 | 60 | 2014-05-23 | EA | 0 | 0 | 1 | No | 2013-11-26 | 2017-10-27 | 0 | 0
8022 | 473 | 514 |  | 514-01-00001-802 | 681500-000000003 | WATER REGULATING VALVE MANIF | 1 | 1 | 2015-01-05 | 90 | 2014-10-07 | EA | 0 | 0 | 1 | No | 2013-05-23 | 2017-10-27 | 0 | 0
8022 | 473 | 514 |  | 514-01-00001-L65 | -L65 | EXTENDED WARRANTY | 1 | 1 | 2015-01-05 | 123 | 2014-09-04 | EA | 0 | 0 | 1 | No | 2013-05-23 | 2017-10-27 | 0 | 0 | 471 | 2013-03-25
8022 | 473 | 635 |  | 635-00-V0001-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2011-10-28
8022 | 473 | 637 |  | 637-00-V0001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-00-V0010-S00 | -S00 | CONTRACT MOD, INCORP CF 2470 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-AA-01010-001 | 090107-000000011 | PANEL, HINGED ACCESS, CRES | 6 | 6 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 6 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.06 | 450 | 2009-06-04
8022 | 473 | 637 |  | 637-AB-1001M-001 | 090103-000000014 | PANEL, BHD ACCESS, 25MM ALUM | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 444 | 444 | 450 | 2010-07-01
8022 | 473 | 637 |  | 637-PB-10050-001 | 090107-000000010 | PANEL, BHD, 25MM CRES FACED | 22 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 22 | 22 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-PB-10050-002 | 090107-000000007 | PANEL, BHD, 25MM CRES FACED | 10 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 10 | 10 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-PB-10050-003 | 090107-000000008 | PANEL, BHD, 25MM CRES FACED | 12 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 12 | 12 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-PB-10050-004 | 090107-000000009 | PANEL, BHD, 25MM CRES FACED | 9 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 9 | 9 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-PB-35010-001 | 090107-000000001 | PANEL, CEILING, STAINLESS ST | 43 | 43 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 43 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.43 | 450 | 2009-06-04
8022 | 473 | 637 |  | 637-PB-35010-001 | 090107-000000001 | PANEL, CEILING, STAINLESS ST | 43 | 43 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 43 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.43 | 450 | 2009-06-04
8022 | 473 | 637 |  | 637-PB-35010-002 | 090107-000000002 | PANEL, CEILING, STAINLESS ST | 8 | 8 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 8 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.08 | 450 | 2009-06-04
8022 | 473 | 637 |  | 637-PB-35010-003 | 090107-000000003 | PANEL, CEILING, STAINLESS ST | 7 | 7 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 7 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.07 | 450 | 2009-06-04
8022 | 473 | 637 |  | 637-PB-35010-004 | 090107-000000004 | PANEL, CEILING, STAINLESS ST | 13 | 13 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 13 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.13 | 450 | 2009-06-04
8022 | 473 | 637 |  | 637-PB-38030-009 | 090103-000000015 | PANEL, BHD, 25MM ALUMINUM FA | 2 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-PB-38030-015 | 090103-000000016 | PANEL, BHD, 25MM ALUMINUM FA | 10 | 10 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 10 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-PB-38030-016 | 090103-000000017 | PANEL, BHD, 25MM ALUMINUM FA | 3 | 3 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 3 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-PB-38030-017 | 090103-000000018 | PANEL, BHD, 25MM ALUMINUM FA | 13 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 13 | 13 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8022 | 473 | 637 |  | 637-SB-05150-001 | 090005-000000004 | HANGER SET, GALVANIZED STEEL | 20 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 20 | 20 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.2 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-SB-10020-001 | 090005-000000005 | TOP SHOE 16 GA | 13 | 13 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 13 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.13 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-SB-15050-001 | 090007-000000001 | T-CARRIER, CRES, 1MM THK | 6 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 6 | 6 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.06 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-SB-20050-001 | 090107-000000015 | COVER PROFILE, CRES, 0.6MM T | 6 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 6 | 6 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.06 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-SB-20100-001 | 090107-000000005 | TRIM, EDGE, CRES, 1MM THK | 11 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 11 | 11 | No | 2014-04-27 | 2017-10-27 | 0.01 | 0.11 | 450 | 2009-12-02
8022 | 473 | 637 |  | 637-SB-50010-001 | 090005-000000006 | BOTTOM SHOE, 18 GA GALVANEAL | 13 | 13 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 13 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.13 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-10010-001 | 090100-000000008 | END PROFILE | 6 | 6 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 6 | No | 2014-04-29 | 2017-10-27 | 29 | 174 | 450 | 2010-05-11
8022 | 473 | 637 |  | 637-TB-10010-003 | 090107-000000014 | END PROFILE | 8 | 8 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 8 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.08 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-10010-004 | 090100-000000009 | END PROFILE | 2 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2014-04-29 | 2017-10-27 | 17 | 34 | 450 | 2010-09-02
8022 | 473 | 637 |  | 637-TB-10010-006 | 090100-000000010 | END PROFILE | 4 | 4 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 4 | No | 2014-04-29 | 2017-10-27 | 17 | 68 | 450 | 2010-08-11
8022 | 473 | 637 |  | 637-TB-15010-001 | 090100-000000011 | INTERNAL CORNER PROFILE | 4 | 4 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 4 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.04 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-15010-005 | 090100-000000012 | INTERNAL CORNER PROFILE | 2 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-15010-008 | 090107-000000013 | INTERNAL CORNER PROFILE | 5 | 5 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 5 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.05 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-15020-001 | 090107-000000017 | ANGLE PROFILE, CRES, 1MM THK | 10 | 0 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 10 | 10 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.1 | 450 | 2009-12-02
8022 | 473 | 637 |  | 637-TB-15990-001 | 090105-000000002 | ANGLE, REINFORCEMENT | 2 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-20010-005 | 090100-000000013 | EXTERNAL CORNER PROFILE | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-20010-006 | 090100-000000014 | EXTERNAL CORNER PROFILE | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-20010-007 | 090107-000000012 | EXTERNAL CORNER PROFILE | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-2001R-003 | 090100-000000015 | EXTERNAL 25 MM RADIUS PROFIL | 2 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-2001R-005 | 090100-000000016 | EXTERNAL 25 MM RADIUS PROFIL | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2010-03-03
8022 | 473 | 637 |  | 637-TB-2001R-007 | 090107-000000016 | EXTERNAL 25 MM RADIUS PROFIL | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-06-08
8022 | 473 | 637 |  | 637-TB-20990-001 | 090105-000000003 | ANGLE, BACKING | 7 | 7 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 7 | No | 2014-04-29 | 2017-10-27 | 0 | 0 | 403 | 2005-03-10
8022 | 473 | 640 |  | 640-02-00023-801 | 740200-000000022 | CLIP, DECK, END TABLE | 2 | 2 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 2 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00028-801 | 740200-000000023 | CLIP, DECK, COFFEE TABLE | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00030-801 | 740200-000000009 | SUB-BASE, SOFA, ALUMINUM | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00040-801 | 740200-000000011 | SUBBASE, FOR (2) SIDEBOARD | 2 | 2 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 2 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.02 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00061-801 | 740200-000000013 | SUBBASE, LIBRARY CABINET, AL | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 144 | 144 | 450 | 2010-10-21
8022 | 473 | 640 |  | 640-02-00088-801 | 740200-000000016 | SUB-BASE, TABLE LEAF LOCKER | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00089-801 | 740200-000000018 | SUB-BASE, TABLE LEAF LOCKER | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00090-801 | 742300-000000004 | CLIP, DECK, ROUND TABLE, | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2014-12-03 | 2017-10-27 | 0.01 | 0.03 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00093-801 | 742300-000000020 | CLIP, DECK, SOLID TOP TABLE | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-00147-800 | 740200-000000005 | SUB-BASE, ENTERTAINMENT, ALU | 1 | 1 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0 | 0
8022 | 473 | 640 |  | 640-02-0017L-801 | 742300-000000023 | SUBBASE, DESK, SINGLE PEDEST | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 640 |  | 640-02-0030A-801 | 742300-000000025 | SUB-BASE, SOFA, ALUMINUM | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-28
8022 | 473 | 644 |  | 644-00-V0001-L02 | -L02 | MANUALS, TECHNICAL, PRELIMIN | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2014-12-05
8022 | 473 | 644 |  | 644-00-V0001-L08 | -L08 | DRAWINGS, PRELIMINARY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2014-12-05
8022 | 473 | 644 |  | 644-00-V0001-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2014-12-05
8022 | 473 | 644 |  | 644-00-V0001-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2014-12-05
8022 | 473 | 644 |  | 644-00-V0001-L15 | -L15 | DATA, WEIGHT | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2014-12-05
8022 | 473 | 644 |  | 644-00-V0001-L22 | -L22 | MANUALS, TECHNICAL, FINAL | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2014-12-05
8022 | 473 | 644 |  | 644-00-V0001-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2014-12-05
8022 | 473 | 651 |  | 651-00-V0001-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8022 | 473 | 651 |  | 651-01-00001-801 | 731201-000000002 | SHELVES, CRES, WITH EXTENDED | 1 | -1 | 2014-12-09 | 123 | 2014-08-08 | LO | 0 | 2 | 1 | No | 2015-04-09 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00002-801 | 731201-000000008 | SHELVES, CRES, WITH EXTENDED | 1 | -1 | 2014-12-09 | 123 | 2014-08-08 | LO | 0 | 2 | 1 | No | 2015-04-09 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00003-801 | 731201-000000004 | SHELVES, CRES, WITH EXTENDED | 2 | -2 | 2014-12-09 | 123 | 2014-08-08 | LO | 0 | 4 | 2 | No | 2015-04-09 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00007-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00009-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00010-802 | 731801-000000003 | BOWL, SST 220, 20 QT | 1 | 0 | 2014-12-09 | 160 | 2014-07-02 | EA | 0 | 1 | 1 | No | 2013-07-16 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00010-803 | 731801-000000004 | BEATER-ALU220, 20 QT ALUM B | 1 | 0 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 1 | 1 | No | 2013-07-16 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00010-804 | 731801-000000005 | DWHIP, SST220, 20 QT BOWL | 1 | 0 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 1 | 1 | No | 2013-07-16 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00010-805 | 731801-000000006 | SPLASH-LEX020, 20 QT BOWL | 1 | 0 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 1 | 1 | No | 2013-07-16 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00010-807 | 731801-000000007 | BOWL SCRAPPER, 20 QT | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-23 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00010-808 | 731801-000000008 | MIXER DOUGH ARM, HOBART | 1 | 1 | 2014-12-09 | 180 | 2014-06-12 | EA | 0 | 0 | 1 | No | 2017-09-28 | 2017-10-27 | 0 | 0
8022 | 473 | 651 |  | 651-01-00010-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00011-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00012-801 | 732501-000000002 | WATER WASH CONTROL PANEL, GA | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00012-802 | 732501-000000003 | 3/4" NPT VACUUM BREAKER, GAY | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00012-803 | 732501-000000004 | 3/4" NPT SEQUENCING SOLENOID | 2 | 2 | 2014-12-09 | 48 | 2014-10-22 | EA | 0 | 0 | 2 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00012-804 | 732501-000000005 | 3/4" NPT SEQUENCING SOLENOID | 2 | 2 | 2014-12-09 | 48 | 2014-10-22 | EA | 0 | 0 | 2 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00012-805 | 732501-000000006 | DETERGENT LINE ANTI SIPHON | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00012-806 | 732501-000000007 | ADAPTER, 3/8" COMPRESSION | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00012-807 | 732501-000000008 | 1/4" COPPER TUBING | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00012-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00013-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00014-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00015-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00016-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00017-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00018-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00019-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00020-801 | 733003-000000002 | LEVER DRAIN, 2" | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0.01 | 0.01 | 481 | 2017-08-04
8022 | 473 | 651 |  | 651-01-00020-802 | 733003-000000003 | FAUCET W/12" SWING NOZZLE | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00020-803 | 733003-000000004 | PRE-RINSE UNIT | 1 | 1 | 2014-12-09 | 42 | 2014-10-28 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00020-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00021-803 | 733901-000000005 | LEVER DRAIN, 2" | 1 | 0 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 1 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 479 | 2016-06-19
8022 | 473 | 651 |  | 651-01-00021-804 | 733901-000000007 | FAUCET, WALL MTD, 8" CTRS | 2 | 2 | 2014-12-09 | 180 | 2014-06-12 | EA | 0 | 0 | 2 | No | 2015-09-08 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00021-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00022-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00023-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00024-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00028-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00035-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00036-801 | 733003-000000005 | FAUCET, SINGLE PANTRY | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-08 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00036-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00038-800 | 734001-000000009 | DISPLAY, COLD FOOD COUNTER | 2 | 1 | 2014-12-09 | 180 | 2014-06-12 | EA | 0 | 1 | 2 | No | 2015-09-08 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00038-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00039-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00042-801 | 733003-000000006 | PRE-RINSE UNIT | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8022 | 473 | 651 |  | 651-01-00042-802 | 733003-000000007 | FAUCET, ADD-ON FOR PRE-RINSE | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2013-07-17 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00122-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-00123-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-0048A-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8022 | 473 | 651 |  | 651-01-G032A-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2014-05-01 | 2017-10-27 | 0 | 0
8022 | 473 | 651 |  | 651-01-G032A-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2014-05-01 | 2017-10-27 | 0 | 0
8022 | 473 | 664 |  | 664-02-00119-800 | 780800-000000005 | SCBA STWG BAG | 34 | 34 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 34 | No | 2014-09-23 | 2017-10-27 | 0.01 | 0.34 | 450 | 2010-01-20
8022 | 473 | 664 |  | 664-02-00121-801 | 780600-000000007 | SUB-BASE, SCBA LOCKER, MDL-7 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-19 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-08-04
8022 | 473 | 664 |  | 664-02-00123-801 | 780600-000000009 | SUB-BASE, SCBA LOCKER, MDL-7 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-19 | 2017-10-27 | 203 | 203 | 450 | 2009-04-28
8022 | 473 | 664 |  | 664-02-00170-801 | 780600-000000002 | SUB-BASE, SCBA LOCKER | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-19 | 2017-10-27 | 0 | 0
8022 | 473 | 986 |  | 986-01-60001-R01 | TEST00-000001065 | NETWORK INTERFACE KIT | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2016-02-18 | 2017-10-27 | 0 | 0
8024 | 473 | 167 |  | 167-01-00012 | 610512-000000001 | MISC PARTS,AVTN MISSION ZONE | 1 | 1 | 2015-02-12 | 140 | 2014-09-25 | EA | 0 | 0 | 1 | No | 2014-07-10 | 2017-10-27 | 0 | 0 | 471 | 2014-08-04
8024 | 473 | 243 |  | 243-01-00002 | 204100-000000001 | BOOST SHAFT BRAKE ASL 2/160 | 2 | 2 | 2015-01-16 | 180 | 2014-07-20 | SYS | 0 | 0 | 2 | No | 2016-03-16 | 2017-10-27 | 25000 | 50000 | 120 | 2013-05-03
8024 | 473 | 304 |  | 304-00-00127 | 309301140113-001 | CABLE, COAXIAL, M17/190-0000 | 2405 | 470 | 2014-01-20 | 160 | 2013-08-13 | LF | 85 | 0 | 385 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8024 | 473 | 304 |  | 304-00-00171 | 308401140113-174 | CABLE, COAXIAL, M17/191-0000 | 1600 | 1600 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 1500 | 100 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8024 | 473 | 304 |  | 304-00-00340 | 309602151201-001 | CABLE, ELECTRIC, M27500-22RC | 1549 | 1549 | 2014-01-20 | 120 | 2013-09-22 | FT | 0 | 0 | 1549 | No | 2014-02-11 | 2017-10-27 | 0 | 0 | 450 | 2009-08-20
8024 | 473 | 311 |  | 311-01-VS004 | -VSR | VSR, 100 HR MAINT, SSDG 1-4 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-10-02 | 2017-10-27 | 0 | 0
8024 | 473 | 410 |  | 410-01-00005 | 370400000004-001 | PHONE, GLOBAL | 83 | 4 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 2 | 2 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8024 | 473 | 410 |  | 410-01-00022 | 360101060108-001 | NAVY CONNECTION BOX, WATERTI | 2 | 2 | 2014-10-10 | 84 | 2014-07-18 | EA | 0 | 0 | 2 | No | 2017-05-11 | 2017-10-27 | 0 | 0
8024 | 473 | 573 |  | 573-01-00063 | 230000-000000005 | KIT, LRHS SHOCK MODS | 1 | 1 | 2015-07-03 | 180 | 2015-01-04 | EA | 0 | 0 | 1 | No | 2017-07-12 | 2017-10-27 | 0 | 0
8024 | 473 | 573 |  | 573-10-00003 | 232800-000000001 | CRANE BRIDGE, AMZ, PAYLOAD | 1 | 1 | 2015-06-15 | 123 | 2015-02-12 | EA | 0 | 0 | 1 | No | 2013-06-06 | 2017-10-27 | 51834.34 | 51834.34
8024 | 473 | 573 |  | 573-10-00004 | 230000-000000004 | KIT, PAYLOAD CRANE, SHOCK MO | 1 | 1 | 2015-06-22 | 123 | 2015-02-19 | EA | 0 | 0 | 1 | No | 2017-06-20 | 2017-10-27 | 50745 | 50745 | 450 | 2011-03-04
8024 | 473 | 604 |  | 604-01-00003 | 727600-000000003 | PADLOCK, HIGH SECURITY, SHRO | 24 | 24 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 24 | No | 2014-09-24 | 2017-10-27 | 0 | 0 | 450 | 2011-06-24
8024 | 473 | 610 |  | 610-01-00003 | 760103-000000003 | FIRE EXTINGUISHER, DCHEM (PK | 3 | 3 | 2014-01-20 | 56 | 2013-11-25 | EA | 2 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 667.4 | 667.4
8024 | 473 | 982 |  | 982-01-00109 | SRV650-011000001 | COMPLETE DEMO TO SUPPORT BDT | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-07-05 | 2017-10-27 | 38220.68 | 38220.68 | 471 | 2017-10-18
8024 | 473 | 982 |  | 982-01-00110 | SRV650-011000002 | 2 TECHS TO SUPPORT BDT & BST | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-07-05 | 2017-10-27 | 5223.39 | 5223.39 | 469 | 2017-09-19
8024 | 473 | 167 |  | 167-01-00006-200 | 610512-000000047 | SEAL, KNIFE EDGE | 1 | 1 | 2015-02-12 | 360 | 2014-02-17 | EA | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 856.8 | 856.8 | 403 | 2007-05-18
8024 | 473 | 167 |  | 167-01-00006-201 | 610512-000000048 | SEAL, DOG SHAFT | 6 | 6 | 2015-02-12 | 360 | 2014-02-17 | EA | 0 | 0 | 6 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 469 | 2014-06-16
8024 | 473 | 167 |  | 167-01-00006-802 | 610512-000000051 | MISC PARTS,AVTN MISSION ZONE | 1 | 1 | 2015-02-12 | 140 | 2014-09-25 | EA | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 475 | 2014-08-04
8024 | 473 | 167 |  | 167-01-00006-803 | 610512-000000052 | PLATFORM LIFTING TACKLE | 1 | 1 | 2015-02-12 | 120 | 2014-10-15 | EA | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 467 | 2011-09-30
8024 | 473 | 167 |  | 167-01-00006-L47 | -L47 | GOVERNMENT INSPECTION | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | LO | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 477 | 2017-05-16
8024 | 473 | 167 |  | 167-01-00012-813 | 610512-000000015 | BELL | 2 | 1 | 2014-12-22 | 370 | 2013-12-17 | EA | 0 | 0 | 1 | No | 2014-07-14 | 2017-10-27 | 0 | 0
8024 | 473 | 167 |  | 167-01-00012-844 | 610512-000000055 | SHACKLE, F169915 F/N 33 | 2 | 2 | 2015-02-12 | 112 | 2014-10-23 | EA | 0 | 0 | 2 | No | 2015-07-23 | 2017-10-27 | 0 | 0 | 483 | 2017-05-16
8024 | 473 | 169 |  | 169-01-00007-300 | 610312-000000032 | SEAL, CLEAN GRIP, EPDM, 100 | 1 | 1 | 2015-03-17 | 123 | 2014-11-14 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 481 | 2016-02-03
8024 | 473 | 169 |  | 169-01-00007-301 | 610312-000000033 | SEAL, CLEAN GRIP, EPDM, 100 | 1 | 1 | 2015-03-17 | 123 | 2014-11-14 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 481 | 2016-02-03
8024 | 473 | 169 |  | 169-01-00007-302 | 610312-000000034 | SEAL, CLEAN GRIP, EPDM, 100 | 1 | 1 | 2015-03-17 | 123 | 2014-11-14 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 481 | 2016-02-03
8024 | 473 | 169 |  | 169-01-00007-835 | 610312-000000070 | HANGAR DOOR, ADHESIVES AND | 1 | 0 | 2015-03-17 | 180 | 2014-09-18 | EA | 0 | 1 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0
8024 | 473 | 169 |  | 169-01-00007-836 | 610312-000000071 | HANGAR DOOR, SHORT HINGE PIN | 36 | 0 | 2015-03-17 | 180 | 2014-09-18 | EA | 0 | 36 | 2 | No | 2013-06-03 | 2017-10-27 | 0 | 0
8024 | 473 | 169 |  | 169-01-00007-882 | 610312-000000117 | HANGAR DOOR,INSTRUCTION PLAT | 1 | 0 | 2015-03-17 | 180 | 2014-09-18 | EA | 0 | 1 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0
8024 | 473 | 202 |  | 202-01-00213-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 25 | 25 | 450 | 2009-09-03
8024 | 473 | 233 |  | 233-01-00001-827 | 230200-000000079 | WASHER, METRIC HARD STEEL | 384 | 192 | 2015-01-05 | 324 | 2014-02-15 | EA | 0 | 0 | 192 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8024 | 473 | 233 |  | 233-01-00001-8A3 | 230200-000000141 | WASHER, PART OF | 128 | 128 | 2015-01-05 | 123 | 2014-09-04 | EA | 127 | 0 | 1 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8024 | 473 | 233 |  | 233-01-00001-8A4 | 230200-000000142 | WASHER, FOR FITTED BOLT | 16 | 16 | 2015-01-05 | 123 | 2014-09-04 | EA | 15 | 0 | 1 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8024 | 473 | 233 |  | 233-01-00001-8A5 | 230200-000000143 | BOLT, HEX HEAD, M14 X 40 | 64 | 64 | 2015-01-05 | 123 | 2014-09-04 | EA | 63 | 0 | 1 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8024 | 473 | 234 |  | 234-01-00001-101 | 230100-000000014 | LIFTING PAD, MT 30 | 4 | 4 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 4 | No | 2013-11-19 | 2017-10-27 | 0 | 0 | 475 | 2017-05-15
8024 | 473 | 234 |  | 234-01-00001-102 | 230100-000000015 | BOLTS, LIFTING PAD | 32 | 32 | 2014-11-19 | 14 | 2014-11-05 | EA | 0 | 0 | 32 | No | 2013-11-19 | 2017-10-27 | 0 | 0 | 475 | 2017-05-15
8024 | 473 | 234 |  | 234-01-00001-833 | 230100-000000065 | ESS DRIVE CABINET | 2 | 2 | 2014-11-19 | 140 | 2014-07-02 | EA | 0 | 0 | 2 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 475 | 2017-05-15
8024 | 473 | 234 |  | 234-01-00001-834 | 230100-000000066 | PIPE SPOOL | 4 | 2 | 2014-11-19 | 140 | 2014-07-02 | EA | 0 | 0 | 2 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8024 | 473 | 234 |  | 234-01-00001-857 | 230100-000000089 | MOUNT, SHOCK | 56 | 48 | 2014-11-19 | 140 | 2014-07-02 | EA | 0 | 0 | 48 | No | 2013-11-20 | 2017-10-27 | 0 | 0
8024 | 473 | 234 |  | 234-01-00001-8L7 | 230100-000000235 | COLLAR | 4 | 4 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 4 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8024 | 473 | 234 |  | 234-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 475 | 2017-05-15
8024 | 473 | 234 |  | 234-01-00006-S00 | -S00 | KIT, ESS FILTER/RECTIFIER | 1 | 1 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 1 | No | 2017-06-05 | 2017-10-27 | 0 | 0
8024 | 473 | 241 |  | 241-01-00001-804 | 202800-000000053 | GEAR UNIT ASL 2-160 STARBOAR | 1 | 1 | 2015-08-24 | 123 | 2015-04-23 | EA | 0 | 0 | 1 | No | 2013-11-20 | 2017-10-27 | 0 | 0
8024 | 473 | 241 |  | 241-01-00001-L20 | -L20 | SUPPORT, VENDOR | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | LO | 0 | 0 | 1 | No | 2014-08-19 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8024 | 473 | 241 |  | 241-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8024 | 473 | 241 |  | 241-01-00002-S00 | -S00 | KIT, REDUCTION GEAR, SNUBBER | 1 | 1 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 1 | No | 2017-04-26 | 2017-10-27 | 0 | 0
8024 | 473 | 241 |  | 241-01-00002-S00 | -S00 | KIT, REDUCTION GEAR, SNUBBER | 1 | 1 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 1 | No | 2017-04-26 | 2017-10-27 | 0 | 0
8024 | 473 | 241 |  | 241-01-00003-S00 | -S00 | KIT, REDUCTION GEAR, RETROFI | 1 | 1 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 1 | No | 2017-06-05 | 2017-10-27 | 0 | 0
8024 | 473 | 241 |  | 241-01-00005-S00 | -S00 | KIT, REDUCTION GEAR, HMI PAN | 1 | 1 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 1 | No | 2017-06-05 | 2017-10-27 | 0 | 0
8024 | 473 | 243 |  | 243-01-00001-832 | 202000-000000032 | CLAMP, J500466CCG-1 | 2 | 2 | 2015-01-05 | 123 | 2014-09-04 | EA | 0 | 1 | 1 | No | 2013-11-22 | 2017-10-27 | 0 | 0
8024 | 473 | 243 |  | 243-01-00001-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-01-05 | 60 | 2014-11-06 | LO | 0 | 0 | 1 | No | 2014-08-08 | 2017-10-27 | 0 | 0 | 469 | 2013-06-11
8024 | 473 | 243 |  | 243-01-00001-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-01-05 | 60 | 2014-11-06 | LO | 0 | 0 | 1 | No | 2014-08-08 | 2017-10-27 | 0 | 0 | 469 | 2013-06-11
8024 | 473 | 247 |  | 247-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-25 | 60 | 2014-12-27 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8024 | 473 | 252 |  | 252-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 475 | 2017-05-15
8024 | 473 | 252 |  | 252-01-00001-L63 | -L63 | COMPUTER SOFTWARE/PROGRAM | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2014-08-07 | 2017-10-27 | 0 | 0 | 479 | 2017-05-18
8024 | 473 | 252 |  | 252-01-00001-L64 | -L64 | COMPUTER SOFTWARE/PROGRAM | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2014-08-07 | 2017-10-27 | 0 | 0 | 479 | 2017-05-18
8024 | 473 | 252 |  | 252-01-00006-S00 | -S00 | KIT, CANMAN, SHOCK MODS | 1 | 1 | 2015-03-04 | 123 | 2014-11-01 | EA | 0 | 0 | 1 | No | 2017-06-05 | 2017-10-27 | 0 | 0
8024 | 473 | 252 |  | 252-01-00007-S00 | -S00 | KIT, WATERJET CONTROL SYSTEM | 1 | 1 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 1 | No | 2017-06-05 | 2017-10-27 | 0 | 0
8024 | 473 | 311 |  | 311-01-00001-830 | 414900-000000025 | RESILIENT SUBBASE, D0201215A | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-03-13 | 2017-10-27 | 0 | 0 | 483 | 2017-07-11
8024 | 473 | 311 |  | 311-01-00001-831 | 414900-000000026 | PREHEATER/PRELUBE, 00C52300A | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-03-13 | 2017-10-27 | 0 | 0 | 477 | 2017-06-30
8024 | 473 | 311 |  | 311-01-00001-836 | 414900-000000031 | PART OF EXHAUST, 00F58700 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-03-13 | 2017-10-27 | 0 | 0 | 477 | 2017-06-30
8024 | 473 | 311 |  | 311-01-00001-837 | 414900-000000032 | V1708C2ME SET, GEP02005652 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-03-13 | 2017-10-27 | 0 | 0 | 477 | 2017-06-30
8024 | 473 | 311 |  | 311-01-00001-838 | 414900-000000033 | CONTROL SYSTEM, DECS-00 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-03-13 | 2017-10-27 | 0 | 0 | 477 | 2017-06-30
8024 | 473 | 311 |  | 311-01-00001-839 | 414900-000000034 | LOOSE PARTS, GSP02005652 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-03-13 | 2017-10-27 | 0 | 0 | 477 | 2017-06-30
8024 | 473 | 410 |  | 410-01-00001-875 | 410100-000000088 | ADAPTER, CONTACT, CRIMP, | 42 | 42 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 3 | 39 | No | 2014-02-13 | 2017-10-27 | 0 | 0
8024 | 473 | 410 |  | 410-01-00001-8WN | 410100-000000143 | SERVER, 8 CORE, 2X300GB | 2 | 2 | 2014-01-20 | 48 | 2013-12-03 | EA | 0 | 0 | 2 | No | 2015-02-09 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 411 |  | 411-01-00017-S00 | 415400-000000001 | COMMAND & DECISION SYSTEM (C | 5 | 5 | 2017-04-12 | 123 | 2016-12-10 | EA | 0 | 0 | 5 | No | 2017-04-12 | 2017-04-12 | 0 | 0
8024 | 473 | 415 |  | 415-01-00001-206 | 410100-000000002 | ASSY, COMMERCIAL PC--3EH TOW | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00001-219 | 410100-000000003 | SAFETY LABEL | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00001-220 | 410100-000000004 | CCA, PCI, SERVER ADP | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00001-221 | 410100-000000005 | CONNECTOR ASSEMBLY | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00001-222 | 410100-000000006 | SCREW, MACHINE, FLAT | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00001-223 | 410100-000000007 | WORKSTATION, DELL, P/N:79227 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00001-224 | 410100-000000008 | CCA, VIDEO FRAME | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00001-225 | 410100-000000009 | BRACKET, PC BOARD | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 415 |  | 415-01-00017-S00 | -S00 | PRINTER, LASERJET, B & W, HP | 6 | 6 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 6 | No | 2017-05-19 | 2017-10-27 | 0 | 0
8024 | 473 | 420 |  | 420-01-00001-S01 | -S00 | ALARM SWITCHBOARD, IC/SM-4, | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-08 | 2017-10-27 | 0 | 0
8024 | 473 | 420 |  | 420-01-00001-S02 | 410201-000000002 | ALARM RELAY BOX, C-4LN100 | 1 | 1 | 2017-04-12 | 120 | 2016-12-13 | EA | 0 | 0 | 1 | No | 2017-04-12 | 2017-04-12 | 0 | 0
8024 | 473 | 423 |  | 423-01-00002-S03 | -S00 | PRINTER, HOLSTER | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8024 | 473 | 426 |  | 426-01-00002-870 | 413900-000000119 | ROUND SHELL CONNECTOR | 13 | 12 | 2014-01-20 | 48 | 2013-12-03 | EA | 0 | 0 | 12 | No | 2014-02-12 | 2017-10-27 | 0 | 0
8024 | 473 | 432 |  | 432-05-00001-830 | 410600-000000027 | RF CONNECTOR, N MALE, ANDREW | 7 | 6 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 6 | No | 2014-02-13 | 2017-10-27 | 0 | 0
8024 | 473 | 432 |  | 432-05-00001-831 | 410600-000000028 | RF CONNECTOR, N FEMALE | 7 | 7 | 2014-01-20 | 120 | 2013-09-22 | EA | 1 | 0 | 6 | No | 2014-02-13 | 2017-10-27 | 0 | 0
8024 | 473 | 432 |  | 432-05-00001-864 | 410600-000000046 | BATTERY IMPRES FM IMMERSIBLE | 70 | 70 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 60 | 10 | No | 2014-02-13 | 2017-10-27 | 0 | 0
8024 | 473 | 432 |  | 432-05-00001-867 | 410600-000000049 | BELT CLIP KIT | 70 | 70 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 60 | 10 | No | 2014-02-13 | 2017-10-27 | 0 | 0
8024 | 473 | 438 |  | 438-01-00001-S69 | 410200-000000097 | ANTENNA, GPS, TRIMBLE, L1/L2 | 2 | 2 | 2017-04-12 | 123 | 2016-12-10 | EA | 0 | 0 | 2 | No | 2017-04-12 | 2017-04-12 | 0 | 0
8024 | 473 | 441 |  | 441-01-00001-804 | 412200-000000017 | ANTENNA, LOS, UHF, AS-4163/U | 3 | 3 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 3 | No | 2014-04-11 | 2017-10-27 | 0 | 0
8024 | 473 | 441 |  | 441-01-00001-8F1 | 412200-000000206 | GCS BIT DRIVER TX | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2016-07-29 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 441 |  | 441-01-00001-8F2 | 412200-000000207 | GCS AUDIO MIXER NO. 1 & 2 | 2 | 2 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 2 | No | 2016-07-29 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 441 |  | 441-01-00001-8FL | 412200-000000208 | GCS AUDIO MIXER NO. 3 & 4 | 2 | 2 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 2 | No | 2016-07-29 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 441 |  | 441-01-00002-806 | 412200-000000165 | RADIO, PRC-117 (LMCO SUPPLIE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-07-23 | 2017-10-27 | 0 | 0 | 479 | 2017-05-18
8024 | 473 | 441 |  | 441-01-00002-830 | 412200-000000187 | IRIDIUM MODEM (LMCO SUPPLIED | 1 | 1 | 2014-01-20 | 48 | 2013-12-03 | EA | 0 | 0 | 1 | No | 2014-07-23 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 441 |  | 441-01-00008-801 |  | DLA BATTERIES FOR AN/URC-141 | 1 | 1 | 2015-07-03 | 120 | 2015-03-05 | EA | 0 | 0 | 1 | No | 2016-08-15 | 2017-10-27 | 0 | 0 | 475 | 2017-08-04
8024 | 473 | 441 |  | 441-01-00013-S04 | 414200-000000006 | MOUNTING KIT, EPIRB | 2 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8024 | 473 | 441 |  | 441-01-00016-822 | 410600-000000075 | MICROPHONE | 1 | 1 | 2015-04-27 | 120 | 2014-12-28 | EA | 0 | 0 | 1 | No | 2016-07-29 | 2017-10-27 | 0 | 0 | 485 | 2017-07-26
8024 | 473 | 441 |  | 441-01-00016-S12 | 410600-000000074 | SPEAKER, REMOTE, VHF, EXTERN | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8024 | 473 | 441 |  | 441-01-00016-S21 | -S00 | NAVY CONNECTION BOX, SUBMERS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-10 | 2017-10-27 | 74 | 74 | 477 | 2017-06-13
8024 | 473 | 453 |  | 453-01-00001-80R | 412500-000000032 | FUSE 10A 250 V T | 10 | 10 | 2014-01-20 | 123 | 2013-09-19 | EA | 1 | 0 | 9 | No | 2015-02-10 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-80S | 412500-000000033 | FUSE 3A 125 V FF | 10 | 10 | 2014-01-20 | 123 | 2013-09-19 | EA | 1 | 0 | 9 | No | 2015-02-10 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-80T | 412500-000000034 | FUSE 5A 125 V FF | 10 | 10 | 2014-01-20 | 123 | 2013-09-19 | EA | 1 | 0 | 9 | No | 2015-02-10 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-81J | 412500-000000048 | CABLE W100 | 2 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2015-02-11 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-81J | 412500-000000048 | CABLE W100 | 2 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2015-02-11 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-81L | 412500-000000049 | CABLE W177 | 2 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2015-02-11 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-81V | 412500-000000056 | CABLE W211 | 2 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2015-02-11 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-81X | 412500-000000057 | CABLE W92 | 2 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2015-02-11 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-82A | 412500-000000060 | GASKET | 2 | 1 | 2014-01-20 | 96 | 2013-10-16 | EA | 0 | 0 | 1 | No | 2015-02-11 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-83A | 412500-000000084 | EYE BOLT (CABINET 2, 3, AND | 12 | 12 | 2014-01-20 | 96 | 2013-10-16 | EA | 0 | 4 | 8 | No | 2015-02-10 | 2017-10-27 | 0 | 0
8024 | 473 | 453 |  | 453-01-00001-84B | 412500-000000116 | ATTENUATOR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2016-05-26 | 2017-10-27 | 0 | 0 | 475 | 2017-05-16
8024 | 473 | 453 |  | 453-01-00001-84C | 412500-000000117 | ATTENUATOR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2016-05-26 | 2017-10-27 | 0 | 0 | 475 | 2017-05-16
8024 | 473 | 453 |  | 453-01-00001-84D | 412500-000000118 | ATTENUATOR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2016-05-26 | 2017-10-27 | 0 | 0 | 475 | 2017-05-16
8024 | 473 | 453 |  | 453-01-00001-84E | 412500-000000119 | ATTENUATOR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2016-05-26 | 2017-10-27 | 0 | 0 | 475 | 2017-05-16
8024 | 473 | 453 |  | 453-01-00001-84F | 412500-000000120 | ATTENUATOR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2016-05-26 | 2017-10-27 | 0 | 0 | 475 | 2017-05-16
8024 | 473 | 453 |  | 453-01-00001-84G | 412500-000000121 | ATTENUATOR | 2 | 2 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 2 | No | 2016-05-26 | 2017-10-27 | 0 | 0 | 475 | 2017-05-16
8024 | 473 | 453 |  | 453-01-00001-8S3 | 412500-000000207 | ST & E - FUNNEL HOSE, FC-77 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-05-26 | 2017-10-27 | 0 | 0 | 475 | 2017-05-16
8024 | 473 | 472 |  | 472-01-00001-203 | 414500-000000005 | CIRCUIT CARD ASSEMBLY | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-204 | 414500-000000006 | CIRCUIT CARD ASSEMBLY | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-205 | 414500-000000007 | CIRCUIT CARD ASSEMBLY | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-206 | 414500-000000008 | CIRCUIT CARD ASSEMBLY | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-207 | 414500-000000009 | SWITCH, ETHERNET, 023068VC-2 | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-208 | 414500-000000010 | CONVERTER, FREQUENCY | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-209 | 414500-000000011 | FILTER, RADIO FREQUENCY | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-210 | 414500-000000012 | INLINE AMPLIFER, 023200AD-1 | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-211 | 414500-000000013 | DISK DRIVE UNIT, 026626AD-1 | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-212 | 414500-000000014 | FAN, TUBEAXIAL, 023120AI-1 | 1 | 1 | 2015-09-04 | 123 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-15 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 472 |  | 472-01-00001-808 | 414500-000000024 | CONNECTOR, L734/P/NI | 4 | 4 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 4 | No | 2015-03-20 | 2017-10-27 | 0 | 0 | 485 | 2017-07-27
8024 | 473 | 492 |  | 492-01-00001-800 | 412800-000000002 | TRACK SUBSYSTEM | 1 | 1 | 2015-07-23 | 80 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2014-05-13 | 2017-10-27 | 0 | 0 | 471 | 2013-03-28
8024 | 473 | 492 |  | 492-01-00001-851 | 413100-000000004 | GCS WORKSTATION #1 (AVO) | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2016-07-22 | 2017-10-27 | 0 | 0
8024 | 473 | 492 |  | 492-01-00001-852 | 413100-000000001 | GCS WORKSTATION #1 HEADSET | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2016-07-22 | 2017-10-27 | 0 | 0
8024 | 473 | 492 |  | 492-01-00001-853 | 413100-000000002 | GCS WORKSTATION #2 (MPO) | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2016-07-22 | 2017-10-27 | 0 | 0
8024 | 473 | 492 |  | 492-01-00001-854 | 413100-000000003 | GCS WORKSTATION #2 HEADSET | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2016-07-22 | 2017-10-27 | 0 | 0
8024 | 473 | 555 |  | 555-07-E0002-804 | 681014-000000005 | UNLOADING VALVE REPAIR KIT | 2 | 2 | 2015-01-12 | 105 | 2014-09-29 | EA | 0 | 0 | 2 | No | 2017-02-01 | 2017-10-27 | 0 | 0 | 403 | 2005-04-25
8024 | 473 | 565 |  | 565-01-00001-819 | 230900-000000021 | HPU, INTERCEPTOR, | 2 | 1 | 2015-01-05 | 180 | 2014-07-09 | EA | 0 | 0 | 1 | No | 2013-05-10 | 2017-10-27 | 0 | 0
8024 | 473 | 565 |  | 565-01-00001-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2015-01-05 | 60 | 2014-11-06 | LO | 0 | 0 | 1 | No | 2013-05-10 | 2017-10-27 | 0 | 0 | 485 | 2017-08-02
8024 | 473 | 565 |  | 565-01-00001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-07-09 | 60 | 2015-05-10 | EA | 0 | 0 | 1 | No | 2016-04-07 | 2017-10-27 | 0 | 0 | 485 | 2017-08-02
8024 | 473 | 565 |  | 565-01-00001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-01-05 | 123 | 2014-09-04 | LO | 0 | 0 | 1 | No | 2013-05-10 | 2017-10-27 | 0 | 0 | 485 | 2017-08-02
8024 | 473 | 571 |  | 571-01-00200-L04 | -L04 | PROCEDURES, IN-PLANT TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-22 | 2017-10-27 | 500 | 500 | 479 | 2017-04-06
8024 | 473 | 573 |  | 573-01-00002-812 | 232400-000000082 | ASSEMBLY, COLLECTOR, LRHS RA | 4 | 4 | 2015-06-15 | 390 | 2014-05-21 | EA | 0 | 0 | 4 | No | 2013-06-04 | 2017-10-27 | 0 | 0
8024 | 473 | 573 |  | 573-01-00002-819 | 232400-000000089 | HELICAL GEAR RACK | 11 | 11 | 2015-06-15 | 123 | 2015-02-12 | EA | 0 | 0 | 11 | No | 2013-06-04 | 2017-10-27 | 0 | 0 | 479 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-842 | 232400-000000112 | FASTENER, SEALING STRIP | 60 | 60 | 2015-06-15 | 14 | 2015-06-01 | EA | 32 | 0 | 28 | No | 2013-06-04 | 2017-10-27 | 0 | 0
8024 | 473 | 573 |  | 573-01-00002-852 | 232400-000000121 | CHAIN TENSIONER ASSEMBLY W/ | 2 | 2 | 2015-06-15 | 123 | 2015-02-12 | EA | 0 | 1 | 1 | No | 2013-06-04 | 2017-10-27 | 0 | 0
8024 | 473 | 573 |  | 573-01-00002-897 | 232400-000000166 | ASSEMBLY, TRUCK, END, TROLLE | 4 | 4 | 2015-06-15 | 123 | 2015-02-12 | EA | 0 | 0 | 4 | No | 2015-03-27 | 2017-10-27 | 0 | 0 | 475 | 2016-06-17
8024 | 473 | 573 |  | 573-01-00002-8A2 | 232400-000000171 | SHIM SET | 4 | 4 | 2015-06-16 | 123 | 2015-02-13 | EA | 0 | 0 | 4 | No | 2015-03-27 | 2017-10-27 | 0 | 0 | 475 | 2016-06-17
8024 | 473 | 573 |  | 573-01-00002-8A3 | 232400-000000172 | CHAIN #50 | 4 | 4 | 2015-06-16 | 123 | 2015-02-13 | EA | 0 | 0 | 4 | No | 2015-03-27 | 2017-10-27 | 0 | 0 | 479 | 2017-03-17
8024 | 473 | 573 |  | 573-01-00002-8A4 | 232400-000000173 | CAPSCREW, HEX HD | 24 | 24 | 2015-06-16 | 123 | 2015-02-13 | EA | 0 | 0 | 24 | No | 2015-03-27 | 2017-10-27 | 0 | 0 | 477 | 2016-12-07
8024 | 473 | 573 |  | 573-01-00002-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | LO | 0 | 0 | 1 | No | 2013-06-04 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-L07 | -L07 | REPORT, SHIPBOARD TEST, IAW | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | LO | 0 | 0 | 1 | No | 2013-06-04 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | LO | 0 | 0 | 1 | No | 2013-06-04 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-L15 | -L15 | DATA, WEIGHT | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-L20 | -L20 | SUPPORT, VENDOR | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-L51 | -L51 | DATA, FOR WEIGHT CRITICAL IT | 1 | 1 | 2015-06-15 | 60 | 2015-04-16 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 477 | 2015-11-20
8024 | 473 | 573 |  | 573-01-00002-S00 | -S00 | LRHS SHOCK RETROFIT, CF 2133 | 1 | 1 | 2015-07-03 | 123 | 2015-03-02 | EA | 0 | 0 | 1 | No | 2017-05-10 | 2017-10-27 | 0 | 0
8024 | 473 | 573 |  | 573-01-00017-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2015-06-26 | 60 | 2015-04-27 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 450 | 2011-10-31
8024 | 473 | 573 |  | 573-01-00017-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-06-26 | 60 | 2015-04-27 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 450 | 2011-10-31
8024 | 473 | 573 |  | 573-01-00017-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-06-26 | 60 | 2015-04-27 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 450 | 2011-10-31
8024 | 473 | 573 |  | 573-01-00063-S00 | -S00 | KIT, LRHS SHOCK MODS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-12 | 2017-10-27 | 0 | 0
8024 | 473 | 573 |  | 573-09-00002-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-07-16 | 60 | 2015-05-17 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 475 | 2014-10-10
8024 | 473 | 573 |  | 573-10-00004-S00 | -S00 | KIT, PAYLOAD CRANE, SHOCK MO | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-06-20 | 2017-10-27 | 0 | 0
8024 | 473 | 581 |  | 581-01-00002-L15 | -L15 | DATA, WEIGHT | 1 | 1 | 2015-02-19 | 60 | 2014-12-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 581 |  | 581-01-00002-L51 | -L51 | DATA, FOR WEIGHT CRITICAL IT | 1 | 1 | 2015-02-19 | 60 | 2014-12-21 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 581 |  | 581-01-00002-L52 | -L52 | TESTING, NOISE AND VIBRATION | 1 | 1 | 2015-02-19 | 60 | 2014-12-21 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 582 |  | 582-01-00001-803 | 232600-000000003 | STATION, PUSHBUTTON, JERED | 2 | 1 | 2015-02-19 | 224 | 2014-07-10 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8024 | 473 | 582 |  | 582-01-00001-804 | 232600-000000004 | CONTROLLER, JERED #190485 | 2 | 1 | 2015-02-19 | 224 | 2014-07-10 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8024 | 473 | 582 |  | 582-01-00001-805 | 232600-000000005 | GASKET, CAPSTAN HEAD COVER | 2 | 1 | 2015-02-19 | 180 | 2014-08-23 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8024 | 473 | 582 |  | 582-01-00001-L52 | -L52 | TESTING, NOISE AND VIBRATION | 1 | 1 | 2015-02-19 | 60 | 2014-12-21 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 583 |  | 583-01-00001-801 | 761900-000000005 | LIFTING SLING | 1 | 1 | 2014-08-04 | 21 | 2014-07-14 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 4625 | 4625
8024 | 473 | 583 |  | 583-01-00001-802 | 761900-000000006 | LIGHT MAST | 1 | 1 | 2014-08-04 | 21 | 2014-07-14 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-803 | 760100-000000001 | FIRE EXTINGUISHER | 1 | 1 | 2014-08-04 | 21 | 2014-07-14 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-805 | 761900-000000009 | BOAT HOOK | 1 | 1 | 2014-08-04 | 14 | 2014-07-21 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-806 | 761900-000000010 | ANCHOR W/ 200' LINE | 1 | 1 | 2014-08-04 | 123 | 2014-04-03 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-807 | 761900-000000011 | 20 RING BUOY | 1 | 1 | 2014-08-04 | 123 | 2014-04-03 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-808 | 761900-000000012 | SPOT LIGHT HAND HELD | 1 | 1 | 2014-08-04 | 56 | 2014-06-09 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-809 | 761900-000000013 | FOOT PUMP | 1 | 1 | 2014-08-04 | 14 | 2014-07-21 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-810 | 761900-000000014 | TUBE REPAIR KIT | 1 | 1 | 2014-08-04 | 14 | 2014-07-21 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-811 | 761900-000000015 | TECHNICAL DATA PACKAGE | 1 | 1 | 2014-08-04 | 123 | 2014-04-03 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-01-00001-812 | 761900-000000016 | LABEL PACKAGE, MMC 5.7M RIB | 1 | 1 | 2014-08-04 | 123 | 2014-04-03 | SE | 0 | 0 | 1 | No | 2015-04-07 | 2017-10-27 | 0 | 0 | 481 | 2017-04-26
8024 | 473 | 583 |  | 583-01-00001-L99 | -L99 | OTHER | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 1535 | 1535 | 469 | 2016-09-16
8024 | 473 | 583 |  | 583-01-00002-R03 | -R00 | RESCUE BOAT DAVIT VENDOR CLA | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2017-09-12 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-02-00001-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 4 | 4 | 2014-09-26 | 60 | 2014-07-28 | LO | 0 | 0 | 4 | No | 2017-08-25 | 2017-10-27 | 0 | 0
8024 | 473 | 583 |  | 583-03-00001-L02 | -L02 | MANUALS, TECHNICAL, PRELIMIN | 1 | 1 | 2015-06-03 | 60 | 2015-04-04 | LO | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0 | 485 | 2017-03-14
8024 | 473 | 583 |  | 583-03-00001-L22 | -L22 | MANUALS, TECHNICAL, FINAL | 1 | 1 | 2015-06-03 | 60 | 2015-04-04 | LO | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0 | 450 | 2009-10-07
8024 | 473 | 583 |  | 583-03-00001-L47 | -L47 | GOVERNMENT INSPECTION | 1 | 1 | 2015-06-03 | 60 | 2015-04-04 | LO | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0 | 485 | 2017-03-14
8024 | 473 | 583 |  | 583-03-00001-S15 | -S00 | BRACKET, TOW WINCH, SHOCK QU | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-11 | 2017-10-27 | 1375 | 1375 | 467 | 2017-06-02
8024 | 473 | 610 |  | 610-01-00003-800 | 760103-000000004 | BRACKET, PKP (18LB), PORTABL | 3 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 2 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 140 | 140
8024 | 473 | 610 |  | 610-01-00007-800 | 760103-000000008 | BRACKET,AFFF(2.5 GAL),PORTAB | 13 | 5 | 2014-01-20 | 123 | 2013-09-19 | EA | 1 | 0 | 4 | No | 2014-05-11 | 2017-10-27 | 72.5 | 290
8024 | 473 | 633 |  | 633-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-05-01 | 2017-10-27 | 0 | 0 | 479 | 2017-05-19
8024 | 473 | 711 |  | 711-01-00013-223 | 870200-000000025 | RELAY BOARD, DOUBLE | 1 | 1 | 2014-10-17 | 123 | 2014-06-16 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2017-05-19
8024 | 473 | 711 |  | 711-01-00013-224 | 870200-000000026 | POWER UNIT | 1 | 1 | 2014-10-17 | 123 | 2014-06-16 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2017-05-19
8024 | 473 | 711 |  | 711-01-00013-8X6 | 870200-000000239 | AMMO STORAGE RACK RIGHT | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8024 | 473 | 711 |  | 711-01-00013-8X7 | 870200-000000240 | AMMO STORAGE RACK LEFT | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8024 | 473 | 721 |  | 721-01-00001-817 | 413200-000000019 | ALIGNMENT BORESCOPE | 1 | 1 | 2015-07-23 | 80 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2012-06-02 | 2017-10-27 | 0 | 0 | 475 | 2014-09-22
8024 | 473 | 721 |  | 721-01-00001-827 | 413200-000000028 | CONNECTOR, MS3475W12-10P | 2 | 1 | 2014-01-20 | 168 | 2013-08-05 | EA | 0 | 0 | 1 | No | 2012-06-02 | 2017-10-27 | 0 | 0
8024 | 473 | 721 |  | 721-01-00001-839 | 413200-000000040 | CONNECTOR, MS3475W18-32S | 4 | 1 | 2014-01-20 | 168 | 2013-08-05 | EA | 0 | 0 | 1 | No | 2012-06-02 | 2017-10-27 | 0 | 0
8024 | 473 | 721 |  | 721-01-00001-847 | 413200-000000048 | CONNECTOR, MS3475W24-19S | 5 | 1 | 2014-01-20 | 168 | 2013-08-05 | EA | 0 | 0 | 1 | No | 2012-06-02 | 2017-10-27 | 0 | 0
8024 | 473 | 721 |  | 721-01-00001-8E3 | 413200-000000110 | RAM LAUNCHER LIFTING SLING | 1 | 1 | 2015-07-23 | 123 | 2015-03-22 | EA | 0 | 0 | 1 | No | 2012-09-21 | 2017-10-27 | 0 | 0 | 467 | 2013-05-20
8024 | 473 | 721 |  | 721-01-00001-8E4 | 413200-000000111 | RAM LAUNCHER DRILLING TEMPLA | 1 | 1 | 2015-07-23 | 123 | 2015-03-22 | SE | 0 | 0 | 1 | No | 2012-09-21 | 2017-10-27 | 0 | 0 | 467 | 2013-05-20
8024 | 473 | 780 |  | 780-01-00001-802 | 233000-000000002 | CHAIN, ROLLER, PART OF THE T | 2 | 2 | 2015-05-27 | 365 | 2014-05-27 | EA | 0 | 0 | 2 | No | 2013-05-09 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 780 |  | 780-01-00001-812 | 233000-000000009 | AIR HOSE, 1" ID X 15 FT LONG | 1 | 1 | 2015-05-27 | 365 | 2014-05-27 | EA | 0 | 0 | 1 | No | 2013-05-09 | 2017-10-27 | 0 | 0
8024 | 473 | 780 |  | 780-01-00001-825 | 233000-000000012 | CAPSCREW, BUTTON HEAD | 42 | 42 | 2015-05-27 | 365 | 2014-05-27 | EA | 0 | 0 | 42 | No | 2013-05-09 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 780 |  | 780-01-00001-826 | 233000-000000013 | HEX NUT, SELF LOCKING, 1/4-2 | 42 | 42 | 2015-05-27 | 365 | 2014-05-27 | EA | 0 | 0 | 42 | No | 2013-05-09 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 780 |  | 780-01-00001-827 | 233000-000000014 | WASHER, 1/4" X .063 THK, FOR | 42 | 42 | 2015-05-27 | 365 | 2014-05-27 | EA | 0 | 0 | 42 | No | 2013-05-09 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 780 |  | 780-01-00001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-07-03 | 60 | 2015-05-04 | EA | 0 | 0 | 1 | No | 2016-04-07 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8024 | 473 | 780 |  | 780-01-00001-L52 | -L52 | TESTING, NOISE AND VIBRATION | 1 | 1 | 2015-05-27 | 60 | 2015-03-28 | EA | 0 | 0 | 1 | No | 2013-05-09 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8025 | 473 | 150 |  | 150-00-00016 | 500800300700-00C | PIPE, CRES 2205, 6" NPS SCH | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | LF | 0 | 0 | 3 | No | 2013-12-03 | 2017-10-27 | 157.14 | 471.42 | 477 | 2016-05-13
8025 | 473 | 150 |  | 150-00-00018 | 500800300700-00F | PIPE, CRES 2205, 12" NPS SCH | 8 | 2.5 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 2.5 | No | 2013-12-03 | 2017-10-27 | 584.1303 | 1460.3258
8025 | 473 | 150 |  | 150-00-00018 | 500800300700-00F | PIPE, CRES 2205, 12" NPS SCH | 8 | 2.5 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 2.5 | No | 2013-12-03 | 2017-10-27 | 584.1303 | 1460.3258
8025 | 473 | 161 |  | 161-04-00001 | 501107252705-00E | PIPE, 10", 10.75" O.D. X .38 | 10 | 10 | 2014-02-28 | 150 | 2013-10-01 | LF | 0 | 0 | 10 | No | 2013-12-03 | 2017-10-27 | 1106 | 11060 | 469 | 2013-03-19
8025 | 473 | 161 |  | 161-04-00A18 | 500800-000000002 | PIPE, 18", 18" OD X .5" THK | 3.7 | 3.7 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 3.7 | No | 2015-06-12 | 2017-10-27 | 1847 | 6833.9 | 481 | 2015-12-10
8025 | 473 | 167 |  | 167-01-P9008 | 500800020600-003 | PIPE,3/4" IPS,1.050 ODX .824 | 40 | 40 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 40 | No | 2014-09-22 | 2017-10-27 | 2.42 | 96.8 | 477 | 2016-10-11
8025 | 473 | 259 |  | 259-05-00028 | 500816-000000002 | PIPE 8" IPS, SCH 10S, 321 SS | 9 | 4 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 4 | No | 2013-06-28 | 2017-10-27 | 85 | 340
8025 | 473 | 259 |  | 259-05-00070 | 545009-000000002 | ELBOW, 45 DEG, 12" LONG RADI | 4 | 1 | 2014-01-20 | 45 | 2013-12-06 | EA | 0 | 0 | 1 | No | 2013-06-28 | 2017-10-27 | 645 | 645
8025 | 473 | 259 |  | 259-05-22509 | 111201041813-001 | TEE, WT 155 X 10.5, STL, AH3 | 4 | 4 | 2014-06-11 | 240 | 2013-10-14 | LF | 0 | 0 | 4 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-00016 | 501352000000-Z01 | TUBE, SQ, AL 5083, 2-1/2 | 3 | 3 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 3 | No | 2017-03-07 | 2017-10-27 | 240.28 | 720.84 | 650 | 2013-08-09
8025 | 473 | 505 |  | 505-01-00514 | 13-1215150420 | ANGLE, 1-1/2" X 1-1/2" X 1/4 | 6 | 6 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 6 | No | 2016-08-09 | 2017-10-27 | 23.41 | 140.46 | 477 | 2017-04-12
8025 | 473 | 505 |  | 505-01-FN002 | 584310233200-003 | FUNNEL, RND, 3/4" IPS, COPPE | 14 | 3 | 2014-03-28 | 30 | 2014-02-26 | EA | 1 | 0 | 2 | No | 2013-11-09 | 2017-10-27 | 370 | 740
8025 | 473 | 505 |  | 505-01-FN003 | 584310233200-004 | FUNNEL, RND, 1" IPS, COPPER | 20 | 2 | 2014-03-07 | 30 | 2014-02-05 | EA | 1 | 1 | 3 | No | 2013-11-09 | 2017-10-27 | 420 | 1260
8025 | 473 | 505 |  | 505-01-FN011 | 584310280000-004 | FUNNEL, 1" IPS OUTLET, COPPE | 4 | 1 | 2014-03-28 | 30 | 2014-02-26 | EA | 0 | 0 | 1 | No | 2013-11-09 | 2017-10-27 | 270 | 270
8025 | 473 | 505 |  | 505-01-P0002 | 501508162600-001 | TUBE,CPR NKL,90-10,1/4" IPS | 213 | 153 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 153 | No | 2013-11-09 | 2017-10-27 | 2.88 | 440.64
8025 | 473 | 505 |  | 505-01-P0003 | 501108252605-Z04 | TUBE,CPR NKL,90-10,3/8" IPS | 925 | 925 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 925 | No | 2013-11-09 | 2017-10-27 | 3.77 | 3487.25
8025 | 473 | 505 |  | 505-01-P0004 | 501508162600-003 | TUBE,CU/NI,90-10,1/2" IPS X | 2419.5 | 2239.5 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 2239.5 | No | 2013-11-09 | 2017-10-27 | 4.63 | 10368.885
8025 | 473 | 505 |  | 505-01-P0005 | 501508162600-004 | TUBE, CUNI,90-10,3/4" | 1949 | 1554 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 1554 | No | 2013-11-09 | 2017-10-27 | 5.9 | 9168.6
8025 | 473 | 505 |  | 505-01-P0006 | 501508162600-005 | TUBE,CU/NI,90-10,1" IPS X 1. | 4699 | 3659 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 3659 | No | 2013-11-09 | 2017-10-27 | 7.44 | 27222.96
8025 | 473 | 505 |  | 505-01-P0008 | 501508162600-007 | TUBE, CU/NI,90-10,1-1/2" | 4747 | 3423 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 14 | 3437 | No | 2013-11-09 | 2017-10-27 | 12.08 | 41518.96
8025 | 473 | 505 |  | 505-01-P0009 | 501508162600-008 | TUBE,CNA,90-10, 2" IPS | 3416 | 2536 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 2536 | No | 2013-11-09 | 2017-10-27 | 17.41 | 44151.76
8025 | 473 | 505 |  | 505-01-P0010 | 501508162600-009 | TUBE,CU/NI ,90-10,2-1/2" | 1643 | 1344 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 9 | 1353 | No | 2013-11-09 | 2017-10-27 | 21.27 | 28778.31
8025 | 473 | 505 |  | 505-01-P0011 | 501108252605-Z12 | TUBE, CUNI, 90/10, 3" | 2927 | 2361 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 6 | 2367 | No | 2013-11-09 | 2017-10-27 | 29.8 | 70536.6
8025 | 473 | 505 |  | 505-01-P0013 | 501508162600-012 | TUBE,CPR NKL,90-10,4" IPS X | 1437 | 1347 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 1347 | No | 2013-11-09 | 2017-10-27 | 44.09 | 59389.23
8025 | 473 | 505 |  | 505-01-P0014 | 501508162600-013 | TUBE,CPR NKL,90-10,5" IPS X | 1423 | 1151 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 102 | 1253 | No | 2013-11-09 | 2017-10-27 | 74.85 | 93787.05
8025 | 473 | 505 |  | 505-01-P0015 | 501108252605-Z15 | TUBE,6" CU/NI ,90-10 | 1368 | 1223 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 5 | 1228 | No | 2013-11-09 | 2017-10-27 | 99.93 | 122714.04
8025 | 473 | 505 |  | 505-01-P0016 | 501108252605-Z16 | TUBE,CPR NKL,90-10,8" IPS X | 520 | 520 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 520 | No | 2013-11-09 | 2017-10-27 | 160.23 | 83319.6
8025 | 473 | 505 |  | 505-01-P0018 | 500818162405-001 | PIPE,SSTL,1/4"IPS,SCH 10S | 23 | 1 | 2014-01-20 | 30 | 2013-12-21 | LF | 2 | 2 | 3 | No | 2013-11-09 | 2017-10-27 | 3.43 | 10.29
8025 | 473 | 505 |  | 505-01-P0020 | 500818162405-002 | PIPE,SSTL,1/2"IPS,SCH 10S | 90 | 90 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 90 | No | 2013-11-09 | 2017-10-27 | 5.12 | 460.8
8025 | 473 | 505 |  | 505-01-P0021 | 500818162405-003 | PIPE, SSTL 304L, 3/4" IPS, | 141 | 141 | 2014-01-20 | 180 | 2013-07-24 | LF | 0 | 0 | 141 | No | 2013-11-09 | 2017-10-27 | 2.61 | 368.01
8025 | 473 | 505 |  | 505-01-P0024 | 500818162405-006 | PIPE,SSTL,1-1/2"IPS,SCH 10S | 84 | 84 | 2014-02-28 | 30 | 2014-01-29 | LF | 0 | 0 | 84 | No | 2015-10-29 | 2017-10-27 | 5.1 | 428.4 | 481 | 2017-09-05
8025 | 473 | 505 |  | 505-01-P0025 | 500818162405-007 | PIPE,SSTL,2"IPS,SCH 10S | 284 | 254 | 2014-01-20 | 45 | 2013-12-06 | LF | 0 | 30 | 284 | No | 2013-11-09 | 2017-10-27 | 7.11 | 2019.24
8025 | 473 | 505 |  | 505-01-P0026 | 500818162405-008 | PIPE,SSTL,2-1/2"IPS,SCH 10S | 133 | 132 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 1 | 133 | No | 2013-11-09 | 2017-10-27 | 9.12 | 1212.96
8025 | 473 | 505 |  | 505-01-P0027 | 500818162405-009 | PIPE,SSTL,3"IPS,SCH 10S | 395 | 355 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 355 | No | 2013-11-09 | 2017-10-27 | 16.32 | 5793.6
8025 | 473 | 505 |  | 505-01-P0029 | 500818162405-00A | PIPE,SSTL,4"IPS,SCH 10S | 214 | 214 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 214 | No | 2013-11-09 | 2017-10-27 | 15.3 | 3274.2
8025 | 473 | 505 |  | 505-01-P0033 | 501104143905-Z01 | TUBE,CPR,1/4",NOM .375" OD X | 252 | 32 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 32 | No | 2013-08-12 | 2017-10-27 | 0.73 | 23.36
8025 | 473 | 505 |  | 505-01-P0056 | 500817162205-008 | PIPE,STN STL,2-1/2"IPS,SCH 4 | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2014-01-23 | 2017-10-27 | 31.8 | 636
8025 | 473 | 505 |  | 505-01-P0078 | 500837160605-00H | PIPE,STL,3/8",PL,SCH 40 IPS | 300 | 280 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 280 | No | 2013-11-18 | 2017-10-27 | 3.22 | 901.6
8025 | 473 | 505 |  | 505-01-P0083 | 500837160605-006 | PIPE,STL,1 1/2",PL,SCH 40 IP | 80 | 18.67 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 1.3 | 20 | No | 2013-11-18 | 2017-10-27 | 2.8 | 56
8025 | 473 | 505 |  | 505-01-P0084 | 500837160605-007 | PIPE,STL,2",PL,SCH 40 IPS 2. | 220 | 100 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 100 | No | 2013-11-18 | 2017-10-27 | 3.318 | 331.8
8025 | 473 | 505 |  | 505-01-P0088 | 500837160605-00A | PIPE,STL,4",PL,SCH 40 IPS 4. | 280 | 60.75 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 99.2 | 160 | No | 2013-11-18 | 2017-10-27 | 8.9 | 1424
8025 | 473 | 505 |  | 505-01-P0090 | 500837160605-00C | PIPE,STL,6",PL,SCH 40 IPS 6. | 40 | 14.17 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 5.8 | 20 | No | 2013-11-18 | 2017-10-27 | 15.35 | 307
8025 | 473 | 505 |  | 505-01-P0092 | 500837160605-00E | PIPE,STL,10",PL,SCH 40 IPS 1 | 2 | 2 | 2014-01-20 | 90 | 2013-10-22 | LF | 0 | 0 | 2 | No | 2013-11-18 | 2017-10-27 | 133.88 | 267.76
8025 | 473 | 505 |  | 505-01-P0152 | 501108252605-Z01 | TUBE, 1/4" CNA,90-10 1/4'" O | 62 | 22 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 22 | No | 2013-11-18 | 2017-10-27 | 3.59 | 78.98
8025 | 473 | 505 |  | 505-01-P0159 | 500837160705-004 | PIPE,STL,1",PL,SCH 80 IPS 1. | 327 | 94 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 2 | 96 | No | 2013-11-18 | 2017-10-27 | 2.35 | 225.6
8025 | 473 | 505 |  | 505-01-P0164 | 500837160705-009 | PIPE,STL,3",PL,SCH 80 IPS 3. | 20 | 20 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 8.05 | 161
8025 | 473 | 505 |  | 505-01-P0167 | 500837160705-00B | PIPE, STL, 5", PL, SCH 80, | 380 | 340 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 40 | 340 | No | 2013-11-18 | 2017-10-27 | 17.87 | 6075.8
8025 | 473 | 505 |  | 505-01-P0168 | 500837160705-00C | PIPE,STL,6",PL,SCH 80 IPS 6. | 60 | 60 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 60 | No | 2013-11-18 | 2017-10-27 | 23.11 | 1386.6
8025 | 473 | 505 |  | 505-01-P0169 | 500837160705-00D | PIPE,STL,8",PL,SCH 80 | 20 | 10 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 10 | No | 2013-11-18 | 2017-10-27 | 37.04 | 370.4
8025 | 473 | 505 |  | 505-01-P0172 | 500818162205-00H | PIPE,STN STL,3/8"IPS,SCH 40S | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 4.37 | 87.4
8025 | 473 | 505 |  | 505-01-P0173 | 500818162205-002 | PIPE,STN STL,1/2"IPS,SCH 40S | 60 | 60 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 60 | No | 2013-11-18 | 2017-10-27 | 4.84 | 290.4
8025 | 473 | 505 |  | 505-01-P0174 | 500818162205-003 | PIPE,STN STL,3/4"IPS,SCH 40S | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 18 | 2 | No | 2013-11-18 | 2017-10-27 | 3.09 | 6.18
8025 | 473 | 505 |  | 505-01-P0179 | 500818162200-010 | PIPE,STN STL,2-1/2"IPS, SCH | 120 | 120 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 120 | No | 2015-07-22 | 2017-10-27 | 22.27 | 2672.4
8025 | 473 | 505 |  | 505-01-P0183 | 500818162205-00B | PIPE,STN STL,5"IPS,SCH 40S | 10 | 10 | 2014-01-20 | 84 | 2013-10-28 | LF | 0 | 0 | 10 | No | 2013-11-18 | 2017-10-27 | 41.88 | 418.8
8025 | 473 | 505 |  | 505-01-P0185 | 500818162205-00D | PIPE,STN STL,8"IPS,SCH 40S, | 5 | 5 | 2014-01-20 | 42 | 2013-12-09 | LF | 0 | 0 | 5 | No | 2013-11-18 | 2017-10-27 | 141.93 | 709.65
8025 | 473 | 505 |  | 505-01-P0228 | 500914000607-008 | PIPE, 1-1/2" STL SCH 40 GR.L | 1289 | 280 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 3 | 283 | No | 2013-11-18 | 2017-10-27 | 4.66 | 1318.78
8025 | 473 | 505 |  | 505-01-P0228 | 500914000607-008 | PIPE, 1-1/2" STL SCH 40 GR.L | 1289 | 280 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 3 | 283 | No | 2013-11-18 | 2017-10-27 | 4.66 | 1318.78
8025 | 473 | 505 |  | 505-01-P0231 | 500914000607-011 | PIPE, STEEL, 3", 3.5" O.D. x | 961 | 363 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 363 | No | 2013-11-18 | 2017-10-27 | 7.5 | 2722.5
8025 | 473 | 505 |  | 505-01-P0993 | 500814450603-004 | PIPE,1" DIA,SCH40 GALVANIZED | 1660 | 1411 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 160 | 1251 | No | 2013-11-18 | 2017-10-27 | 2.1 | 2627.1
8025 | 473 | 505 |  | 505-01-P0994 | 500814450603-005 | PIPE, 1-1/4", SCH 40 | 120 | 120 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 120 | No | 2013-11-18 | 2017-10-27 | 2.72 | 326.4
8025 | 473 | 505 |  | 505-01-P1046 | 501118164405-Z01 | TUBING, SST, 1/4" OD | 40 | 36 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 4 | 40 | No | 2013-11-18 | 2017-10-27 | 0.68 | 27.2
8025 | 473 | 505 |  | 505-01-P1066 | 500818162405-001 | PIPE, SSTL, 1/4" IPS, SCH 10 | 10 | 10 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 10 | No | 2013-11-18 | 2017-10-27 | 2.86 | 28.6
8025 | 473 | 505 |  | 505-01-P1083 | 500817162305-001 | PIPE,STAIN STL,1/4"IPS,SCH 8 | 1 | -1 | 2014-06-24 | 30 | 2014-05-25 | LF | 0 | 2 | 1 | No | 2013-11-18 | 2017-10-27 | 5.12 | 5.12
8025 | 473 | 505 |  | 505-01-P1099 | 500818162305-004 | PIPE,STN STL, 1"IPS, SCH 80S | 22 | 22 | 2014-01-20 | 30 | 2013-12-21 | LF | 20 | 0 | 2 | No | 2013-11-18 | 2017-10-27 | 10.93 | 21.86
8025 | 473 | 505 |  | 505-01-P9007 | 500802160600-002 | PIPE,1/2" IPS,.840 ODX .622 | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 1.82 | 36.4
8025 | 473 | 505 |  | 505-01-P9011 | 500802160600-006 | PIPE, 1-1/2" IPS, 1.900 OD X | 200 | 1 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 1 | No | 2013-11-18 | 2017-10-27 | 5.71 | 5.71
8025 | 473 | 505 |  | 505-01-P9014 | 500802160600-009 | PIPE,3" IPS, 3.500 OD X 3.06 | 240 | 80 | 2014-01-20 | 20 | 2013-12-31 | LF | 0 | 0 | 80 | No | 2013-11-18 | 2017-10-27 | 16.45 | 1316
8025 | 473 | 505 |  | 505-01-P9015 | 500802160600-Z01 | PIPE,3-1/2" IPS, 4.000 OD X | 20 | 20 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 19.06 | 381.2
8025 | 473 | 505 |  | 505-01-P9016 | 500802160600-00A | PIPE,4" IPS, 4.500 OD X 4.02 | 40 | 20 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 22.43 | 448.6
8025 | 473 | 505 |  | 505-01-P9017 | 500802160600-00B | PIPE,5" IPS, 5.563 OD X 5.04 | 60 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 34.68 | 693.6
8025 | 473 | 505 |  | 505-01-P9023 | 501104144005-Z03 | TUBE, 1/2", NOM, TYPE L, COP | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2015-01-02 | 2017-10-27 | 1.13 | 22.6
8025 | 473 | 505 |  | 505-01-P9025 | 501104144005-Z05 | TUBE, 3/4", NOM, TYPE L, COP | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2015-04-01 | 2017-10-27 | 1.44 | 28.8
8025 | 473 | 505 |  | 505-01-P9033 | 501104144005-Z12 | TUBE, 4", NOM, TYPE L, CU | 100 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2013-08-12 | 2017-10-27 | 22.08 | 441.6
8025 | 473 | 505 |  | 505-01-P9043 | 501107252705-Z08 | TUBE, 1-1/2", CU-NI, 70-30, | 70 | 30 | 2014-01-20 | 60 | 2013-11-21 | LF | 0 | 0 | 30 | No | 2013-11-18 | 2017-10-27 | 41.43 | 1242.9
8025 | 473 | 505 |  | 505-01-P9045 | 501107252605-Z15 | TUBE, 6" IPS, CLASS 200, 70- | 80 | 60 | 2014-01-20 | 45 | 2013-12-06 | LF | 0 | 0 | 60 | No | 2013-11-18 | 2017-10-27 | 157.59 | 9455.4
8025 | 473 | 505 |  | 505-01-P9047 | 501107252605-Z16 | TUBE, 8" IPS, CLASS 200, 70- | 20 | 20 | 2014-01-20 | 45 | 2013-12-06 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 238.73 | 4774.6
8025 | 473 | 505 |  | 505-01-P9049 | 501107252605-Z13 | TUBE, 4" IPS, CLASS 200, 70- | 20 | 5 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 5 | No | 2013-11-18 | 2017-10-27 | 73.86 | 369.3
8025 | 473 | 505 |  | 505-01-P9054 | 501107252705-Z10 | TUBE, 2-1/2", CU-NI, 70-30, | 21 | 1 | 2014-01-20 | 60 | 2013-11-21 | LF | 0 | 0 | 1 | No | 2013-11-18 | 2017-10-27 | 79 | 79
8025 | 473 | 505 |  | 505-01-P9055 | 501107251705-Z01 | TUBE, 1/4"O.D. x .058 WALL, | 5520 | 3160 | 2014-01-20 | 28 | 2013-12-23 | LF | 0 | 0 | 3160 | No | 2013-11-18 | 2017-10-27 | 6.75 | 21330
8025 | 473 | 505 |  | 505-01-P9056 | 501118164705-Z01 | TUBE,1/4" OD X 0.065 WALL, 3 | 3180 | 3180 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 3180 | No | 2013-11-18 | 2017-10-27 | 1.67 | 5310.6
8025 | 473 | 505 |  | 505-01-P9058 | 501118164405-Z17 | TUBING, SST 304, 1/2"OD x | 1592 | 1591 | 2014-01-20 | 35 | 2013-12-16 | LF | 1260 | 0 | 332 | No | 2013-11-18 | 2017-10-27 | 1.7 | 564.4
8025 | 473 | 505 |  | 505-01-P9059 | 501118164405-Z18 | TUBING, SST 304, 5/8" OD x | 10 | 10 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 10 | No | 2013-11-18 | 2017-10-27 | 1.89 | 18.9
8025 | 473 | 505 |  | 505-01-P9069 | 501214160005-Z02 | MECHANICAL TUBE, 10" OD X 1/ | 2 | 2 | 2014-01-20 | 42 | 2013-12-09 | LF | 0 | 0 | 2 | No | 2015-05-04 | 2017-10-27 | 104.21 | 208.42 | 471 | 2015-06-04
8025 | 473 | 505 |  | 505-01-P9070 | 501214160005-Z01 | MECHANICAL TUBE, 8" OD X 1/2 | 3 | 3 | 2014-01-20 | 42 | 2013-12-09 | LF | 0 | 0 | 3 | No | 2015-05-04 | 2017-10-27 | 83.16 | 249.48 | 471 | 2015-06-04
8025 | 473 | 505 |  | 505-01-P9079 | 500837160905-00A | PIPE, STEEL, 4" IPS x 4.5" O | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 29.57 | 591.4 | 481 | 2017-09-05
8025 | 473 | 505 |  | 505-01-P9082 | 500818162405-00E | PIPE,SSTL,10"IPS,SCH 10S | 20 | 20 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 357.16 | 7143.2
8025 | 473 | 505 |  | 505-01-P9085 | 501107252705-Z09 | TUBE, 2", CU-NI, 70-30, PL, | 100 | 60 | 2014-01-20 | 30 | 2013-12-21 | LF | 0 | 0 | 60 | No | 2013-11-18 | 2017-10-27 | 51.72 | 3103.2
8025 | 473 | 505 |  | 505-01-P9088 | 501107251705-Z07 | TUBE, 3/4", 70-30 CNA, CL600 | 20 | 20 | 2014-01-20 | 84 | 2013-10-28 | LF | 0 | 0 | 20 | No | 2013-11-18 | 2017-10-27 | 60.57 | 1211.4
8025 | 473 | 505 |  | 505-01-P9093 | 500818162405-00F | PIPE,SSTL,12"IPS,SCH 10S | 40 | 40 | 2014-01-20 | 84 | 2013-10-28 | LF | 37 | 0 | 3 | No | 2013-11-18 | 2017-10-27 | 133.33 | 399.99
8025 | 473 | 505 |  | 505-01-P9098 | 500817162305-004 | PIPE, 1"IPS, 1.315 OD, W/.17 | 103.5 | 83.5 | 2014-01-20 | 49 | 2013-12-02 | LF | 99 | 0 | 4.5 | No | 2014-02-12 | 2017-10-27 | 7.38 | 33.21
8025 | 473 | 505 |  | 505-01-P9105 | 500818162405-005 | PIPE, STAINLESS STEEL, 304L, | 80 | 80 | 2014-01-20 | 49 | 2013-12-02 | LF | 76 | 0 | 4 | No | 2013-11-18 | 2017-10-27 | 4.8 | 19.2
8025 | 473 | 505 |  | 505-01-P9123 | 500818162205-008 | PIPE, STN STL, 2-1/2" IPS,SC | 408.5 | 408.5 | 2014-01-20 | 49 | 2013-12-02 | LF | 400 | 0 | 8.5 | No | 2013-11-18 | 2017-10-27 | 27.01 | 229.585
8025 | 473 | 505 |  | 505-01-P9140 | 500837160705-006 | PIPE,STL,1 1/2",PL,SCH 80 IP | 22 | 22 | 2014-01-20 | 30 | 2013-12-21 | LF | 21 | 0 | 1 | No | 2013-11-18 | 2017-10-27 | 3.75 | 3.75
8025 | 473 | 505 |  | 505-01-P9142 | 500837160705-009 | PIPE,STL,3",PL,SCH 80 IPS 3. | 120 | 120 | 2014-01-20 | 15 | 2014-01-05 | LF | 111 | 0 | 9 | No | 2013-11-18 | 2017-10-27 | 8.05 | 72.45
8025 | 473 | 505 |  | 505-01-P9146 | 500817162305-001 | PIPE,STAIN STL,1/4"IPS,SCH 8 | 632 | 557 | 2014-01-20 | 30 | 2013-12-21 | LF | 627 | 0 | 5 | No | 2013-11-18 | 2017-10-27 | 5.12 | 25.6
8025 | 473 | 505 |  | 505-01-P9148 | 500818162405-00E | PIPE,SSTL,10"IPS,SCH 10S | 40 | 40 | 2014-01-20 | 30 | 2013-12-21 | LF | 38 | 0 | 2 | No | 2013-11-18 | 2017-10-27 | 73.68 | 147.36
8025 | 473 | 505 |  | 505-01-P9161 | 501107251805-Z11 | TUBE, 1" IPS, CNA 70:30 | 85 | 85 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 85 | No | 2013-11-18 | 2017-10-27 | 41.43 | 3521.55
8025 | 473 | 505 |  | 505-01-P9176 | 500817162205-00H | PIPE, 3/8" IPS, SSTL, PLAIN | 981 | 438.68 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 438.6 | No | 2014-07-14 | 2017-10-27 | 4.37 | 1917.0666
8025 | 473 | 505 |  | 505-01-P9178 | 500817162205-003 | PIPE, 3/4" IPS, SSTL, PLAIN | 280 | 38 | 2014-01-20 | 35 | 2013-12-16 | LF | 0 | 0 | 38 | No | 2014-06-20 | 2017-10-27 | 8.16 | 310.08
8025 | 473 | 505 |  | 505-01-P9181 | 501109410700-001 | PIPE - PROTECTION TUBE | 40 | 36 | 2014-01-20 | 45 | 2013-12-06 | EA | 0 | 0 | 36 | No | 2014-05-14 | 2017-10-27 | 533.3 | 19198.8
8025 | 473 | 505 |  | 505-01-P9185 | 500817162305-003 | PIPE, 3/4", SS, PL, SCH 80S | 27 | 27 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 27 | No | 2014-10-03 | 2017-10-27 | 8.29 | 223.83
8025 | 473 | 505 |  | 505-01-P9197 | 501117164405-Z12 | TUBING, SST 316L, 3/4" OD X | 1820 | 1100 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 1100 | No | 2013-11-18 | 2017-10-27 | 2.21 | 2431
8025 | 473 | 505 |  | 505-01-P9198 | 501117164405-Z21 | TUBING, SST 316L, 1" OD X | 70 | 70 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 70 | No | 2013-11-18 | 2017-10-27 | 3.44 | 240.8
8025 | 473 | 505 |  | 505-01-P9199 | 501117164405-Z15 | TUBE, 1/4 OD X 0.065 WALL, S | 26 | 26 | 2014-06-04 | 49 | 2014-04-16 | LF | 20 | 0 | 6 | No | 2015-04-01 | 2017-10-27 | 2.54 | 15.24
8025 | 473 | 505 |  | 505-01-P9207 | 500818162305-Z17 | PIPE, 3/8" IPS, SS 304L, SCH | 3 | 3 | 2014-07-08 | 49 | 2014-05-20 | LF | 0 | 0 | 3 | No | 2015-06-26 | 2017-10-27 | 9.44 | 28.32 | 477 | 2016-10-11
8025 | 473 | 505 |  | 505-01-P9208 | 501107251805-Z03 | TUBE, 1/2" OD, CUNI 70-30 | 320 | 285 | 2014-02-28 | 49 | 2014-01-10 | LF | 0 | 35 | 320 | No | 2015-09-02 | 2017-10-27 | 10.1 | 3232
8025 | 473 | 505 |  | 505-01-P9209 | 501117164405-002 | TUBE, 1/2" OD, SS 316L, SMLS | 540 | 483 | 2014-02-28 | 49 | 2014-01-10 | LF | 0 | 57 | 540 | No | 2015-09-02 | 2017-10-27 | 3.94 | 2127.6
8025 | 473 | 505 |  | 505-01-P9210 | 501117164405-Z02 | TUBE, SST 316L, 3/8" OD X .0 | 7.5 | 7.5 | 2014-06-04 | 49 | 2014-04-16 | LF | 0 | 0 | 7.5 | No | 2016-10-10 | 2017-10-27 | 1.07 | 8.025
8025 | 473 | 505 |  | 505-01-P9211 | 501108251805-Z07 | TUBE, 1/4" IPS, CNA 90-10 | 4 | 4 | 2014-07-08 | 49 | 2014-05-20 | LF | 0 | 0 | 4 | No | 2016-10-17 | 2017-10-27 | 11.24 | 44.96 | 475 | 2016-10-28
8025 | 473 | 505 |  | 505-01-V0001 | SRV523-031000002 | SUPPORT, FLUSHING AND HYDRO | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2015-10-21 | 2017-10-27 | 1008 | 1008 | 467 | 2017-01-25
8025 | 473 | 505 |  | 505-01-V0001 | SRV523-031000002 | SUPPORT, FLUSHING AND HYDRO | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2015-10-21 | 2017-10-27 | 1008 | 1008 | 467 | 2017-01-25
8025 | 473 | 505 |  | 505-03-A0018 | 551402450200-006 | ADAPTER,1-1/2" IPS, SILB X M | 16 | 5 | 2014-01-20 | 25 | 2013-12-26 | EA | 4 | 0 | 1 | No | 2013-11-14 | 2017-10-27 | 20 | 20
8025 | 473 | 505 |  | 505-03-A0029 | 555402590200-011 | BUSHING,REDUCING,1"X1/2" IPS | 19 | 3 | 2014-01-20 | 25 | 2013-12-26 | EA | 2 | 0 | 1 | No | 2013-11-14 | 2017-10-27 | 7.6 | 7.6
8025 | 473 | 505 |  | 505-03-A0035 | 555402590200-064 | BUSHING,REDUCING,1-1/2"X1" I | 23 | -3 | 2014-02-03 | 25 | 2014-01-09 | EA | 0 | 4 | 1 | No | 2013-11-14 | 2017-10-27 | 13.44 | 13.44
8025 | 473 | 505 |  | 505-03-A0324 | 551404720201-003 | ADAPTER, FPT x M WELD, 3/4" | 7 | 3 | 2014-02-24 | 30 | 2014-01-25 | EA | 3 | 0 | 1 | No | 2013-11-15 | 2017-10-27 | 34.8 | 34.8
8025 | 473 | 505 |  | 505-03-A9072 | 551412B60000-022 | ADAPTER, 1/2 FEM SW X 1/2-08 | 3 | 1 | 2014-01-20 | 35 | 2013-12-16 | EA | 0 | 0 | 1 | No | 2013-11-15 | 2017-10-27 | 249.21 | 249.21
8025 | 473 | 505 |  | 505-03-A9644 | 542807152603-062 | REDUCER,INSERT,1-1/2 X 1/2, | 1 | 1 | 2014-06-04 | 49 | 2014-04-16 | EA | 0 | 0 | 1 | No | 2017-10-02 | 2017-10-27 | 9.34 | 9.34 | 481 | 2017-03-08
8025 | 473 | 505 |  | 505-03-A9730 | 54A607920000-023 | ADPTR, HYD, 1/2" X 3/4", SST | 19 | 10 | 2014-03-21 | 35 | 2014-02-14 | EA | 7 | 2 | 12 | No | 2017-07-03 | 2017-10-27 | 57.64 | 691.68
8025 | 473 | 505 |  | 505-03-A9749 | 551401K50000-012 | ADAPTER, 1/4" X 1/2", BRASS | 1 | 1 | 2014-06-04 | 77 | 2014-03-19 | EA | 0 | 0 | 1 | No | 2016-11-07 | 2017-10-27 | 9.97 | 9.97 | 481 | 2017-06-29
8025 | 473 | 505 |  | 505-03-A9750 | 551401K50000-0H2 | ADAPTER, 3/8" X 1/2", BRASS | 1 | 1 | 2014-06-04 | 77 | 2014-03-19 | EA | 0 | 0 | 1 | No | 2016-11-01 | 2017-10-27 | 9.61 | 9.61 | 481 | 2017-06-29
8025 | 473 | 505 |  | 505-03-B0387 | 543604152803-Z06 | SOCKOLET, 1-1/2"-1-1/4" RUN | 1 | 1 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 1 | No | 2017-02-13 | 2017-10-27 | 7 | 7 | 483 | 2017-04-17
8025 | 473 | 505 |  | 505-03-B9019 | 543618152603-Z20 | SOCKOLET, REDUCING, SST 304L | 8 | 2 | 2014-06-18 | 20 | 2014-05-29 | EA | 2 | 0 | 2 | No | 2013-11-12 | 2017-10-27 | 10.17 | 20.34
8025 | 473 | 505 |  | 505-03-C9146 | 550510121801-007 | COUPLING, 2", SW, CUNI 70-30 | 2 | 0 | 2014-02-24 | 35 | 2014-01-20 | EA | 0 | 1 | 1 | No | 2013-11-15 | 2017-10-27 | 83.6 | 83.6
8025 | 473 | 505 |  | 505-03-K9093 | 810146191300-00A | GASKET, 4" NAVY PATTERN, 150 | 16 | 4 | 2014-03-07 | 81 | 2013-12-16 | EA | 0 | 0 | 4 | No | 2013-11-19 | 2017-10-27 | 33.89 | 135.56
8025 | 473 | 505 |  | 505-03-L0025 | 550202280201-009 | ELL, 45 DEGREE, 2-1/2" IPS, | 94 | 6 | 2014-01-20 | 25 | 2013-12-26 | EA | 4 | 0 | 2 | No | 2013-11-19 | 2017-10-27 | 36.03 | 72.06
8025 | 473 | 505 |  | 505-03-L0095 | 541704150503-005 | ELBOW, 3/4 IPS, 45 DEG, 3000 | 61 | 4 | 2014-02-03 | 20 | 2014-01-14 | EA | 2 | 0 | 4 | No | 2013-11-19 | 2017-10-27 | 5.94 | 23.76
8025 | 473 | 505 |  | 505-03-L0308 | 554904022201-00A | ELB, 90 DEG, 4" IPS, SR, CL | 51 | -3 | 2014-01-20 | 40 | 2013-12-11 | EA | 2 | 6 | 3 | No | 2013-11-18 | 2017-10-27 | 129.95 | 389.85
8025 | 473 | 505 |  | 505-03-L0343 | 550204120201-004 | ELB, 45 DEG., 1-1/4" IPS, 40 | 70 | -4 | 2014-02-24 | 30 | 2014-01-25 | EA | 0 | 7 | 3 | No | 2013-11-18 | 2017-10-27 | 39.18 | 117.54
8025 | 473 | 505 |  | 505-03-L0344 | 550204120201-005 | ELB, 45 DEG., 1-1/2" IPS, 40 | 104 | 3 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 3 | No | 2013-11-18 | 2017-10-27 | 46.26 | 138.78
8025 | 473 | 505 |  | 505-03-L0421 | 544806021200-001 | ELBOW, 90 DEG., 2-1/2" IPS, | 50 | 17 | 2014-06-04 | 20 | 2014-05-15 | EA | 14 | 2 | 1 | No | 2013-11-18 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-03-L9023 | 544806021101-008 | ELL,90 DEGREES, 3" IPS, SCH. | 133 | 29 | 2014-01-20 | 20 | 2013-12-31 | EA | 27 | 1 | 2 | No | 2013-11-18 | 2017-10-27 | 6.38 | 12.76
8025 | 473 | 505 |  | 505-03-L9158 | 554910020801-00D | ELBOW, 8", 90 DEG, SR, 70/30 | 2 | 2 | 2014-02-28 | 90 | 2013-11-30 | EA | 0 | 0 | 2 | No | 2014-03-30 | 2017-10-27 | 2208 | 4416 | 477 | 2016-05-26
8025 | 473 | 505 |  | 505-03-L9332 | 54B407C30003-002 | ELBOW, 45 DEG, 1/2" IPS, SST | 10 | 2 | 2014-02-28 | 35 | 2014-01-24 | EA | 0 | 0 | 2 | No | 2014-06-22 | 2017-10-27 | 254.44 | 508.88
8025 | 473 | 505 |  | 505-03-L9339 | 54B507C30003-002 | ELBOW, 90 DEG, SR, 1/2", SST | 35 | 1 | 2014-02-28 | 35 | 2014-01-24 | EA | 0 | 0 | 1 | No | 2014-06-22 | 2017-10-27 | 264.1 | 264.1
8025 | 473 | 505 |  | 505-03-M9156 | 55C122581301-002 | NIPPLE, CLOSE, NPT 1/2" | 122 | 83 | 2014-01-20 | 35 | 2013-12-16 | EA | 36 | 0 | 47 | No | 2016-09-16 | 2017-10-27 | 1.22 | 57.34
8025 | 473 | 505 |  | 505-03-R0469 | 554504020201-019 | RED CONC B.W. 3X1-1/2 IPS,CP | 18 | 1 | 2014-01-27 | 30 | 2013-12-28 | EA | 0 | 0 | 1 | No | 2013-11-14 | 2017-10-27 | 53 | 53
8025 | 473 | 505 |  | 505-03-R0480 | 554504020201-030 | RED B.W.6X4 IPS,CPR NKL,90-1 | 15 | -4 | 2014-01-20 | 30 | 2013-12-21 | EA | 1 | 5 | 1 | No | 2013-11-14 | 2017-10-27 | 130.5 | 130.5
8025 | 473 | 505 |  | 505-03-R9120 | 54B707C30003-054 | CPLNG, REDC, 1-1/4 X 1", SS | 4 | 0 | 2014-04-17 | 35 | 2014-03-13 | EA | 3 | 1 | 1 | No | 2014-06-20 | 2017-10-27 | 183.02 | 183.02
8025 | 473 | 505 |  | 505-03-T0096 | 554702280200-004 | TEE, LNG TRN SGL SWP, 1" IPS | 6 | 1 | 2014-02-28 | 25 | 2014-02-03 | EA | 0 | 0 | 1 | No | 2013-11-14 | 2017-10-27 | 29.75 | 29.75
8025 | 473 | 505 |  | 505-03-T0235 | 550304120201-005 | TEE, 1-1/2" IPS, 400 PSI WOG | 46 | -2 | 2014-01-20 | 30 | 2013-12-21 | EA | 1 | 3 | 1 | No | 2013-11-14 | 2017-10-27 | 65.5 | 65.5
8025 | 473 | 505 |  | 505-03-T9184 | 54B807C30003-533 | TEE, RED, 1-1/4 X 3/4, LOKRI | 2 | 0 | 2014-04-17 | 35 | 2014-03-13 | EA | 0 | 2 | 2 | No | 2017-03-23 | 2017-10-27 | 757.74 | 1515.48 | 477 | 2017-06-29
8025 | 473 | 505 |  | 505-03-U9086 | 546807920000-023 | UNION, REDUC, 1/2" X 3/4", S | 3 | 3 | 2014-03-21 | 35 | 2014-02-14 | EA | 0 | 0 | 3 | No | 2017-07-03 | 2017-10-27 | 304.25 | 912.75 | 481 | 2017-06-19
8025 | 473 | 505 |  | 505-03-Y0003 | 551002280200-222 | Y-BRANCH, 1/2" IPS, SILB, 40 | 1 | 1 | 2014-02-28 | 35 | 2014-01-24 | EA | 0 | 0 | 1 | No | 2014-05-09 | 2017-10-27 | 18.86 | 18.86
8025 | 473 | 505 |  | 505-03-Y9005 | 557002330001-006 | Y BRANCH, 2"NOM, 45 DEGREE | 66 | 4 | 2014-01-20 | 30 | 2013-12-21 | EA | 2 | 1 | 1 | No | 2013-11-14 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-99-HMISU | SRV523-032800002 | START UP/ HMI PIPING CONTRAC | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-06-10 | 2017-10-27 | 0 | 0
8025 | 473 | 512 |  | 512-06-00100 | 501133600000-001 | TUBING, COIL, 1/4" OD, SSTL3 | 3 | 3 | 2014-01-27 | 49 | 2013-12-09 | EA | 0 | 0 | 3 | No | 2017-06-19 | 2017-10-27 | 0.8 | 2.4 | 450 | 2011-06-24
8025 | 473 | 512 |  | 512-88-01588 | 540508M70000-011 | CONNECTOR, MALE, TUBE FITTIN | 6 | 6 | 2014-01-27 | 35 | 2013-12-23 | EA | 0 | 0 | 6 | No | 2017-06-19 | 2017-10-27 | 0 | 0 | 450 | 2011-06-24
8025 | 473 | 512 |  | 512-88-01592 | 540508M60000-011 | CONNECTOR, COMPRESSION, 1/4" | 6 | 6 | 2014-01-27 | 35 | 2013-12-23 | EA | 0 | 0 | 6 | No | 2017-06-19 | 2017-10-27 | 0 | 0
8025 | 473 | 573 |  | 573-09-00017 | 232500-000000011 | COMPLETE QUICK ACTING COUPLE | 3 | -1 | 2014-09-29 | 240 | 2014-02-01 | EA | 0 | 3 | 2 | No | 2014-12-02 | 2017-10-27 | 58.8 | 117.6
8025 | 473 | 573 |  | 573-09-00018 | 232500-000000012 | ADAPTER, FROM 3/8"-18 NPT MA | 6 | -2 | 2014-09-29 | 240 | 2014-02-01 | EA | 0 | 6 | 4 | No | 2014-12-02 | 2017-10-27 | 23.41 | 93.64
8025 | 473 | 581 |  | 581-01-00035 | 500818162300-008 | PIPE,STAINLESS STL,2"IPS,SCH | 1 | 1 | 2014-05-28 | 30 | 2014-04-28 | LF | 0 | 0 | 1 | No | 2013-11-21 | 2017-10-27 | 9.41 | 9.41 | 477 | 2016-10-07
8025 | 473 | 581 |  | 581-01-00041 | 500809000000-011 | PIPE 12", SCH 140, CARBON ST | 15 | 15 | 2014-07-08 | 49 | 2014-05-20 | LF | 0 | 0 | 15 | No | 2013-11-21 | 2017-10-27 | 141.3 | 2119.5 | 477 | 2016-10-07
8025 | 473 | 582 |  | 582-01-00051 | 500814000700-010 | PIPE, STEEL 10" SCHD 80,A500 | 20 | 20 | 2014-07-08 | 30 | 2014-06-08 | LF | 0 | 0 | 20 | No | 2013-12-12 | 2017-10-27 | 60.22 | 1204.4 | 475 | 2016-10-28
8025 | 473 | 986 |  | 986-01-00588 | TEST00-000001033 | HOSE, 1-1/2" RUBBER, MAX WOR | 120 | 120 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 120 | No | 2015-09-08 | 2017-10-27 | 8.59 | 1030.8 | 469 | 2016-01-28
8025 | 473 | 986 |  | 986-01-00614 | 551402-000000005 | ADAPTER, 2-5/8"-8NS-2 X 2, B | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-10-12 | 2017-10-27 | 308 | 308 | 477 | 2016-08-29
8025 | 473 | 995 |  | 995-01-00030 | 500814190700-001 | PIPE, ROUND, 4" DIA, SCH 80 | 5 | 5 | 2014-01-20 | 49 | 2013-12-02 | EA | 0 | 0 | 5 | No | 2015-06-12 | 2017-10-27 | 13.18 | 65.9 | 467 | 2013-05-20
8025 | 473 | 167 |  | 167-03-00063-S00 | -S00 | CONNECTOR, COMPRESSION, 1/8" | 8 | 8 | 2015-07-03 | 123 | 2015-03-02 | EA | 0 | 0 | 8 | No | 2017-04-19 | 2017-10-27 | 0 | 0
8025 | 473 | 256 |  | 256-01-HA070-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | LO | 0 | 0 | 1 | No | 2015-06-29 | 2017-10-27 | 0 | 0 | 483 | 2016-04-28
8025 | 473 | 256 |  | 256-01-V0006-S01 | -S00 | VALVE ACTUATOR | 1 | 1 | 2017-02-23 | 180 | 2016-08-27 | EA | 0 | 0 | 1 | No | 2017-02-23 | 2017-02-23 | 8694 | 8694
8025 | 473 | 259 |  | 259-05-00004-S01 | -S00 | ELBOW, 90 DEG, 12", SHORT | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 1 | No | 2017-06-12 | 2017-10-27 | 995 | 995
8025 | 473 | 259 |  | 259-05-00005-S00 | -S00 | ELBOW, 90 DEG, 8", SHORT | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 733 | 1466
8025 | 473 | 259 |  | 259-05-00005-S01 | -S00 | ELBOW, 90 DEG, 8", SHORT | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-12 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00009-S00 | -S00 | PIPE, 12" IPS, SCH 10S | 3.5 | 3.5 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 3.5 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00009-S01 | -S00 | PIPE, 12" IPS, SCH 10S | 3.5 | 3.5 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 3.5 | No | 2017-06-12 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00009-S01 | -S00 | PIPE, 12" IPS, SCH 10S | 3.5 | 3.5 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 3.5 | No | 2017-06-12 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00011-S00 | -S00 | REDUCER, 12" X 8" CONC, 321 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-24 | 2017-10-27 | 488 | 488
8025 | 473 | 259 |  | 259-05-00028-S00 | -S00 | PIPE 8" IPS, SCH 10S, 321 SS | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00028-S01 | -S00 | PIPE 8" IPS, SCH 10S, 321 SS | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-12 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00070-S00 | -S00 | ELBOW, 45 DEG, 12" LONG RADI | 2 | 2 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00547-S00 | -S00 | TUBE, SQUARE, 3" X 3" | 6.3 | 6.3 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 6.3 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-00561-S00 | -S00 | CLAMP, PIPE, 13-1/4" DIA, SS | 2 | 2 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 300 | 600
8025 | 473 | 259 |  | 259-05-22001-S00 | -S00 | ASSEMBLY, BELLOWS, 6" X 8" | 3 | 3 | 2014-03-14 | 123 | 2013-11-11 | EA | 0 | 0 | 3 | No | 2017-04-24 | 2017-10-27 | 3511 | 10533
8025 | 473 | 259 |  | 259-05-22003-S00 | -S00 | PIPE, 6" IPS, SCH 10, 321 CR | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-22003-S01 | -S00 | PIPE, 6" IPS, SCH 10, 321 CR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-22006-S00 | -S00 | ASSEMBLY, BELLOWS, 6" X 8" | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 1 | No | 2017-04-24 | 2017-10-27 | 3511 | 3511
8025 | 473 | 259 |  | 259-05-22504-S00 | 500814190905-001 | PIPE, 3" IPS, STL, PLAIN | 3 | 3 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 3 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-22504-S01 | 500814190905-001 | PIPE, 3" IPS, STL, PLAIN | 3 | 3 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 3 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-22505-S00 | 501214610005-001 | TUBING, MECHANICAL, 5-1/4"OD | 0.7 | 0.7 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 0.7 | No | 2017-06-21 | 2017-10-27 | 71.5 | 50.05
8025 | 473 | 259 |  | 259-05-22509-S00 | 111201041813-001 | TEE, WT 155 X 10.5, STL, AH3 | 4 | 4 | 2014-01-20 | 240 | 2013-05-25 | LF | 0 | 0 | 4 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-22510-S00 | 500814190705-001 | PIPE, 4"IPS, SCH 80, STL, | 1 | 1 | 2014-01-20 | 49 | 2013-12-02 | LF | 0 | 0 | 1 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-MT001-S00 | -S00 | MECHANICAL TUBING, 4-1/4" OD | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-05-MT001-S01 | -S00 | MECHANICAL TUBING, 4-1/4" OD | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 1 | No | 2017-06-12 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-07-00061-S00 | -S00 | NIPPLE, TOE, STAINLESS STEEL | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 48 | 96
8025 | 473 | 259 |  | 259-07-00061-S01 | -S00 | NIPPLE, TOE, STAINLESS STEEL | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 1 | No | 2017-06-12 | 2017-10-27 | 48 | 48
8025 | 473 | 259 |  | 259-07-00062-S00 | -S00 | CAP, 1/2" IPS,3000# SCRD,STA | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8025 | 473 | 259 |  | 259-07-00062-S01 | -S00 | CAP, 1/2" IPS,3000# SCRD,STA | 1 | 1 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 1 | No | 2017-06-12 | 2017-10-27 | 2.08 | 2.08
8025 | 473 | 437 |  | 437-03-00069-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 |  | 2014-03-03 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-00011-S00 | -S00 | SQUARE TUBING,2x 2x 1/4" WAL | 1 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-01 | 2017-10-27 | 65.1 | 65.1
8025 | 473 | 505 |  | 505-01-P0008-S00 | -S00 | TUBE, CU/NI,90-10,1-1/2" | 8 | 8 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 8 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P0014-S00 | -S00 | TUBE,CPR NKL,90-10,5" IPS X | 9 | 9 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 9 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P0037-S00 | -S00 | TUBE,CPR,3/4",NOM .875" OD X | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P0166-S00 | -S00 | PIPE, STL, 4", PL, SCH 80 IP | 1 | 1 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P9028-S00 | -S00 | TUBE, 1-1/2", NOM, TYPE L, C | 1.5 | 1.5 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1.5 | No | 2017-07-25 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P9029-S00 | -S00 | TUBE, 2", NOM, TYPE L, CU | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2017-07-25 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P9121-S00 | -S00 | PIPE, STN STL, 1-1/4" IPS,SC | 5 | 5 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 5 | No | 2017-07-25 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P9123-S00 | -S00 | PIPE, STN STL, 2-1/2" IPS,SC | 7.5 | 7.5 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 7.5 | No | 2017-07-25 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-01-P9124-S00 | -S00 | PIPE, STN STL, 3" IPS,SCH | 8 | 8 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 8 | No | 2017-07-25 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-03-B0138-S00 | -S00 | SOCKOLET, 5" IPS RUN X 1/4" | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-03-B0213-S00 | -S00 | SOCKOLET, 5" IPS RUN X 1-1/2 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-03-L0299-S00 | -S00 | ELL 90,L.R.,5 IPS,CPR NKL,90 | 5 | 5 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 5 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-03-L0337-S00 | -S00 | ELB, 90 DEG., 1-1/2" IPS, 40 | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8025 | 473 | 505 |  | 505-03-L0421-S00 | -S00 | ELBOW, 90 DEG., 2-1/2" IPS, | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2017-07-25 | 2017-10-27 | 10.23 | 30.69
8025 | 473 | 505 |  | 505-03-L0422-S00 | -S00 | ELBOW, 90 DEG, 3" IPS, BW, L | 5 | 5 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 5 | No | 2017-07-25 | 2017-10-27 | 10.23 | 51.15
8025 | 473 | 505 |  | 505-03-L0434-S00 | -S00 | ELBOW, 45 DEG., 2-1/2" IPS | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2017-07-25 | 2017-10-27 | 8 | 24
8025 | 473 | 505 |  | 505-03-L0435-S00 | -S00 | ELBOW, 45 DEG., 3" IPS, SCH | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-07-25 | 2017-10-27 | 7.39 | 14.78
8025 | 473 | 505 |  | 505-03-M9218-S00 | -S00 | NIPPLE, 1-1/2" IPS, SSTL 316 | 5 | 5 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 5 | No | 2017-06-05 | 2017-10-27 | 129.05 | 645.25
8025 | 473 | 505 |  | 505-03-R9142-S00 | -S00 | REDUCER, CONCENTRIC, 4 X 3, | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-16 | 2017-10-27 | 6.99 | 6.99
8025 | 473 | 505 |  | 505-03-R9143-S00 | -S00 | REDUCER, CONC, 8 X 4, BW, SS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-16 | 2017-10-27 | 66.75 | 66.75
8025 | 473 | 505 |  | 505-03-U0015-S00 | -S00 | UNION,1-1/4"IPS, 3000# SOC W | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-25 | 2017-10-27 | 9.45 | 9.45
8025 | 473 | 505 |  | 505-03-U0043-S00 | -S00 | UNION,SLDR,1-1/2"NOM CU SZ, | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-25 | 2017-10-27 | 25.37 | 25.37
8025 | 473 | 505 |  | 505-03-U0044-S00 | -S00 | UNION,SLDR,2"NOM CU SZ, WROT | 3 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2017-07-25 | 2017-10-27 | 43.19 | 129.57
8025 | 473 | 505 |  | 505-03-U9087-S00 | -S00 | UNION, 1-1/4", SW, SSTL 304L | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-16 | 2017-10-27 | 22.7 | 22.7
8025 | 473 | 505 |  | 505-03-Y9005-S00 | -S00 | Y BRANCH, 2"NOM, 45 DEGREE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-25 | 2017-10-27 | 27.75 | 27.75
8025 | 473 | 506 |  | 506-01-V0020-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | EA | 0 | 0 | 1 | No | 2016-02-26 | 2017-10-27 | 0 | 0 | 481 | 2017-03-08
8025 | 473 | 533 |  | 533-03-HA004-S00 | -S00 | ASSEMBLY, FLEXIBLE HOSE, NAV | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-06-08 | 2017-10-27 | 2678.17 | 2678.17
8025 | 473 | 533 |  | 533-03-HA004-S00 | -S00 | ASSEMBLY, FLEXIBLE HOSE, NAV | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-06-08 | 2017-10-27 | 2678.17 | 2678.17
8028 | 473 | 202 |  | 202-01-00019 | 301P02110903-001 | CABLE, STRAIGHT THROUGH EXTE | 12 | 4 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 4 | No | 2014-01-12 | 2017-10-27 | 7.76 | 31.04
8028 | 473 | 202 |  | 202-01-00056 | 384000000096-001 | SENSOR, LEVEL, 3195MM, 3" FL | 4 | 1 | 2015-02-19 | 123 | 2014-10-19 | EA | 0 | 4 | 5 | No | 2014-01-12 | 2017-10-27 | 1400 | 7000
8028 | 473 | 304 |  | 304-00-00326 | 304938200101-005 | CABLE, ELECTRIC, LS2SUS-19 | 124 | 124 | 2014-01-20 | 120 | 2013-09-22 | LF | 0 | 0 | 124 | No | 2017-06-08 | 2017-10-27 | 9.39 | 1164.36 | 471 | 2015-10-05
8028 | 473 | 304 |  | 304-01-00105 | 308103200102-001 | CABLE, ELECTRIC, LSTNW-3 | 75 | 25 | 2014-01-20 | 80 | 2013-11-01 | FT | 0 | 0 | 25 | No | 2014-02-23 | 2017-10-27 | 0.49 | 12.25
8028 | 473 | 304 |  | 304-01-00164 | 301L03020101-002 | CABLE, ELECTRIC, TXOW-4 | 2000 | 225 | 2014-01-20 | 40 | 2013-12-11 | LF | 0 | 0 | 225 | No | 2014-02-23 | 2017-10-27 | 1.6 | 360
8028 | 473 | 320 |  | 320-01-00001 | 391215001613-001 | RECEPTACLE, DUPLEX, W/GFCI | 191 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 2 | 1 | No | 2014-01-12 | 2017-10-27 | 14.4 | 14.4
8028 | 473 | 320 |  | 320-01-00002 | 380215000030-001 | RECEPTACLE, DUPLEX, 20A, 125 | 122 | 2 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 2 | No | 2014-01-12 | 2017-10-27 | 2.48 | 4.96
8028 | 473 | 320 |  | 320-01-00007 | 380106000026-002 | COVER, DUPLEX RECEPTACLE | 122 | 2 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 2 | No | 2014-01-12 | 2017-10-27 | 1.3 | 2.6
8028 | 473 | 320 |  | 320-01-00027 | 360101050110-001 | TERM BOX, CONN, 600 VAC, 4TE | 4 | 1 | 2014-01-20 | 100 | 2013-10-12 | EA | 0 | 0 | 1 | No | 2014-01-12 | 2017-10-27 | 47 | 47
8028 | 473 | 320 |  | 320-01-00118 | 350101060105-001 | SWITCH, SYM 838.1 | 8 | 1 | 2014-10-10 | 100 | 2014-07-02 | EA | 0 | 0 | 1 | No | 2014-01-12 | 2017-10-27 | 220 | 220
8028 | 473 | 320 |  | 320-01-00415 | 360102080907-002 | BOX, DBL GANG, W/MOUNTING BO | 54 | 22 | 2014-01-20 | 56 | 2013-11-25 | EA | 18 | 0 | 4 | No | 2015-02-06 | 2017-10-27 | 10.5 | 42
8028 | 473 | 321 |  | 321-02-00003 | 320102020000-005 | MCT, 4 x 3 STEEL | 19 | 19 | 2014-01-20 | 40 | 2013-12-11 | EA | 14 | 0 | 5 | No | 2014-02-23 | 2017-10-27 | 84.66 | 423.3
8028 | 473 | 321 |  | 321-02-00010 | 320102020000-012 | MCT, STEEL, 8 X 2 | 13 | 2 | 2014-02-28 | 56 | 2014-01-03 | EA | 0 | 0 | 2 | No | 2014-02-07 | 2017-10-27 | 72.38 | 144.76
8028 | 473 | 321 |  | 321-02-00856 | 711930390000-001 | SCREW, NO.10-24 X 3/4, SS 31 | 150 | 150 | 2014-03-07 | 14 | 2014-02-21 | EA | 0 | 0 | 150 | No | 2015-10-13 | 2017-10-27 | 0.1322 | 19.83 | 475 | 2016-10-12
8028 | 473 | 324 |  | 324-12-01000 | 390200040006-001 | CIRCUIT BREAKER, ALB-1, 5 AM | 2 | 2 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 2 | No | 2014-04-27 | 2017-10-27 | 112 | 224 | 450 | 2010-03-15
8028 | 473 | 324 |  | 324-12-01008 | 390200040017-001 | CIRCUIT BREAKER, ALB-1, 50 A | 2 | 2 | 2014-10-23 | 48 | 2014-09-05 | EA | 0 | 0 | 2 | No | 2017-04-20 | 2017-10-27 | 208 | 416 | 477 | 2017-10-02
8028 | 473 | 324 |  | 324-12-01040 | 392800040000-001 | YOKE HANDLE (2 POLE) | 9 | 9 | 2014-01-20 | 123 | 2013-09-19 | EA | 2 | 0 | 7 | No | 2017-04-13 | 2017-10-27 | 6.9 | 48.3
8028 | 473 | 330 |  | 330-01-00002 | 330306180202-001 | OVHD, FLUOR.LT.FIXTURE, 40W, | 359 | 4 | 2014-01-20 | 40 | 2013-12-11 | EA | 0 | 0 | 4 | No | 2014-02-12 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00006 | 33011-009 | OVHD, FLUOR.LT.FIXTURE, 60W, | 105 | 16 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 16 | No | 2014-02-11 | 2017-10-27 | 307.55 | 4920.8
8028 | 473 | 330 |  | 330-01-00012 | 330306380202-001 | NEALS LIGHT, 60W SYM 333.1E | 163 | 15 | 2014-01-20 | 40 | 2013-12-11 | EA | 1 | 0 | 14 | No | 2014-02-12 | 2017-10-27 | 833.48 | 11668.72
8028 | 473 | 330 |  | 330-01-00024 | 350201300010-001 | SWITCH, DOOR, 1 CKT - NORMAL | 9 | 1 | 2014-01-20 | 40 | 2013-12-11 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 439 | 439
8028 | 473 | 330 |  | 330-01-00026 | 350202090808-001 | SWITCH TOGGLE | 2 | 2 | 2014-01-20 | 40 | 2013-12-11 | EA | 1 | 0 | 1 | No | 2014-02-12 | 2017-10-27 | 21 | 21
8028 | 473 | 330 |  | 330-01-00039 | 330306140202-001 | LIGHT, INCANDESCENT, 110W, W | 8 | 8 | 2014-01-20 | 40 | 2013-12-11 | EA | 6 | 0 | 2 | No | 2014-02-11 | 2017-10-27 | 419 | 838
8028 | 473 | 330 |  | 330-01-00050 | 350200000001-001 | SWITCH, DPDT, 15A-120V | 130 | 2 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 2 | No | 2014-02-11 | 2017-10-27 | 25.295 | 50.59
8028 | 473 | 330 |  | 330-01-00051 | 350200000001-002 | SWITCH, DPST, 15A-120V | 7 | 7 | 2014-01-20 | 56 | 2013-11-25 | EA | 4 | 0 | 3 | No | 2014-02-12 | 2017-10-27 | 4.5 | 13.5
8028 | 473 | 330 |  | 330-01-00053 | 380706000027-001 | COVER, SWITCH, PASS & SEYMOU | 139 | 4 | 2014-01-20 | 56 | 2013-11-25 | EA | 2 | 0 | 2 | No | 2014-02-12 | 2017-10-27 | 2.87 | 5.74
8028 | 473 | 330 |  | 330-01-00055 | 360101450108-001 | NAVY CONNECTION BOX SUBMERSI | 15 | 14 | 2014-12-09 | 40 | 2014-10-30 | EA | 0 | 0 | 14 | No | 2014-02-11 | 2017-10-27 | 69.5 | 973
8028 | 473 | 330 |  | 330-01-00060 | 33013-003 | LANTERN W/RELAY, SYM #101.2 | 12 | 8 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 0 | 8 | No | 2014-02-11 | 2017-10-27 | 76 | 608
8028 | 473 | 330 |  | 330-01-00078 | 330301200103-001 | LIGHT, INCANDESCENT, 50W, RE | 18 | 0 | 2015-02-12 | 90 | 2014-11-14 | EA | 0 | 1 | 1 | No | 2014-02-11 | 2017-10-27 | 169 | 169
8028 | 473 | 330 |  | 330-01-00096 | 330214140101-001 | LAMP, 110W FOR SYM 48.2 LIGH | 7 | 7 | 2014-08-25 | 90 | 2014-05-27 | EA | 0 | 0 | 7 | No | 2016-03-30 | 2017-10-27 | 13.4 | 93.8 | 481 | 2017-10-25
8028 | 473 | 330 |  | 330-01-00099 | 330300000001-001 | LIGHT, SURGICAL CEILING | 1 | 1 | 2015-03-11 | 100 | 2014-12-01 | EA | 0 | 0 | 1 | Yes | 2014-02-06 | 2017-10-27 | 0 | 0 | 477 | 2015-12-02
8028 | 473 | 330 |  | 330-01-00118 | 34001-003 | BATTERY, 6V DRYCELL, TYPE BA | 58 | 58 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 58 | No | 2014-11-10 | 2017-10-27 | 3.51 | 203.58 | 467 | 2015-01-29
8028 | 473 | 330 |  | 330-01-00130 | 361006031212-001 | COVER, SWITCH, WEATHERPROOF | 1 | 1 | 2015-03-11 | 56 | 2015-01-14 | EA | 0 | 0 | 1 | No | 2016-05-19 | 2017-10-27 | 2.1 | 2.1 | 513 | 2005-04-28
8028 | 473 | 330 |  | 330-LK-00001 | 330300-000000344 | LIGHTING, SUB ASSEMBLY KITS | 1 | 1 | 2014-01-20 | 48 | 2013-12-03 | LO | 0 | 0 | 1 | No | 2014-03-10 | 2017-10-27 | 0 | 0
8028 | 473 | 410 |  | 410-01-00026 | 360303050000-001 | IP PHONE ENCLOSURE, SSTL | 2 | 2 | 2015-06-09 | 56 | 2015-04-14 | EA | 0 | 0 | 2 | No | 2017-09-22 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00026 | 360101150103-001 | NAVY CONNECTION BOX, SUBMERS | 2 | 1 | 2015-08-17 | 40 | 2015-07-08 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 143 | 143
8028 | 473 | 422 |  | 422-01-00027 | 36001-002 | NAVY CONNECTION BOX, WATERTI | 9 | 3 | 2015-02-12 | 84 | 2014-11-20 | EA | 1 | 0 | 2 | No | 2014-02-10 | 2017-10-27 | 55 | 110
8028 | 473 | 432 |  | 432-01-00013 | 37001-006 | BOX, TELEPHONE HEADSET STOWA | 14 | 3 | 2014-01-20 | 90 | 2013-10-22 | EA | 1 | 0 | 2 | No | 2014-02-07 | 2017-10-27 | 151 | 302
8028 | 473 | 432 |  | 432-01-00018 | 37245-002 | BOOTH, ACOUSTIC, TEL, HOSE M | 6 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-07 | 2017-10-27 | 1539 | 1539
8028 | 473 | 433 |  | 433-01-00037 | 310906110053-001 | CONNECTOR, FIBER OPTIC, STRA | 2 | 2 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 2 | No | 2016-05-06 | 2017-10-27 | 742.5 | 1485 | 479 | 2017-09-22
8028 | 473 | 433 |  | 433-01-00038 | 310700000043-001 | BACKSHELL, ENVIRONMENTAL, ST | 2 | 2 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 2 | No | 2016-05-06 | 2017-10-27 | 249.05 | 498.1 | 479 | 2017-09-22
8028 | 473 | 433 |  | 433-01-00039 | 310900110000-001 | CONTACT, FIBER OPTIC SOCKET | 8 | 8 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 8 | No | 2016-05-06 | 2017-10-27 | 31.53 | 252.24 | 477 | 2017-03-15
8028 | 473 | 433 |  | 433-01-00812 | 400406150003-001 | LOUDSPEAKER, LS-387B/SIC, SY | 49 | 4 | 2014-01-20 | 30 | 2013-12-21 | EA | 3 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 439 | 439
8028 | 473 | 434 |  | 434-01-00006 | 371100000023-001 | LCD PROJECTOR MOUNT | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0.36 | 0.36 | 650 | 2011-07-21
8028 | 473 | 434 |  | 434-01-00007 | 371100000024-001 | LCD PROJECTOR TUNER | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 3.6 | 3.6 | 650 | 2011-10-03
8028 | 473 | 434 |  | 434-01-00008 | 371100000024-002 | PROJECTOR SCREEN, WALL MOUNT | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 628 | 628 | 465 | 2013-05-21
8028 | 473 | 434 |  | 434-01-00110 | 371100000000-002 | LCD PROJECTOR, VIEWSONIC | 1 | 1 | 2014-12-09 | 21 | 2014-11-18 | EA | 0 | 0 | 1 | No | 2014-10-01 | 2017-10-27 | 0 | 0
8028 | 473 | 434 |  | 434-01-00113 | 38502300002F-001 | PAD, ATTENUATION SIGNAL STRE | 2 | 2 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 2 | No | 2015-01-28 | 2017-10-27 | 0 | 0
8028 | 473 | 434 |  | 434-01-00114 | 38502300002G-001 | PAD, ATTENUATION SIGNAL STRE | 4 | 4 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 4 | No | 2015-01-28 | 2017-10-27 | 0 | 0
8028 | 473 | 434 |  | 434-01-00119 | 38502300002M-001 | PAD, ATTENUATION SIGNAL STRE | 1 | 1 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 1 | No | 2015-01-28 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-01-00069 | 361006030362-001 | BOX, OUTLET, STK NO. 36003-0 | 23 | -2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 9 | No | 2014-02-11 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-08-00062 | 381800000067-001 | RESISTOR, 1K OHM, 1/4 W, AXI | 2 | 2 | 2015-01-19 | 30 | 2014-12-20 | EA | 0 | 0 | 2 | No | 2016-10-20 | 2017-10-27 | 0.2 | 0.4 | 475 | 2017-01-23
8028 | 473 | 436 |  | 436-08-00063 | 381800000068-001 | RESISTOR, 10K OHM, 1/4 W,AXI | 6 | 6 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 6 | No | 2016-10-20 | 2017-10-27 | 0.02 | 0.12 | 477 | 2017-01-23
8028 | 473 | 436 |  | 436-08-00063 | 381800000068-001 | RESISTOR, 10K OHM, 1/4 W,AXI | 6 | 6 | 2014-09-15 | 123 | 2014-05-15 | EA | 0 | 0 | 6 | No | 2016-10-20 | 2017-10-27 | 0.02 | 0.12 | 477 | 2017-01-23
8028 | 473 | 436 |  | 436-08-00092 | 360101400110-001 | NAVY CONNECTION BOX, SYM 520 | 1 | 1 | 2015-01-05 | 56 | 2014-11-10 | EA | 0 | 0 | 1 | No | 2016-03-07 | 2017-10-27 | 62 | 62 | 475 | 2016-03-18
8028 | 473 | 436 |  | 436-09-00009 | 400104000000-001 | BELL, 88DB, 24VDC, EDWARDS S | 1 | 1 | 2015-06-09 | 35 | 2015-05-05 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 131 | 131
8028 | 473 | 436 |  | 436-10-00003 | 380900000000-001 | RELAY/SOCKET COMBO, 1 POLE, | 2 | 1 | 2014-01-20 | 48 | 2013-12-03 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 36.28 | 36.28
8028 | 473 | 437 |  | 437-04-S0007 | 360302011441-001 | HEATER RELAY BOX, DRS FAN CO | 3 | 3 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 3 | No | 2015-03-11 | 2017-10-27 | 147 | 441 | 479 | 2015-10-27
8028 | 473 | 437 |  | 437-05-00014 | 371602000600-001 | REMOTE CONTROL ENCLOSURE | 7 | 7 | 2014-08-18 | 48 | 2014-07-01 | EA | 0 | 0 | 7 | No | 2017-02-13 | 2017-10-27 | 0.71 | 4.97 | 650 | 2012-07-02
8028 | 473 | 437 |  | 437-12-00111 | 710204510000-001 | SPRING NUT, 3/8", STAINLESS | 238 | 238 | 2014-10-23 | 14 | 2014-10-09 | EA | 0 | 0 | 238 |  | 2014-02-10 | 2017-10-27 | 7.38 | 1756.44
8028 | 473 | 438 |  | 438-01-00114 | 310900140059-001 | CONNECTOR, M24308/4-1 | 6 | 4 | 2014-01-20 | 42 | 2013-12-09 | EA | 0 | 0 | 4 | No | 2014-06-16 | 2017-10-27 | 5.54 | 22.16
8028 | 473 | 438 |  | 438-01-00500 | SRV300-032200001 | VNDR SUPPORT,PIN PELORUS STA | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-05-16 | 2017-10-27 | 1800 | 1800 | 469 | 2016-12-19
8028 | 473 | 439 |  | 439-01-00037 | 382300000082-001 | VGA/RGD VIDEO ADAPTER, MAGEN | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-06-16 | 2017-10-27 | 332.05 | 332.05 | 469 | 2013-04-10
8028 | 473 | 439 |  | 439-01-00038 | 303E00000000-003 | CABLE, VGA TO VGA | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-06-16 | 2017-10-27 | 25 | 50 | 465 | 2013-05-21
8028 | 473 | 453 |  | 453-04-00020 | 450300000000-001 | WAVEGUIDE HANGER KIT, FOR | 1 | 1 | 2015-11-09 | 120 | 2015-07-12 | EA | 0 | 0 | 1 | No | 2016-04-15 | 2017-10-27 | 0 | 0
8028 | 473 | 512 |  | 512-88-01590 | 681200000001-001 | SWITCH, DIFFERENTIAL STATIC | 6 | 6 | 2014-08-18 | 105 | 2014-05-05 | EA | 0 | 0 | 6 | No | 2017-06-19 | 2017-10-27 | 0 | 0
8028 | 473 | 512 |  | 512-88-05210 | 270400-000000002 | GAUGE, DIFFERENTIAL PRESSURE | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2017-02-07 | 2017-10-27 | 360.25 | 360.25 | 477 | 2017-07-20
8028 | 473 | 514 |  | 514-01-00996 | SRV523-032800005 | VENDOR/REFRIGERATION MECHANI | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2013-10-10 | 2017-10-27 | 95.4166 | 95.4166 | 471 | 2016-06-06
8028 | 473 | 514 |  | 514-01-00997 | SRV523-032200004 | VENDOR SERVICES | 1 | 1 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 1 | No | 2013-10-09 | 2017-10-27 | 80 | 80 | 469 | 2017-08-10
8028 | 473 | 514 |  | 514-01-00999 | SRV523-032800003 | VENDOR SERVICES | 1 | 1 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 1 | No | 2013-10-09 | 2017-10-27 | 160 | 160 | 465 | 2014-07-17
8028 | 473 | 514 |  | 514-01-01001 | SRV523-032200002 | VENDOR SERVICE, ADRICK MARIN | 1 | 1 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 1 | No | 2013-10-09 | 2017-10-27 | 15375 | 15375 | 450 | 2010-09-09
8028 | 473 | 555 |  | 555-02-00003 | 765046000001-001 | AQUEOUS FILM FORMING (AFFF) | 41 | 39 | 2014-02-24 | 42 | 2014-01-13 | EA | 33 | 0 | 6 | No | 2013-10-24 | 2017-10-27 | 127.2 | 763.2
8028 | 473 | 555 |  | 555-07-17D11 | 503000-000000024 | GAGE ASSY, DIFFERENTIAL PRES | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | No | 2013-09-18 | 2017-10-27 | 1372.88 | 1372.88
8028 | 473 | 555 |  | 555-07-M0003 | 54E405-000000001 | NO-FLOW DEVICE, EXCESS FLOW | 169 | 1 | 2014-02-03 | 180 | 2013-08-07 | EA | 0 | 0 | 1 | No | 2013-10-24 | 2017-10-27 | 215 | 215
8028 | 473 | 571 |  | 571-01-00095 | 550502-000000005 | PROBE RECEIVER, HYDRASEARCH | 1 | 0 | 2014-12-16 | 120 | 2014-08-18 | EA | 0 | 1 | 1 | No | 2013-08-06 | 2017-10-27 | 3614 | 3614 | 469 | 2014-06-06
8028 | 473 | 571 |  | 571-01-00099 | 550502-000000004 | ADAPTER (FOR ROBB COUPLING) | 1 | 0 | 2014-12-16 | 120 | 2014-08-18 | EA | 0 | 1 | 1 | No | 2013-08-06 | 2017-10-27 | 1261.75 | 1261.75 | 469 | 2013-10-23
8028 | 473 | 573 |  | 573-01-00008 | 231900-000000002 | TWIST LOCK STACK DOUBLE CONE | 70 | 70 | 2015-06-26 | 45 | 2015-05-12 | EA | 54 | 0 | 16 | No | 2013-12-12 | 2017-10-27 | 26 | 416
8028 | 473 | 573 |  | 573-01-00019 | 231900-000000027 | OVERHEAD SLIP JOINT 9" W 4" | 16 | 16 | 2015-06-26 | 14 | 2015-06-12 | IN | 0 | 0 | 16 | No | 2013-12-12 | 2017-10-27 | 1953 | 31248 | 450 | 2012-01-19
8028 | 473 | 581 |  | 581-01-MS002 | SRV524-030900018 | SERVICE, MACHINING, WILDCAT | 1 | 1 | 2014-05-28 | 123 | 2014-01-25 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 23836.8 | 23836.8 | 467 | 2014-02-10
8028 | 473 | 583 |  | 583-01-STR01 | SRV300-032500000 | STORAGE COST, TO FMM BY VEND | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-05-13 | 2017-10-27 | 0 | 0
8028 | 473 | 583 |  | 583-03-00017 | 702000-000000002 | HOOK, QUICK RELEASE, SEA CAT | 1 | 0 | 2014-09-29 | 30 | 2014-08-30 | EA | 0 | 1 | 1 | No | 2015-11-12 | 2017-10-27 | 2386.33 | 2386.33 | 471 | 2017-02-10
8028 | 473 | 610 |  | 610-01-0001A | 760107-000000001 | EXTENSION, 5'-0" LG, FOR C02 | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2016-10-18 | 2017-10-27 | 199.6 | 399.2 | 465 | 2013-05-20
8028 | 473 | 612 |  | 612-01-00999 | SRV521-030600006 | SERVICES FOR SESCO TO COME I | 1 | 1 | 2015-01-16 | 123 | 2014-09-15 | EA | 0 | 0 | 1 | No | 2014-01-21 | 2017-10-27 | 8326.5 | 8326.5 | 471 | 2016-07-26
8028 | 473 | 624 |  | 624-01-00022 | 610300-000000017 | DOOR, JOINER, MODULAR | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0 | 601 | 2003-01-10
8028 | 473 | 631 |  | 631-00-V0001 | SRV525-032700002 | SERVICE, PO FOR CONTRACTING | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 0 | 0 | 471 | 2015-08-11
8028 | 473 | 635 |  | 635-00-V0003 | SRV525-030600053 | SERVICE TO PROVIDE HOTWORK L | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2014-08-15 | 2017-10-27 | 1 | 1 | 471 | 2014-08-07
8028 | 473 | 637 |  | 637-94-00002 | 712400-000000002 | WELD STUDS | 8 | 8 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 8 | No | 2014-09-09 | 2017-10-27 | 0 | 0
8028 | 473 | 637 |  | 637-94-00S10 | 090300-000000022 | CURTAIN PLATE ASSEMBLY | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2014-09-08 | 2017-10-27 | 0 | 0
8028 | 473 | 640 |  | 640-02-00040 | 740200-000000010 | SIDEBOARD, MODULAR, ALUMINUM | 2 | 2 | 2014-12-09 | 0 | 2014-12-09 | EA | 0 | 0 | 2 | No | 2015-12-15 | 2017-10-27 | 0 | 0 | 475 | 2017-07-11
8028 | 473 | 644 |  | 644-01-00001 | 735706-000000002 | SANITARY MODULE, TYPE 1 | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 9.93 | 9.93 | 361 | 2016-09-07
8028 | 473 | 651 |  | 651-00-V0001 | SRV525-030600098 | SERVICES, SUBCONTRACT, MATER | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2013-08-01 | 2017-10-27 | 62641.48 | 62641.48 | 467 | 2012-05-24
8028 | 473 | 651 |  | 651-01-00014 | 731901-000000001 | DOUBLE COMBINATION OVEN | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2013-04-19 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8028 | 473 | 651 |  | 651-01-00055 | 713022-000000001 | BOLT,REG HEX HD (VENDOR FURN | 62 | 62 | 2014-01-20 | 0 | 2014-01-20 | EA | 0 | 0 | 62 | No | 2015-09-04 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8028 | 473 | 651 |  | 651-01-00075 | 712400-000000004 | STUD, WELDING, 3/8-16UNC, SS | 8 | 8 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 8 | No | 2014-12-03 | 2017-10-27 | 544 | 4352 | 601 | 2004-11-14
8028 | 473 | 651 |  | 651-01-00132 | 712200000000-002 | SCREW, 1/4-20 UNC-2A, SS 316 | 16 | 16 | 2014-06-24 | 123 | 2014-02-21 | EA | 0 | 0 | 16 | No | 2015-09-08 | 2017-10-27 | 0.502 | 8.032 | 465 | 2015-02-25
8028 | 473 | 651 |  | 651-01-0017B | 731201-000000016 | SUB-BASE EXTENSION/SUB-BASE | 1 | 1 | 2015-01-12 | 45 | 2014-11-28 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8028 | 473 | 651 |  | 651-01-0019A | 731200-000000002 | SUB-BASE FOR U/C REFRIGERATO | 4 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2013-04-22 | 2017-10-27 | 0 | 0
8028 | 473 | 651 |  | 651-01-0019B | 731200-000000006 | SUB-BASE FOR U/C REFRIGERATO | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2015-01-22 | 2017-10-27 | 0 | 0
8028 | 473 | 651 |  | 651-01-0035A | 732600-000000001 | FOOD PROCESSOR, ELECTRIC | 1 | -1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 2 | 1 | No | 2014-12-08 | 2017-10-27 | 0 | 0 | 601 | 2002-12-12
8028 | 473 | 651 |  | 651-01-0036C | 731201-000000017 | SUB-BASE EXTENSION/SUB-BASE | 1 | 1 | 2014-12-09 | 45 | 2014-10-25 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 481 | 2016-12-16
8028 | 473 | 651 |  | 651-01-0071D | 110600-000000006 | BACKING BAR, IAW DET 1-23-2A | 2 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2013-04-22 | 2017-10-27 | 27.38 | 27.38
8028 | 473 | 651 |  | 651-01-0082A | 733300-000000001 | COVER, ACCESS, IAW DET 1-23- | 2 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2013-04-22 | 2017-10-27 | 14.4 | 14.4
8028 | 473 | 651 |  | 651-01-0082D | 725818-000000007 | SWAYBRACE, MICROWAVE SHELF, | 1 | 1 | 2014-07-29 | 123 | 2014-03-28 | EA | 0 | 0 | 1 | No | 2016-02-16 | 2017-10-27 | 0 | 0
8028 | 473 | 651 |  | 651-01-00S14 | 730100-000000001 | LEGS, MICROWAVE, IAW DET 1-2 | 36 | 24 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 24 | No | 2014-04-17 | 2017-10-27 | 13.33 | 319.92
8028 | 473 | 651 |  | 651-01-00S16 | 730100-000000004 | LEG, TOASTER, IAW 1-23-1A | 4 | 4 | 2014-12-09 | 180 | 2014-06-12 | EA | 0 | 0 | 4 | No | 2015-09-08 | 2017-10-27 | 22.7 | 90.8 | 465 | 2014-11-10
8028 | 473 | 651 |  | 651-01-00S20 | 732401-000000002 | CASING, TRAY DISPENSER, SS 3 | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | EA | 0 | 0 | 1 | No | 2015-09-08 | 2017-10-27 | 0 | 0
8028 | 473 | 652 |  | 652-01-00002 | 780600000000-002 | LOCKER, MEDICAL, PORTABLE | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 487 | 487 | 450 | 2009-08-04
8028 | 473 | 652 |  | 652-01-00002 | 780600000000-002 | LOCKER, MEDICAL, PORTABLE | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 487 | 487 | 450 | 2009-08-04
8028 | 473 | 652 |  | 652-01-00016 | 780600000000-001 | FIRST AID BOX, SHALL BE IAW | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-05-11 | 2017-10-27 | 450 | 450 | 450 | 2009-07-22
8028 | 473 | 664 |  | 664-01-00003 | 780800-000000018 | STOWAGE CONTAINER, EEBD, SHA | 2 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2014-05-11 | 2017-10-27 | 0 | 0 | 467 | 2016-08-05
8028 | 473 | 664 |  | 664-01-00108 | 780511-000000004 | WIRE ROPE, 3/32", CRES 304 | 0.16 | 0.16 | 2014-08-18 | 123 | 2014-04-17 | EA | 0 | 0 | 0.1 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8028 | 473 | 664 |  | 664-01-00132 | 780511-000000005 | WIRE SLICE, HEAVY, AL, #4 WI | 3 | 3 | 2014-08-18 | 123 | 2014-04-17 | EA | 0 | 0 | 3 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8028 | 473 | 664 |  | 664-01-00133 | 780511-000000006 | RING TERMINAL, #12-10 WIRE | 0.25 | 0.25 | 2014-08-18 | 123 | 2014-04-17 | PG | 0 | 0 | 0.2 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8028 | 473 | 664 |  | 664-01-0043N | 780511-000000002 | CLIP, REMOVABLE BATTEN, AL | 6 | 6 | 2014-08-18 | 123 | 2014-04-17 | EA | 0 | 0 | 6 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8028 | 473 | 664 |  | 664-01-0043P | 780511-000000003 | RETAINER, BATTEN, ALUMINUM | 6 | 6 | 2014-08-18 | 123 | 2014-04-17 | EA | 0 | 0 | 6 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8028 | 473 | 664 |  | 664-01-043AC | 780511-000000001 | BATTEN, REMOVABLE, ALUMINUM | 3 | 3 | 2014-08-18 | 123 | 2014-04-17 | EA | 0 | 0 | 3 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8028 | 473 | 664 |  | 664-02-00002 | 710130020038-004 | BOLT, HEX HD, 1/2"-13UNC-2A | 24 | 24 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 24 | No | 2014-05-05 | 2017-10-27 | 0.119 | 2.856 | 471 | 2014-09-15
8028 | 473 | 664 |  | 664-02-00003 | 710202020000-003 | NUT, HEXAGON, 1/2"-13UNC-2B | 36 | 36 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 36 | No | 2014-05-05 | 2017-10-27 | 0.079 | 2.844 | 471 | 2014-09-15
8028 | 473 | 664 |  | 664-02-00016 | 710830000030-006 | WASHER, FLAT, 1/2" NOM, STEE | 36 | 36 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 36 | No | 2014-05-05 | 2017-10-27 | 0.05 | 1.8 | 471 | 2014-09-15
8028 | 473 | 664 |  | 664-02-00017 | 710130020038-005 | BOLT, HEX HD, 1/2-13UNC-2A, | 12 | 12 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 12 | No | 2014-05-05 | 2017-10-27 | 0.214 | 2.568 | 471 | 2014-09-15
8028 | 473 | 664 |  | 664-02-00023 | 704300-000000024 | STRAP, 2" WIDE, 26" LG, WIRE | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-05 | 2017-10-27 | 49.27 | 197.08 | 481 | 2016-02-03
8028 | 473 | 664 |  | 664-02-0008M | 100401-000000011 | PLATE, PATCH, SQUARE SIZE 1 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 35.46 | 141.84 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-0008N | 100401-000000012 | PLATE, PATCH, SQUARE SIZE 2 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 40.56 | 162.24 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-0008P | 100401-000000013 | PLATE, PATCH, SQUARE SIZE 3 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 20.94 | 83.76 | 467 | 2012-08-28
8028 | 473 | 664 |  | 664-02-0008R | 100401-000000014 | PLATE, PATCH, SQUARE SIZE 4 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 60.97 | 243.88 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-0008T | 100401-000000015 | PLATE, PATCH, ROUND, SIZE 1 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 35.46 | 141.84 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-0008U | 100401-000000016 | PLATE, PATCH, ROUND, SIZE 2 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 40.56 | 162.24 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-0008V | 100401-000000017 | PLATE, PATCH, ROUND, SIZE 3 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 49.06 | 196.24 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-0008W | 100401-000000018 | PLATE, PATCH, ROUND, SIZE 4 | 4 | 0 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 4 | 4 | No | 2014-05-06 | 2017-10-27 | 60.97 | 243.88 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-000S5 | 780804-000000001 | STOWAGE, ASSY, PLATE PATCH | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-19 | 2017-10-27 | 167.34 | 167.34 | 467 | 2012-02-27
8028 | 473 | 664 |  | 664-02-000S6 | 727330-000000006 | STAPLE ASSY, IAW DET 1-11-2A | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2014-05-05 | 2017-10-27 | 56.38 | 112.76 | 467 | 2012-08-22
8028 | 473 | 664 |  | 664-02-00119 | 780800-000000004 | SCBA STWG, MDL-12 | 7 | 7 | 2014-01-20 | 77 | 2013-11-04 | EA | 0 | 0 | 7 | No | 2014-05-05 | 2017-10-27 | 1146 | 8022 | 465 | 2014-03-11
8028 | 473 | 664 |  | 664-02-00123 | 780600-000000008 | LOCKER, TRAINING SCBA STOWAG | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-05-05 | 2017-10-27 | 1652 | 1652 | 450 | 2009-08-25
8028 | 473 | 664 |  | 664-02-00130 | 780808-000000001 | LOCKER, STOWAGE, FOR EEBD | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-05-05 | 2017-10-27 | 737 | 737 | 450 | 2009-08-25
8028 | 473 | 664 |  | 664-02-00137 | 710000000000-001 | STUD, TAPPED, COMMERCIAL | 28 | 28 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 28 | No | 2014-09-19 | 2017-10-27 | 0.76 | 21.28 | 467 | 2012-06-21
8028 | 473 | 664 |  | 664-02-00170 | 780600-000000001 | LOCKER, SCBA STOWAGE, MDL-9N | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-05-05 | 2017-10-27 | 5581 | 5581 | 465 | 2014-02-27
8028 | 473 | 664 |  | 664-02-00S50 | 780800-000000007 | STOWAGE ASSY, BOX PATCH | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-09-19 | 2017-10-27 | 194.11 | 194.11 | 467 | 2012-08-22
8028 | 473 | 982 |  | 982-01-JP500 | SRV520-011000032 | JP-5 (F44) AIRCRAFT FUEL FOR | 38000 | 24988 | 2014-01-20 | 123 | 2013-09-19 | GL | 0 | 0 | 24988 | No | 2015-08-25 | 2017-10-27 | 2.533 | 63294.604
8028 | 473 | 986 |  | 986-01-00562 | SRV656-011000002 | VENDOR SERVICES, CONDUCT SCB | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-06-26 | 2017-10-27 | 8500 | 8500 | 467 | 2015-08-26
8028 | 473 | 986 |  | 986-01-00596 | SRV656-012400001 | VNDR SRVC, PIPE FLUSHER RENT | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2015-10-20 | 2017-10-27 | 80612.4 | 80612.4 | 470 | 2016-02-25
8028 | 473 | 986 |  | 986-01-00893 | 330200000001-001 | LAMP, EIKO 757, 28V, BAYONET | 10 | 10 | 2014-01-20 | 56 | 2013-11-25 | PG | 0 | 0 | 10 | No | 2017-10-13 | 2017-10-27 | 0 | 0
8028 | 473 | 986 |  | 986-01-00894 | 330200000001-002 | LAMP, 2.5V, T1 3/4 SCREW BAS | 15 | 15 | 2014-01-20 | 56 | 2013-11-25 | PG | 0 | 0 | 15 | No | 2017-10-18 | 2017-10-27 | 0 | 0
8028 | 473 | 992 |  | 992-01-00038 | SRV515-011900001 | SERVICE, PHOTOGRAPHER TO DOC | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2016-02-24 | 2017-10-27 | 1 | 1 | 361 | 2016-09-23
8028 | 473 | 992 |  | 992-01-00102 | SRV515-030500004 | FAB TRANSITION RAMPS, SUPPOR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-02-04 | 2017-10-27 | 20 | 20 | 403 | 2007-02-07
8028 | 473 | 996 |  | 996-01-00009 | SRV533-021700003 | SERVICES, DIVER. UNDERWATER | 1 | 1 | 2014-01-20 | 100 | 2013-10-12 | EA | 0 | 0 | 1 | No | 2016-02-24 | 2017-10-27 | 0 | 0 | 360 | 2015-11-10
8028 | 473 | 996 |  | 996-01-00010 | SRV533-021700004 | SERVICE, DIVER. UNDERWATER T | 1 | 1 | 2014-01-20 | 100 | 2013-10-12 | EA | 0 | 0 | 1 | No | 2016-02-24 | 2017-10-27 | 0 | 0 | 469 | 2015-02-20
8028 | 473 | 996 |  | 996-01-00011 | SRV533-021700005 | SERVICE, DIVER. UNDERWATER T | 1 | 1 | 2014-01-20 | 100 | 2013-10-12 | EA | 0 | 0 | 1 | No | 2016-02-24 | 2017-10-27 | 1 | 1 | 477 | 2017-09-28
8028 | 473 | 996 |  | 996-01-00012 | SRV533-021800001 | SERVICES, TUG BOATS | 1 | 1 | 2014-01-20 | 100 | 2013-10-12 | EA | 0 | 0 | 1 | No | 2016-02-24 | 2017-10-27 | 1 | 1 | 474 | 2016-09-23
8028 | 473 | 996 |  | 996-01-00027 | 701500-000000006 | WIRE ROPE PENDANT, 1", 6 X 1 | 2 | 2 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 2 | No | 2016-05-13 | 2017-10-27 | 193.45 | 386.9
8028 | 473 | 202 |  | 202-01-00055-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 469 | 2013-05-14
8028 | 473 | 202 |  | 202-01-00056-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00057-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00204-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00210-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00224-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00226-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00227-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00301-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00303-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00304-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00422-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00422-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00423-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00435-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00437-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-01-00439-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 469 | 2015-02-02
8028 | 473 | 202 |  | 202-01-00443-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 202 |  | 202-09-00006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 256 |  | 256-01-SG001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-05-14 | 60 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00012-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00016-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00019-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00020-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00026-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00110-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00117-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00118-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00125-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-01-00128-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-09-00004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8028 | 473 | 320 |  | 320-09-00022-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 324 |  | 324-01-00083-L34 | -L34 | PROVISIONING TECH DOC. | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2014-03-10 | 2017-10-27 | 0 | 0
8028 | 473 | 324 |  | 324-22-00006-L06 | -L06 | REPORT, IN-PLANT TEST, IAW A | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | LO | 0 | 0 | 1 | No | 2017-04-12 | 2017-10-27 | 0 | 0 | 467 | 2017-06-05
8028 | 473 | 330 |  | 330-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00005-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00009-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00010-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00012-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00013-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00014-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00016-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00017-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00019-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00020-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00021-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00023-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00024-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00025-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00027-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 330 |  | 330-01-00028-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-12-02
8028 | 473 | 330 |  | 330-01-00071-800 | 330304550103-002 | YELLOW FILTER FOR SYM 317 LI | 34 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-12 | 2017-10-27 | 33.55 | 33.55
8028 | 473 | 330 |  | 330-01-00099-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-03-10 | 2017-10-27 | 0 | 0
8028 | 473 | 420 |  | 420-02-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 420 |  | 420-02-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00005-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00007-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00007-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00010-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00020-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00021-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00022-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00025-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00026-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00027-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00028-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00030-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00042-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00200-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8028 | 473 | 422 |  | 422-01-00201-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-12 | 2017-10-27 | 0 | 0
8028 | 473 | 432 |  | 432-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 432 |  | 432-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 432 |  | 432-01-00004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0 | 450 | 2009-08-12
8028 | 473 | 432 |  | 432-01-00006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0 | 450 | 2009-08-12
8028 | 473 | 432 |  | 432-01-00009-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 432 |  | 432-01-00010-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 432 |  | 432-01-00016-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00002-828 | 413500-000000030 | ISOLATION KIT, VIBRATION | 1 | 1 | 2015-09-04 | 48 | 2015-07-18 | KT | 0 | 0 | 1 | No | 2016-05-20 | 2017-10-27 | 0 | 0 | 485 | 2017-07-26
8028 | 473 | 433 |  | 433-01-00010-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00011-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00013-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00014-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00015-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00810-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00811-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00812-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00813-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00817-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00827-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00829-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 433 |  | 433-01-00830-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 434 |  | 434-01-00020-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 434 |  | 434-01-00086-801 | 410800-000000002 | BOOT, CONNECTOR, SHAKESPEARE | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0 | 450 | 2010-05-03
8028 | 473 | 434 |  | 434-01-00086-802 | 410800-000000003 | SCREW, #6 X 1/2" | 2 | 2 | 2014-12-09 | 91 | 2014-09-09 | EA | 0 | 0 | 2 | No | 2014-02-15 | 2017-10-27 | 0 | 0 | 450 | 2010-06-15
8028 | 473 | 434 |  | 434-01-00086-803 | 300100000000-007 | CABLE, COAX, RG-59, 30 FT | 1 | 1 | 2014-12-09 | 120 | 2014-08-11 | LF | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0.48 | 0.48 | 469 | 2013-10-29
8028 | 473 | 434 |  | 434-01-00086-804 | 410800-000000004 | CONNECTOR, F TYPE, SCREW ON | 4 | 4 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 4 | No | 2014-02-15 | 2017-10-27 | 6.96 | 27.84 | 465 | 2013-09-05
8028 | 473 | 436 |  | 436-03-00009-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-09-14
8028 | 473 | 436 |  | 436-08-00082-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-08-00083-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-08-00085-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-08-00086-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-10-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-10-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-10-00004-S00 | -S00 | PUSHBUTTON CONTROL STATION, | 5 | 0 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 5 | No | 2017-05-11 | 2017-10-27 | 500 | 2500
8028 | 473 | 436 |  | 436-10-00005-S00 | -S00 | PUSHBUTTON CONTROL STATION, | 4 | 0 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 4 | No | 2017-05-11 | 2017-10-27 | 645 | 2580
8028 | 473 | 436 |  | 436-10-S0001-S00 | -S00 | SRVC, MODIFY SUB ASSY, CF 23 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-08 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-10-S0003-S00 | -S00 | SRVC, MODIFY SUB ASSY, CF 23 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-08 | 2017-10-27 | 0 | 0
8028 | 473 | 436 |  | 436-10-S0004-S00 | -S00 | SRVC, MODIFY SUB ASSY, CF 23 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-05-08 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-03-00044-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-03-00045-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-03-00045-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-04-00069-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-04-00070-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-04-00140-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-04-00178-S00 | -S00 | NAVY CONNECTION BOX, SYM 520 | 2 | 2 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 2 | No | 2017-06-15 | 2017-10-27 | 66 | 132
8028 | 473 | 437 |  | 437-05-00013-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-05-00203-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-05-00204-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-05-00205-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 437 |  | 437-05-00207-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8028 | 473 | 439 |  | 439-01-00006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0
8028 | 473 | 441 |  | 441-01-00001-806 | 412200-000000019 | COMMUNICATION, TERMINAL CUTO | 7 | 1 | 2015-01-19 | 123 | 2014-09-18 | EA | 0 | 0 | 1 | No | 2014-02-19 | 2017-10-27 | 155 | 155
8028 | 473 | 443 |  | 443-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0 | 481 | 2016-01-05
8028 | 473 | 514 |  | 514-01-SG001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-19 | 60 | 2014-12-21 | EA | 0 | 0 | 1 | No | 2013-10-22 | 2017-10-27 | 0 | 0
8028 | 473 | 533 |  | 533-01-E0006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 477 | 2016-03-11
8028 | 473 | 542 |  | 542-01-E0007-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-02-03
8028 | 473 | 542 |  | 542-01-M0005-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0 | 481 | 2016-09-15
8028 | 473 | 711 |  | 711-01-00013-8AU | 870200-000000296 | CABLE ASSY, PART OF FCS57-00 | 1 | 1 | 2014-10-17 | 123 | 2014-06-16 | EA | 0 | 0 | 1 | No | 2016-07-07 | 2017-10-27 | 0 | 0
8028 | 473 | 711 |  | 711-01-00013-8AV | 870200-000000297 | CONN ASSY, PART OF FCS57-001 | 1 | 1 | 2014-10-17 | 123 | 2014-06-16 | EA | 0 | 0 | 1 | No | 2016-07-07 | 2017-10-27 | 0 | 0
8034 | 473 | 259 |  | 259-05-22999 | SRV527-030900003 | SRVC, DRILL EXPANSION JOINTS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-08-17 | 2017-10-27 | 0 | 0
8034 | 473 | 262 |  | 262-01-M0034 | 561826590203-00B | EXPANSION JOINT, 5", SINGLE | 1 | 0 | 2014-03-14 | 49 | 2014-01-24 | EA | 0 | 1 | 1 | No | 2017-09-15 | 2017-10-27 | 0 | 0
8034 | 473 | 262 |  | 262-01-M0035 | 561826600203-00D | EXPANSION JOINT, 8", QUAD AR | 2 | 2 | 2014-02-28 | 49 | 2014-01-10 | EA | 0 | 0 | 2 | No | 2017-09-15 | 2017-10-27 | 0 | 0
8034 | 473 | 441 |  | 441-06-00013 | 451400030000-001 | ADAPTER, 90 DEG, FORMED "H" | 1 | 1 | 2015-09-04 | 42 | 2015-07-24 | EA | 0 | 0 | 1 | No | 2014-08-06 | 2017-10-27 | 0 | 0
8034 | 473 | 505 |  | 505-03-F0019 | 560111060936-003 | FLANGE,NAVY,3/4"IPS,CLASS 15 | 4 | 2 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 2 | No | 2013-11-15 | 2017-10-27 | 24.75 | 49.5
8034 | 473 | 505 |  | 505-03-F9024 | 561114150110-001 | 3/4" FLG, NAVY, SW, CNA 90/1 | 6 | 2 | 2014-01-27 | 30 | 2013-12-28 | EA | 1 | 0 | 1 | No | 2013-11-18 | 2017-10-27 | 100.73 | 100.73
8034 | 473 | 505 |  | 505-03-F9042 | 560314101527-00A | FLANGE, 4" BUTTERFLY, SW | 43 | 4 | 2014-01-20 | 30 | 2013-12-21 | EA | 4 | 0 | 1 | No | 2013-11-18 | 2017-10-27 | 260 | 260
8034 | 473 | 505 |  | 505-03-F9043 | 561114000000-008 | FLANGE, 5", 90-10 CUNI, SW, | 49 | 0 | 2014-01-20 | 75 | 2013-11-06 | EA | 0 | 1 | 1 | No | 2013-11-18 | 2017-10-27 | 317 | 317
8034 | 473 | 505 |  | 505-03-F9054 | 560805210202-00C | FLANGE, 6" IPS, CLASS 150, W | 33 | 1 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 1 | No | 2013-11-18 | 2017-10-27 | 81.81 | 81.81
8034 | 473 | 505 |  | 505-03-F9252 | 560105150109-001 | FLANGE, 3", WN, 304L SST, NA | 42 | 12 | 2014-01-20 | 42 | 2013-12-09 | EA | 4 | 0 | 8 | No | 2013-11-19 | 2017-10-27 | 172.05 | 1376.4
8034 | 473 | 505 |  | 505-03-F9392 | 564300000000-006 | FLANGE, 1-1/2" IPS, SST 316L | 2 | 2 | 2014-02-28 | 49 | 2014-01-10 | EA | 0 | 0 | 2 | No | 2017-01-23 | 2017-10-27 | 510 | 1020 | 475 | 2017-01-31
8034 | 473 | 505 |  | 505-03-K0063 | 810600-000000001 | KIT, FLANGE ISOLATION, 3/4" | 19 | 1 | 2014-03-07 | 15 | 2014-02-20 | EA | 0 | 1 | 2 | No | 2013-11-19 | 2017-10-27 | 12.05 | 24.1
8034 | 473 | 505 |  | 505-03-K9158 | 810649-000000001 | FLANGE ISOLATION KIT, 2" X 1 | 1 | 1 | 2014-06-24 | 45 | 2014-05-10 | EA | 0 | 0 | 1 | No | 2017-08-11 | 2017-10-27 | 0 | 0
8034 | 473 | 528 |  | 528-03-M9023 | 55D910G60002-007 | DECK DRAIN, 2"IPS, 70-30 CU- | 3 | 1 | 2014-05-28 | 60 | 2014-03-29 | EA | 0 | 0 | 1 | No | 2013-10-17 | 2017-10-27 | 750 | 750
8034 | 473 | 542 |  | 542-01-M0002 | 581704-000000001 | NOZZLE, DFM FUELING AUTO-SHU | 2 | 2 | 2014-10-16 | 180 | 2014-04-19 | EA | 0 | 0 | 2 | No | 2013-10-18 | 2017-10-27 | 256.25 | 512.5 | 471 | 2015-02-23
8034 | 473 | 167 |  | 167-01-00401-800 | 610602040000-002 | PIN, QUICK RELEASE, SSTL | 15 | 15 | 2014-01-20 | 112 | 2013-09-30 | EA | 0 | 0 | 15 | No | 2017-04-04 | 2017-10-27 | 0 | 0
8034 | 473 | 167 |  | 167-01-00401-801 | 610602040000-003 | RETAINING PIN EARS, 0.375", | 30 | 30 | 2014-01-20 | 112 | 2013-09-30 | EA | 0 | 0 | 30 | No | 2017-04-04 | 2017-10-27 | 0 | 0
8034 | 473 | 167 |  | 167-01-00401-802 | 610602040000-004 | LANYARD | 15 | 15 | 2014-01-20 | 112 | 2013-09-30 | EA | 0 | 0 | 15 | No | 2017-04-04 | 2017-10-27 | 0 | 0
8034 | 473 | 259 |  | 259-01-00013-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-04 | 60 | 2014-04-05 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-06-28
8034 | 473 | 259 |  | 259-05-00027-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 485 | 2017-08-31
8034 | 473 | 259 |  | 259-05-00027-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 481 | 2015-12-02
8034 | 473 | 259 |  | 259-05-00037-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 485 | 2017-08-31
8034 | 473 | 259 |  | 259-05-00037-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 481 | 2015-12-02
8034 | 473 | 259 |  | 259-05-00038-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-03-14 | 60 | 2014-01-13 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 450 | 2009-06-25
8034 | 473 | 259 |  | 259-05-00038-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-14 | 60 | 2014-01-13 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 483 | 2016-07-08
8034 | 473 | 259 |  | 259-05-00038-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-03-14 | 60 | 2014-01-13 | LO | 0 | 0 | 1 | No | 2014-05-19 | 2017-10-27 | 0 | 0 | 481 | 2015-12-02
8034 | 473 | 259 |  | 259-05-22002-S00 | -S00 | FLANGE, WELD NECK, RAISED, 8 | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 520 | 1040
8034 | 473 | 259 |  | 259-05-22002-S01 | -S00 | FLANGE, WELD NECK, RAISED, 8 | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 520 | 1040
8034 | 473 | 259 |  | 259-05-22999-S00 | -S00 | SRVC, DRILL EXPANSION JOINTS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-08-17 | 2017-10-27 | 0 | 0
8034 | 473 | 259 |  | 259-05-22999-S01 | -S00 | SRVC, DRILL EXPANSION JOINTS | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-08-17 | 2017-10-27 | 0 | 0
8034 | 473 | 259 |  | 259-07-00008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2013-09-05 | 2017-10-27 | 0 | 0 | 483 | 2016-07-08
8034 | 473 | 259 |  | 259-07-00008-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | LO | 0 | 0 | 1 | No | 2013-09-05 | 2017-10-27 | 0 | 0 | 477 | 2015-09-21
8034 | 473 | 259 |  | 259-07-00008-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | LO | 0 | 0 | 1 | No | 2013-09-05 | 2017-10-27 | 0 | 0 | 477 | 2015-09-21
8034 | 473 | 259 |  | 259-07-00009-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2013-09-06 | 2017-10-27 | 0 | 0 | 479 | 2016-05-17
8034 | 473 | 259 |  | 259-07-00009-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2013-09-06 | 2017-10-27 | 0 | 0 | 477 | 2015-09-21
8034 | 473 | 259 |  | 259-07-00014-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2013-09-06 | 2017-10-27 | 0 | 0 | 483 | 2016-07-08
8034 | 473 | 259 |  | 259-07-00014-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2013-09-06 | 2017-10-27 | 0 | 0 | 477 | 2015-09-21
8034 | 473 | 262 |  | 262-01-M0034-S00 | -S00 | EXPANSION JOINT, 5", SINGLE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-09-21 | 2017-10-27 | 0 | 0
8034 | 473 | 262 |  | 262-01-M0035-S00 | -S00 | EXPANSION JOINT, 8", QUAD AR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-09-21 | 2017-10-27 | 0 | 0
8034 | 473 | 505 |  | 505-03-F0065-S00 | -S00 | FLANGE,2-1/2"IPS,CLASS 150,S | 6 | 6 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 6 | No | 2017-07-25 | 2017-10-27 | 38.19 | 229.14
8034 | 473 | 505 |  | 505-03-F9032-S00 | -S00 | FLANGE, 5", NAVY, SW, 90/10 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8034 | 473 | 505 |  | 505-03-F9043-S00 | -S00 | FLANGE, 5", 90-10 CUNI, SW, | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-07-24 | 2017-10-27 | 0 | 0
8034 | 473 | 505 |  | 505-03-F9124-S00 | -S00 | FLANGE, 1-1/4", SW, SST TYPE | 2 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2017-07-25 | 2017-10-27 | 150 | 300
8034 | 473 | 505 |  | 505-03-F9132-S00 | -S00 | FLANGE, 3", SWLDG | 6 | 6 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 6 | No | 2017-07-25 | 2017-10-27 | 39.36 | 236.16
8034 | 473 | 512 |  | 512-01-SH001-S00 | -S00 | COST, SHOCK CF 2262, HEATER | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-02-27 | 2017-10-27 | 0 | 0
8034 | 473 | 514 |  | 514-01-00001-S00 | -S00 | MODIFY AC PLANT IAW CF 2177 | 2 | 2 | 2017-02-24 | 123 | 2016-10-24 | EA | 0 | 1 | 1 | No | 2017-02-24 | 2017-02-24 | 0 | 0
8034 | 473 | 555 |  | 555-02-E0005-801 | 502043-000000011 | AFFF NOZZLE, ASM TYPE I | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | EA | 0 | 0 | 1 | No | 2017-05-30 | 2017-10-27 | 0 | 0
8034 | 473 | 555 |  | 555-02-E0005-802 | 502043-000000012 | NOZZLE CLAMP, QUICK RELEASE | 1 | 1 | 2014-10-16 | 30 | 2014-09-16 | EA | 0 | 0 | 1 | No | 2017-05-30 | 2017-10-27 | 0 | 0
8034 | 473 | 555 |  | 555-02-E0005-803 | 502043-000000004 | HOSE ASSEMBLY, 1-1/2" X 150' | 1 | 1 | 2014-10-16 | 130 | 2014-06-08 | EA | 0 | 0 | 1 | No | 2017-05-30 | 2017-10-27 | 0 | 0
8037 | 473 | 167 |  | 167-03-00051 | 712204320000-001 | SCREW FLAT SOCKET HD 1/2"-13 | 20 | 10 | 2014-08-04 | 10 | 2014-07-25 | EA | 0 | 0 | 10 | No | 2014-01-24 | 2017-10-27 | 0.79 | 7.9
8037 | 473 | 180 |  | 180-81-00001 | 713035022116-002 | BOLT, HEX, SLF-LKG 3/8-16UNC | 4 | 4 | 2015-01-12 | 42 | 2014-12-01 | EA | 0 | 0 | 4 | No | 2015-07-21 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00545 | 715402663336-002 | NUT, HVY HEX JAM, 1-8UNC-2B | 6 | 3 | 2014-07-01 | 56 | 2014-05-06 | EA | 0 | 0 | 3 | No | 2011-03-03 | 2017-10-27 | 98 | 294
8037 | 473 | 259 |  | 259-05-00546 | 710302030012-001 | NUT, HVY HEX, SELF LKG | 2 | 1 | 2014-07-01 | 56 | 2014-05-06 | EA | 0 | 0 | 1 | No | 2011-03-03 | 2017-10-27 | 8.29 | 8.29
8037 | 473 | 259 |  | 259-05-428RW | SRV527-030500012 | REWORK 428 PARTS-WASHERS | 139 | 10 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 10 | No | 2015-04-29 | 2017-10-27 | 2.25 | 22.5
8037 | 473 | 505 |  | 505-03-00200 | 240914000000-001 | GREASE, GENERAL PURPOSE, MOB | 1 | 1 | 2014-01-20 | 84 | 2013-10-28 | EA | 0 | 0 | 1 | No | 2014-06-09 | 2017-10-27 | 107.07 | 107.07 | 469 | 2016-03-01
8037 | 473 | 505 |  | 505-03-N9173 | 712630004600-001 | ROD, THREADED, 1/2"-13 X 2 | 4 | 0 | 2014-03-21 | 14 | 2014-03-07 | EA | 0 | 4 | 4 | No | 2017-10-13 | 2017-10-27 | 0 | 0
8037 | 473 | 507 |  | 507-10-LPS3U | 790300000000-S3U | LABELS WITHIN GRAND MODULE S | 1 | 1 | 2014-12-22 | 0 | 2014-12-22 | LO | 0 | 0 | 1 | No | 2016-12-15 | 2017-10-27 | 43.61 | 43.61 | 477 | 2017-03-27
8037 | 473 | 571 |  | 571-01-00133 | 710830000000-005 | WASHER, FLAT, 3/4", SSTL 316 | 1 | 1 | 2014-12-16 | 14 | 2014-12-02 | PG | 0 | 0 | 1 | No | 2017-09-22 | 2017-10-27 | 0 | 0
8037 | 473 | 602 |  | 602-01-00001 | 741613-000000002 | CARD HOLDER, TYPE "A" CARD H | 245 | 221 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 221 | No | 2016-04-06 | 2017-10-27 | 81.9 | 18099.9
8037 | 473 | 602 |  | 602-01-00004 | 741613-000000001 | CARD HOLDER, TYPE "D", CARD | 85 | 68 | 2014-01-20 | 123 | 2013-09-19 | EA | 17 | 0 | 51 | No | 2016-04-06 | 2017-10-27 | 12.63 | 644.13
8037 | 473 | 602 |  | 602-01-00006 | 741612-000000002 | PLASTIC PROTECTOR FOR TYPE " | 85 | 68 | 2014-01-20 | 123 | 2013-09-19 | EA | 17 | 0 | 51 | No | 2016-04-06 | 2017-10-27 | 2.63 | 134.13
8037 | 473 | 612 |  | 612-02-00026 | 717330780062-554 | SPRING PIN, 3/16" | 64 | 0 | 2014-12-09 | 14 | 2014-11-25 | EA | 0 | 64 | 64 | No | 2014-04-30 | 2017-10-27 | 0 | 0
8037 | 473 | 630 |  | 630-02-00012 | 630100000027-001 | PAINT, PRIMER | 1 | 1 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 1 | No | 2016-08-17 | 2017-10-27 | 0 | 0
8037 | 473 | 630 |  | 630-02-00013 | 630115070004-001 | PAINT, EPOXY POLYAMIDE, PRIM | 1 | 1 | 2014-01-20 | 35 | 2013-12-16 | KT | 0 | 0 | 1 | No | 2016-08-17 | 2017-10-27 | 62.53 | 62.53 | 471 | 2016-09-09
8037 | 473 | 631 |  | 631-01-000L5 | 630600252700-001 | MS-200 LOW V.O.C. ACRYLIC | 60 | 60 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 60 | Yes | 2014-05-20 | 2017-10-27 | 80.87 | 4852.2 | 477 | 2017-08-07
8037 | 473 | 631 |  | 631-01-000L6 | 630600252700-002 | MS-200 LOW V.O.C. ACRYLIC EP | 15 | 15 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 15 | Yes | 2014-05-20 | 2017-10-27 | 80.87 | 1213.05 | 477 | 2017-08-07
8037 | 473 | 631 |  | 631-01-000L7 | 630600252700-003 | MS-200 LOW V.O.C. ACRYLIC EP | 15 | 15 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 15 | Yes | 2014-05-20 | 2017-10-27 | 80.87 | 1213.05 | 477 | 2017-08-07
8037 | 473 | 631 |  | 631-01-000L8 | 630100250608-001 | PRIMER,NON-SKID,MIL-PRF-2466 | 200 | 100 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 100 | Yes | 2014-05-20 | 2017-10-27 | 51.78 | 5178
8037 | 473 | 631 |  | 631-01-000L9 | 630100250608-002 | PRIMER,NON-SKID,MIL-PRF-2466 | 300 | 300 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 300 | Yes | 2014-05-20 | 2017-10-27 | 49.79 | 14937 | 467 | 2014-05-12
8037 | 473 | 631 |  | 631-01-00L10 | 630100250608-003 | PRIMER,NON-SKID,MIL-PRF-2466 | 52 | 52 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 52 | Yes | 2014-05-20 | 2017-10-27 | 51.78 | 2692.56 | 477 | 2017-08-07
8037 | 473 | 631 |  | 631-01-00L11 | 630215260308-001 | PAINT SPRAY NON-SKID MIL-PRF | 350 | 225 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 225 | Yes | 2014-05-20 | 2017-10-27 | 71.76 | 16146
8037 | 473 | 631 |  | 631-01-00L12 | 630215260308-002 | PAINT SPRAY NON-SKID MIL-PRF | 180 | 180 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 180 | Yes | 2014-05-20 | 2017-10-27 | 45.91 | 8263.8 | 477 | 2017-08-07
8037 | 473 | 631 |  | 631-01-00L18 | 630600480300-001 | PAINT,SHERWIN-WILLIAMS POLYS | 20 | 20 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 20 | Yes | 2014-05-20 | 2017-10-27 | 139.71 | 2794.2 | 475 | 2015-05-27
8037 | 473 | 631 |  | 631-01-00L19 | 630600480300-002 | PAINT,SHERWIN-WILLIAMS POLYS | 12 | 12 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 12 | Yes | 2014-05-20 | 2017-10-27 | 139.71 | 1676.52 | 477 | 2017-06-29
8037 | 473 | 631 |  | 631-01-00L20 | 630600480300-003 | PAINT,SHERWIN-WILLIAMS POLYS | 20 | 20 | 2014-01-20 | 60 | 2013-11-21 | GL | 0 | 0 | 20 | Yes | 2014-05-20 | 2017-10-27 | 139.71 | 2794.2 | 477 | 2017-06-29
8037 | 473 | 631 |  | 631-01-00L24 | 630200032911-003 | PAINT, DOD-E-24607 CHLORINAT | 18 | 3 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 3 | Yes | 2014-05-20 | 2017-10-27 | 45.49 | 136.47
8037 | 473 | 631 |  | 631-01-00L26 | 630600200000-001 | ANTI CONDENSATION TEMPCOAT 1 | 70 | 50 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 50 | Yes | 2014-05-20 | 2017-10-27 | 52.99 | 2649.5
8037 | 473 | 631 |  | 631-01-00L28 | 630600121900-001 | FAST CLAD ER EPOXY,BRUSH GRA | 959 | 951 | 2014-01-20 | 35 | 2013-12-16 | KT | 0 | 0 | 951 | Yes | 2014-05-20 | 2017-10-27 | 77.41 | 73616.91
8037 | 473 | 631 |  | 631-01-00L29 | 630600121900-002 | FAST CLAD ER EPOXY,BRUSH GRA | 31 | 24 | 2014-01-20 | 35 | 2013-12-16 | KT | 0 | 0 | 24 | Yes | 2014-05-20 | 2017-10-27 | 77.41 | 1857.84
8037 | 473 | 631 |  | 631-01-00L32 | 630200121926-006 | PAINT, HIGH SOLID EDGE RETEN | 108 | 79 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 79 | Yes | 2014-05-20 | 2017-10-27 | 57.58 | 4548.82
8037 | 473 | 631 |  | 631-01-00L33 | 630200121926-001 | PAINT HIGH SOLID EDGE RETENT | 922 | 897 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 897 | Yes | 2014-05-20 | 2017-10-27 | 72.28 | 64835.16
8037 | 473 | 631 |  | 631-01-00L34 | 630200121926-007 | PAINT, HIGH SOLID EDGE RETEN | 193 | 133 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 133 | Yes | 2014-05-20 | 2017-10-27 | 72.28 | 9613.24
8037 | 473 | 631 |  | 631-01-00L35 | 630200121926-002 | PAINT HIGH SOLID EDGE RETENT | 90 | 60 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 60 | Yes | 2014-05-20 | 2017-10-27 | 72.28 | 4336.8
8037 | 473 | 631 |  | 631-01-00L35 | 630200121926-002 | PAINT HIGH SOLID EDGE RETENT | 90 | 60 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 60 | Yes | 2014-05-20 | 2017-10-27 | 72.28 | 4336.8
8037 | 473 | 631 |  | 631-01-00L37 | 630200430004-002 | FORMULA 111 EPOXY | 15 | 15 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 15 | Yes | 2014-05-20 | 2017-10-27 | 39.34 | 590.1 | 477 | 2016-06-30
8037 | 473 | 631 |  | 631-01-00L39 | 630600121900-004 | PAINT, MIL-PRF-23236 TYPE VI | 100 | 100 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 100 | Yes | 2014-05-20 | 2017-10-27 | 0 | 0
8037 | 473 | 631 |  | 631-01-00L40 | 630600453130-001 | PAINT, TT-P-28H ALUM HEAT RE | 40 | 40 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 40 | Yes | 2014-05-20 | 2017-10-27 | 102.82 | 4112.8 | 477 | 2016-06-30
8037 | 473 | 631 |  | 631-01-00L41 | 630200032428-016 | PAINT, MIL-PRF-24635, TYPE I | 5 | 5 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 5 | Yes | 2014-05-20 | 2017-10-27 | 64.59 | 322.95 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L42 | 630200032428-017 | PAINT, MIL-PRF-24635, TYPE I | 5 | 5 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 5 | Yes | 2014-05-20 | 2017-10-27 | 64.59 | 322.95 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L43 | 630100000000-001 | PC WELD PRECONSTRUCTION PRIM | 260 | 260 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 260 | Yes | 2014-05-20 | 2017-10-27 | 0 | 0
8037 | 473 | 631 |  | 631-01-00L44 | 630100000000-002 | PC WELD PRECONSTRUCTION PRIM | 300 | 300 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 300 | No | 2014-08-15 | 2017-10-27 | 49.479 | 14843.7 | 403 | 2006-07-12
8037 | 473 | 631 |  | 631-01-00L47 | 630200032428-001 | PAINT, MIL-PRF-24635 TYPE II | 9 | 5 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 5 | Yes | 2014-05-20 | 2017-10-27 | 57.95 | 289.75
8037 | 473 | 631 |  | 631-01-00L48 | 630200032428-002 | PAINT, MIL-PRF-24635 TYPE II | 9 | 4 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 4 | Yes | 2014-05-20 | 2017-10-27 | 72.52 | 290.08
8037 | 473 | 631 |  | 631-01-00L49 | 630200032428-022 | PAINT,MIL-DTL-PRF-24635 TYPE | 9 | 7 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 7 | Yes | 2014-05-20 | 2017-10-27 | 47.47 | 332.29
8037 | 473 | 631 |  | 631-01-00L50 | 630200032428-003 | PAINT, MIL-PRF-24635 TYPE II | 9 | 8 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 8 | Yes | 2014-05-20 | 2017-10-27 | 50.2 | 401.6
8037 | 473 | 631 |  | 631-01-00L51 | 630200032428-004 | PAINT, MIL-PRF-24635 TYPE II | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 50.2 | 451.8 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L52 | 630200032428-005 | PAINT, MIL-PRF-24635 TYPE II | 9 | 8 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 8 | Yes | 2014-05-20 | 2017-10-27 | 64.59 | 516.72
8037 | 473 | 631 |  | 631-01-00L53 | 630200032428-006 | PAINT, MIL-PRF-24635 TYPE II | 9 | 8 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 8 | Yes | 2014-05-20 | 2017-10-27 | 64.59 | 516.72
8037 | 473 | 631 |  | 631-01-00L54 | 630200032428-020 | PAINT, PRF-24635 TYPE II CLA | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 64.59 | 581.31 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L55 | 630200032428-007 | PAINT, MIL-PRF-24635 TYPE II | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 60.3 | 542.7 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L56 | 630200032428-008 | PAINT, MIL-PRF-24635 TYPE II | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 64.59 | 581.31 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L57 | 630200032428-009 | PAINT, MIL-PRF-24635 TYPE II | 9 | 8 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 8 | Yes | 2014-05-20 | 2017-10-27 | 118.11 | 944.88
8037 | 473 | 631 |  | 631-01-00L58 | 630200032428-010 | PAINT, MIL-PRF-24635 TYPE II | 9 | 8 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 8 | Yes | 2014-05-20 | 2017-10-27 | 50.2 | 401.6
8037 | 473 | 631 |  | 631-01-00L59 | 630200032428-011 | PAINT, MIL-PRF-24635 TYPE II | 9 | 8 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 8 | Yes | 2014-05-20 | 2017-10-27 | 50.2 | 401.6
8037 | 473 | 631 |  | 631-01-00L60 | 630200032428-012 | PAINT, MIL-PRF-24635 TYPE II | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 48.97 | 440.73 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L61 | 630200032428-013 | PAINT, MIL-PRF-24635 TYPE II | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 61.47 | 553.23 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L62 | 630200032428-014 | PAINT, MIL-PRF-24635 TYPE II | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 61.47 | 553.23 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L63 | 630200032428-015 | PAINT, MIL-PRF-24635 TYPE II | 9 | 9 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 9 | Yes | 2014-05-20 | 2017-10-27 | 61.47 | 553.23 | 479 | 2017-10-24
8037 | 473 | 631 |  | 631-01-00L71 | 631800-000000001 | PRESERVATIVE, FLO-COAT OR EQ | 220 | 220 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 220 | Yes | 2014-05-20 | 2017-10-27 | 16.3454 | 3595.988 | 471 | 2014-10-03
8037 | 473 | 631 |  | 631-01-00L72 | 160200060000-001 | PRESERVATIVE, LUBE OIL TANK | 300 | 247 | 2014-01-20 | 35 | 2013-12-16 | GL | 55 | 0 | 192 | Yes | 2014-05-20 | 2017-10-27 | 18.44 | 3540.48
8037 | 473 | 631 |  | 631-01-00L73 | 630100440327-001 | PAINT, FORMULA 84, TT-P-645 | 200 | 200 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 200 | Yes | 2014-05-20 | 2017-10-27 | 46.35 | 9270 | 450 | 2010-08-10
8037 | 473 | 631 |  | 631-01-00L74 | 671200-000000003 | MARKING AND WARNING TAPE, TA | 10 | 10 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 10 | Yes | 2014-05-20 | 2017-10-27 | 43.35 | 433.5 | 450 | 2011-08-18
8037 | 473 | 631 |  | 631-01-00L75 | 630200430004-005 | FASTCLAD BRUSH GRADE EPOXY. | 500 | 500 | 2014-01-20 | 35 | 2013-12-16 | KT | 0 | 0 | 500 | Yes | 2014-05-20 | 2017-10-27 | 74.44 | 37220 | 469 | 2014-09-12
8037 | 473 | 631 |  | 631-01-00L77 | 630300000000-001 | RX-2390, MINTEQ | 1 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | Yes | 2014-05-20 | 2017-10-27 | 2026.8 | 2026.8 | 477 | 2017-09-06
8037 | 473 | 631 |  | 631-01-00L91 | 630200032428-018 | PAINT, MIL-PRF-24635, TYPE I | 10 | 10 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 10 | No | 2016-02-25 | 2017-10-27 | 50.2 | 502 | 475 | 2015-05-27
8037 | 473 | 631 |  | 631-01-00L94 | 630200430004-006 | ACRYLIC EPOXY, MIL-PRF-24667 | 50 | 50 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 50 | Yes | 2014-03-12 | 2017-10-27 | 80.87 | 4043.5 | 477 | 2017-08-07
8037 | 473 | 631 |  | 631-01-0L113 | 630300000000-007 | PAINT, LATEX, MIL-PRF-24596 | 10 | 10 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 10 | No | 2015-06-12 | 2017-10-27 | 52.99 | 529.9 | 475 | 2015-05-29
8037 | 473 | 631 |  | 631-01-0L114 | 630300000000-008 | PAINT, LATEX, MIL-PRF-24596 | 10 | 10 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 10 | No | 2015-06-12 | 2017-10-27 | 52.99 | 529.9 | 475 | 2015-05-29
8037 | 473 | 631 |  | 631-01-0L116 | 630300000000-010 | PAINT, MIL-PRF-32171B, TYPE | 40 | 28 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 28 | No | 2014-12-17 | 2017-10-27 | 88.88 | 2488.64
8037 | 473 | 631 |  | 631-01-0L121 | 630300000000-011 | POLYSILOXANE XLE, RED #11105 | 1 | 1 | 2014-01-20 | 35 | 2013-12-16 | EA | 0 | 0 | 1 | No | 2014-12-17 | 2017-10-27 | 139.71 | 139.71 | 477 | 2017-06-29
8037 | 473 | 631 |  | 631-01-0L122 | 630300000000-012 | POLYSILOXANE XLE, WHITE #179 | 1 | 1 | 2014-01-20 | 35 | 2013-12-16 | EA | 0 | 0 | 1 | No | 2014-12-17 | 2017-10-27 | 139.71 | 139.71 | 477 | 2017-06-29
8037 | 473 | 631 |  | 631-01-0L123 | 630300000000-013 | POLYSILOXANE XLE, BLUE #1518 | 1 | 1 | 2014-01-20 | 35 | 2013-12-16 | EA | 0 | 0 | 1 | No | 2014-12-17 | 2017-10-27 | 139.71 | 139.71 | 477 | 2017-06-29
8037 | 473 | 631 |  | 631-01-0L124 | 630300000000-014 | POLYSILOXANE XLE,YELLOW #135 | 1 | 1 | 2014-01-20 | 35 | 2013-12-16 | EA | 0 | 0 | 1 | No | 2014-12-17 | 2017-10-27 | 139.71 | 139.71 | 477 | 2017-06-29
8037 | 473 | 631 |  | 631-01-0L26A | 630600200000-004 | PAINT, ANTICONDENSATION COAT | 40 | 35 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 35 | No | 2014-05-27 | 2017-10-27 | 54.15 | 1895.25
8037 | 473 | 631 |  | 631-01-0L26B | 630600200000-002 | ANTI-CONDENSATION COATING | 40 | 35 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 35 | Yes | 2014-05-20 | 2017-10-27 | 54.15 | 1895.25
8037 | 473 | 631 |  | 631-01-0L26C | 630600200000-003 | ANTI-CONDENSATION COATING | 40 | 30 | 2014-01-20 | 35 | 2013-12-16 | GL | 0 | 0 | 30 | Yes | 2014-05-20 | 2017-10-27 | 54.15 | 1624.5
8037 | 473 | 631 |  | 631-01-0L30C | 630300000000-026 | PAINT, HIGH SOLIDS EDGE RETE | 500 | 500 | 2014-01-20 | 35 | 2013-12-16 | EA | 0 | 0 | 500 | No | 2014-12-17 | 2017-10-27 | 0 | 0
8037 | 473 | 631 |  | 631-01-L1001 | 630324000000-001 | GARNET BLAST ABRASIVE | 80 | 80 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 80 | No | 2014-05-20 | 2017-10-27 | 0 | 0 | 481 | 2017-09-05
8037 | 473 | 671 |  | 671-01-00069 | 760000-000000005 | DISPENSER, EARPLUGS, PLASTIC | 22 | 22 | 2014-01-20 | 21 | 2013-12-30 | EA | 0 | 0 | 22 | No | 2017-09-27 | 2017-10-27 | 0 | 0
8037 | 473 | 992 |  | 992-01-00308 | 712603-000000002 | ROD, 1-8UNC X 32", ALLOY STE | 8 | 8 | 2014-01-20 | 14 | 2014-01-06 | FT | 0 | 0 | 8 | No | 2015-01-19 | 2017-10-27 | 7.48 | 59.84
8037 | 473 | 167 |  | 167-03-00061-S00 | -S00 | PIN, QUICK RELEASE, 5/8", ST | 4 | 4 | 2015-07-03 | 123 | 2015-03-02 | EA | 0 | 0 | 4 | No | 2017-04-19 | 2017-10-27 | 4.22 | 16.88
8037 | 473 | 180 |  | 180-93-00056-S00 | -S00 | BOLT, HEX-HD, 3/8-16UNC-2AX2 | 24 | 24 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 24 | No | 2017-06-05 | 2017-10-27 | 6.27 | 150.48
8037 | 473 | 180 |  | 180-93-00057-S00 | -S00 | NUT, SLFLKG, 3/8-16UNJC-3B, | 24 | 24 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 24 | No | 2017-06-05 | 2017-10-27 | 0.76 | 18.24
8037 | 473 | 180 |  | 180-93-00058-S00 | -S00 | WASHER, 3/8", FLAT, STL GR 8 | 24 | 24 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 24 | No | 2017-06-05 | 2017-10-27 | 0.47 | 11.28
8037 | 473 | 180 |  | 180-97-00100-S00 | -S00 | LOCTITE BLUE 242, 0.34 OZ | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-06-08 | 2017-10-27 | 15.18 | 15.18
8037 | 473 | 180 |  | 180-97-00101-S00 | -S00 | WASHER, FLAT, M6, CRES 316 | 16 | 16 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 16 | No | 2017-06-08 | 2017-10-27 | 0.01 | 0.16
8037 | 473 | 180 |  | 180-97-00104-S00 | -S00 | BOLT, HEX HD, M6 X 1 X 20 | 16 | 16 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 16 | No | 2017-06-08 | 2017-10-27 | 0.06 | 0.96
8037 | 473 | 180 |  | 180-97-00104-S00 | -S00 | BOLT, HEX HD, M6 X 1 X 20 | 16 | 16 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 16 | No | 2017-06-08 | 2017-10-27 | 0.06 | 0.96
8037 | 473 | 259 |  | 259-05-00077-S00 | -S00 | HEX HEAD CAP SCREW, 8MM X 1. | 8 | 8 | 2014-04-24 | 123 | 2013-12-22 | EA | 0 | 0 | 8 | No | 2017-06-14 | 2017-10-27 | 15.95 | 127.6 | 469 | 2017-09-14
8037 | 473 | 259 |  | 259-05-00077-S01 | -S00 | HEX HEAD CAP SCREW, 8MM X 1. | 8 | 8 | 2014-04-24 | 123 | 2013-12-22 | EA | 0 | 0 | 8 | No | 2017-06-12 | 2017-10-27 | 15.95 | 127.6
8037 | 473 | 259 |  | 259-05-00417-S00 | -S00 | HEX HEAD CAP SCREW, 3-1/4" L | 8 | 8 | 2014-04-24 | 123 | 2013-12-22 | EA | 0 | 0 | 8 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00417-S01 | -S00 | HEX HEAD CAP SCREW, 3-1/4" L | 8 | 8 | 2014-04-24 | 123 | 2013-12-22 | EA | 0 | 0 | 8 | No | 2017-06-12 | 2017-10-27 | 29.87 | 238.96
8037 | 473 | 259 |  | 259-05-00420-S00 | -S00 | HEX HD CAP SCREW, 3/4-10UNC- | 16 | 16 | 2014-04-24 | 123 | 2013-12-22 | EA | 0 | 0 | 16 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00420-S01 | -S00 | HEX HD CAP SCREW, 3/4-10UNC- | 16 | 16 | 2014-04-24 | 123 | 2013-12-22 | EA | 0 | 0 | 16 | No | 2017-06-12 | 2017-10-27 | 11.95 | 191.2
8037 | 473 | 259 |  | 259-05-00523-S00 | -S00 | ATTACHMENT, ROD, 1" ROD SIZE | 1 | 1 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 1 | No | 2017-07-25 | 2017-10-27 | 95 | 95
8037 | 473 | 259 |  | 259-05-00526-S00 | -S00 | NUT, HVY HEX, 1-1/8-7UNC-2B | 5 | 5 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 5 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00527-S00 | -S00 | NUT,HVY HEX JAM, 1-1/8-7UNC- | 5 | 5 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 5 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00528-S00 | -S00 | HEX HD CAP SCREW,1-1/8-7UNC- | 2 | 2 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 97 | 194
8037 | 473 | 259 |  | 259-05-00529-S00 | -S00 | NUT, HVY HEX, 1-1/8-7UNC-2B | 2 | 2 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 29.21 | 58.42
8037 | 473 | 259 |  | 259-05-00541-S00 | -S00 | NUT, HVY HEX JAM, 1-8UNC-2B | 2 | 2 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00544-S00 | -S00 | CAPSCREW, 3/4-10 UNC-2A x 2" | 2 | 2 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 2.76 | 5.52
8037 | 473 | 259 |  | 259-05-00545-S00 | -S00 | NUT, HVY HEX JAM, 1-8UNC-2B | 3 | 3 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 3 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00546-S00 | -S00 | NUT, HVY HEX, SELF LKG | 1 | 1 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00552-S00 | -S00 | HEX HD CAP SCREW, 1-8UNC-2A | 2 | 2 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00553-S00 | -S00 | HEX HD CAP SCREW,1-1/8-7UNC- | 2 | 2 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00554-S00 | -S00 | WASHER, 2-3/4" OD X 1-3/16"I | 4 | 4 | 2014-07-01 | 123 | 2014-02-28 | EA | 0 | 0 | 4 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00573-S00 | -S00 | HEX HD CAP SCREW, 1-1/8-7UNC | 2 | 2 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-00574-S00 | -S00 | HEX HD CAP SCREW, 1-1/8-7UNC | 1 | 1 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-0550A-S00 | -S00 | EYE ROD, WELDED, 1", STEEL | 4 | 4 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 4 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-0575T-S00 | -S00 | ROD, CONTINUOUS THREAD, 1", | 1 | 1 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-22010-S00 | -S00 | WASHER, INSULATING,2.25 X 0. | 24 | 24 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 24 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-22010-S01 | -S00 | WASHER, INSULATING,2.25 X 0. | 24 | 24 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 24 | No | 2017-06-21 | 2017-10-27 | 3.99 | 95.76
8037 | 473 | 259 |  | 259-05-22011-S00 | -S00 | WASHER, INSULATING,1.44 X 0. | 24 | 24 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 24 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-22011-S01 | -S00 | WASHER, INSULATING,1.44 X 0. | 24 | 24 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 24 | No | 2017-06-21 | 2017-10-27 | 3.19 | 76.56
8037 | 473 | 259 |  | 259-05-22012-S00 | -S00 | WASHER, FLAT, 316L CRES, 2.2 | 8 | 8 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 8 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-22012-S01 | -S00 | WASHER, FLAT, 316L CRES, 2.2 | 8 | 8 | 2014-02-03 | 123 | 2013-10-03 | EA | 0 | 0 | 8 | No | 2017-06-21 | 2017-10-27 | 14.95 | 119.6
8037 | 473 | 259 |  | 259-05-22014-S00 | -S00 | NUT, HEX, HEAVY, 7/8"-9UNC-2 | 8 | 8 | 2014-02-03 | 14 | 2014-01-20 | EA | 0 | 0 | 8 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-22014-S01 | -S00 | NUT, HEX, HEAVY, 7/8"-9UNC-2 | 8 | 8 | 2014-02-03 | 14 | 2014-01-20 | EA | 0 | 0 | 8 | No | 2017-06-21 | 2017-10-27 | 1.29 | 10.32
8037 | 473 | 259 |  | 259-05-22018-S00 | -S00 | NUT, HEX, HEAVY, 7/8"-9UNC-2 | 16 | 16 | 2014-02-03 | 14 | 2014-01-20 | EA | 0 | 0 | 16 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-22018-S01 | -S00 | NUT, HEX, HEAVY, 7/8"-9UNC-2 | 16 | 16 | 2014-02-03 | 14 | 2014-01-20 | EA | 0 | 0 | 16 | No | 2017-06-21 | 2017-10-27 | 1.29 | 20.64
8037 | 473 | 259 |  | 259-05-22019-S00 | -S00 | WASHER, 8MM, 321 CRES | 16 | 16 | 2014-02-03 | 14 | 2014-01-20 | EA | 0 | 0 | 16 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-05-22019-S01 | -S00 | WASHER, 8MM, 321 CRES | 16 | 16 | 2014-02-03 | 14 | 2014-01-20 | EA | 0 | 0 | 16 | No | 2017-06-21 | 2017-10-27 | 1 | 16
8037 | 473 | 259 |  | 259-07-00102-S00 | -S00 | NUT, HEX, HEAVY, 3/4"-11UNC- | 8 | 8 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 8 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8037 | 473 | 259 |  | 259-07-00102-S01 | -S00 | NUT, HEX, HEAVY, 3/4"-11UNC- | 8 | 8 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 8 | No | 2017-06-12 | 2017-10-27 | 0.65 | 5.2
8037 | 473 | 437 |  | 437-11-00001-S02 | -S00 | SCREW, 10-32 X 0.5, 316 SSTL | 8 | 8 | 2014-02-03 | 123 | 2013-10-03 | EA | 1 | 0 | 7 | No | 2017-06-02 | 2017-10-27 | 4.95 | 34.65
8037 | 473 | 437 |  | 437-11-00001-S03 | -S00 | LOCKNUT, 10-32, 316 SSTL | 8 | 8 | 2014-02-03 | 123 | 2013-10-03 | EA | 1 | 0 | 7 | No | 2017-06-02 | 2017-10-27 | 4.65 | 32.55
8037 | 473 | 437 |  | 437-11-00001-S04 | -S00 | WASHER, FLAT, #10, 316 SSTL | 8 | 8 | 2014-02-03 | 123 | 2013-10-03 | EA | 1 | 0 | 7 | No | 2017-06-02 | 2017-10-27 | 4.24 | 29.68
8037 | 473 | 437 |  | 437-11-00001-S05 | -S00 | SCREW, 8-32 X 0.75", 316 SST | 2 | 2 | 2014-02-03 | 123 | 2013-10-03 | EA | 1 | 0 | 1 | No | 2017-06-02 | 2017-10-27 | 7.61 | 7.61
8037 | 473 | 505 |  | 505-01-00108-S00 | -S00 | TAPE, DBL SIDE FOAM, 1" X 5 | 2 | 2 | 2014-03-07 | 123 | 2013-11-04 | EA | 0 | 0 | 2 | No | 2017-05-15 | 2017-10-27 | 28.56 | 57.12 | 467 | 2017-05-23
8037 | 473 | 613 |  | 613-01-00S14-800 | 712230040000-003 | SCREW, PAN HD, 8-32UNC, CRES | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2017-07-03 | 2017-10-27 | 0 | 0
8037 | 473 | 613 |  | 613-01-00S14-801 | 701004020000-001 | LANYARD, 3/64" WIRE ROPE, CR | 1 | 1 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 0 | 1 | No | 2017-07-03 | 2017-10-27 | 0 | 0
8037 | 473 | 613 |  | 613-01-00S14-802 | 711304270000-012 | PIN, QUICK RELEASE, 1", CRES | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2017-07-03 | 2017-10-27 | 0 | 0
8037 | 473 | 665 |  | 665-01-00007-801 | 761407-000000001 | SHIELD, DRILL PRESS, DELTA | 1 | 0 | 2014-02-24 | 180 | 2013-08-28 | EA | 0 | 1 | 1 | No | 2016-08-17 | 2017-10-27 | 38.4 | 38.4 | 469 | 2016-08-30
8037 | 473 | 671 |  | 671-01-00069-801 | 760000-000000006 | EARPLUGS, YELLOW FOAM, 200PA | 22 | 22 | 2014-01-20 | 21 | 2013-12-30 | BG | 0 | 0 | 22 | No | 2017-09-27 | 2017-10-27 | 0 | 0
8043 | 473 | 073 |  | 073-01-00002 | SRV533-011000001 | SRVC, AIRBORNE NOISE & VIBRA | 1 | 1 | 2014-01-20 | 100 | 2013-10-12 | LO | 0 | 0 | 1 | No | 2016-02-24 | 2017-10-27 | 1 | 1 | 471 | 2017-10-11
8043 | 473 | 167 |  | 167-01-00972 | 610600040000-001 | CLIPS, ALUMINUM, HATCH AND | 20 | 20 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 20 | No | 2015-06-12 | 2017-10-27 | 54 | 1080 | 469 | 2012-07-02
8043 | 473 | 167 |  | 167-01-00973 | 611200030000-001 | CLIP, STL, FOR MANHOLE WRENC | 30 | 30 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 30 | No | 2014-10-02 | 2017-10-27 | 12 | 360 | 475 | 2016-03-01
8043 | 473 | 247 |  | 247-01-MS003 | SRV524-030900014 | SERVICES, MACHINING, TRANSOM | 1 | 1 | 2014-11-26 | 123 | 2014-07-26 | LO | 0 | 0 | 1 | No | 2013-12-11 | 2017-10-27 | 0 | 0
8043 | 473 | 247 |  | 247-01-MS003 | SRV524-030900014 | SERVICES, MACHINING, TRANSOM | 1 | 1 | 2014-11-26 | 123 | 2014-07-26 | LO | 0 | 0 | 1 | No | 2013-12-11 | 2017-10-27 | 0 | 0
8043 | 473 | 247 |  | 247-01-MS005 | SRV524-030800011 | VENDOR SERVICE, THRUST BEARI | 1 | 1 | 2014-02-28 | 123 | 2013-10-28 | LO | 0 | 0 | 1 | No | 2016-10-03 | 2017-10-27 | 1 | 1 | 477 | 2017-04-06
8043 | 473 | 161 |  | 161-01-00001-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | LO | 0 | 0 | 1 | No | 2015-01-13 | 2017-10-27 | 0 | 0
8043 | 473 | 164 |  | 164-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-00-00372-S00 | -S00 | BHD COVER, ALUMINUM, 8" | 1 | 1 | 2014-05-21 | 123 | 2014-01-18 | EA | 0 | 0 | 1 | No | 2017-09-08 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00001-820 | 610305-000000022 | SCREW, CAP, HEX HD, 316 CRES | 2 | 1 | 2015-04-13 | 7 | 2015-04-06 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00001-838 | 610305-000000040 | JOINING PLATE, LOWER, FWD., | 1 | 1 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-839 | 610305-000000041 | JOINING PLATE, UPPER, FOR WB | 1 | 1 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-840 | 610305-000000042 | SCREW, FLAT HD., SOC. HD., F | 28 | 28 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 28 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-841 | 610305-000000043 | FILLER PLATE, LOWER, FOR WBM | 1 | 1 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-842 | 610305-000000044 | FILLER PLATE, UPPER, FOR WBM | 1 | 1 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-843 | 610305-000000045 | SCREW, CAP, SOC. HD., FOR WB | 4 | 4 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 4 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-844 | 610305-000000046 | JOINING PLATE, LOWER, AFT, F | 1 | 1 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-868 | 610305-000000070 | LIMIT SWITCH ASSY., OPEN, FO | 1 | 1 | 2015-04-13 | 365 | 2014-04-13 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00001-872 | 610305-000000074 | LOGIC BOX, FOR SLIDING WT DO | 2 | 1 | 2014-10-10 | 365 | 2013-10-10 | EA | 0 | 0 | 1 | No | 2013-05-06 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00001-873 | 610305-000000075 | SCREW, CAP, SOC. HD., 1.250- | 46 | 30 | 2014-12-22 | 360 | 2013-12-27 | EA | 0 | 0 | 30 | No | 2013-05-06 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00001-882 | 610305-000000083 | UPPER PANEL STOP, 1-1/4" THK | 4 | 4 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 4 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-883 | 610305-000000084 | UPPER PANEL STOP, 1-1/4" THK | 6 | 6 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 6 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-884 | 610305-000000085 | UPPER PANEL STOP, 7/16" THK | 6 | 6 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 6 | No | 2013-05-06 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-886 | 610305-000000088 | SUPPORT GUSSET, 3/8" THK | 2 | 2 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 2 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-887 | 610305-000000089 | SUPPORT GUSSET FLANGE, 3/8" | 2 | 2 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 2 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-893 | 610305-000000096 | PANEL GUSSET, 3/4" THK | 4 | 4 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 4 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-895 | 610305-000000098 | SMALL BOTTOM PANEL STOP | 2 | 2 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 2 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-896 | 610305-000000099 | SOCKET BOTTOM, 316 SSTL, 3/8 | 10 | 10 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 10 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-897 | 610305-000000100 | SOCKET RIGHTSIDE, 316 SSTL, | 10 | 10 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 10 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-898 | 610305-000000101 | SOCKET LEFTSIDE, 316 SSTL, | 10 | 10 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 10 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-899 | 610305-000000102 | SOCKET BAR, 316 SSTL, 3/4" D | 10 | 10 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 10 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00001-901 | 610305-000000104 | PANEL STIFFENER, GR DH36 STL | 4 | 4 | 2015-04-13 | 360 | 2014-04-18 | EA | 0 | 0 | 4 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 485 | 2017-09-08
8043 | 473 | 167 |  | 167-01-00001-905 | 610305-000000110 | SHEAVE, SPACER, FOR WBMZ/RC2 | 2 | 2 | 2015-04-13 | 56 | 2015-02-16 | EA | 0 | 0 | 2 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 465 | 2013-05-06
8043 | 473 | 167 |  | 167-01-00001-907 | 610305-000000112 | SOCKET HEAD CAP SCREW | 1 | 1 | 2015-04-13 | 123 | 2014-12-11 | EA | 0 | 0 | 1 | No | 2014-12-10 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-04-13 | 120 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 403 | 2005-04-26
8043 | 473 | 167 |  | 167-01-00001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-04-13 | 123 | 2014-12-11 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00002-807 | 610305-000000121 | WEDGE, MEDIUM, FOR RC1/RC2 | 4 | 4 | 2014-12-22 | 25 | 2014-11-27 | EA | 0 | 0 | 4 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 471 | 2012-07-25
8043 | 473 | 167 |  | 167-01-00002-824 | 610305-000000138 | SLIDE PLATE, NAVAL BRASS | 2 | 1 | 2014-12-22 | 21 | 2014-12-01 | EA | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00002-870 | 610305-000000184 | LIMIT SWITCH ASSY., OPEN, FO | 2 | 1 | 2014-12-22 | 365 | 2013-12-22 | EA | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00002-L08 | -L08 | DRAWINGS, PRELIMINARY | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 450 | 2009-06-18
8043 | 473 | 167 |  | 167-01-00002-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 450 | 2009-06-18
8043 | 473 | 167 |  | 167-01-00002-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 403 | 2005-04-26
8043 | 473 | 167 |  | 167-01-00002-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-12-22 | 123 | 2014-08-21 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 485 | 2017-09-08
8043 | 473 | 167 |  | 167-01-00003-L47 | -L47 | GOVERNMENT INSPECTION | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | LO | 0 | 0 | 1 | No | 2013-05-07 | 2017-10-27 | 0 | 0 | 485 | 2017-09-08
8043 | 473 | 167 |  | 167-01-00003-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-02-12 | 123 | 2014-10-12 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00005-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-11-19 | 123 | 2014-07-19 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 485 | 2017-09-06
8043 | 473 | 167 |  | 167-01-00006-R01 | SRV650-032200002 | REPAIR, JIB BOOM,GEARBOX&MOT | 1 | 1 | 2017-01-26 | 123 | 2016-09-25 | LO | 0 | 0 | 1 | No | 2017-01-26 | 2017-01-26 | 0 | 0
8043 | 473 | 167 |  | 167-01-00110-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 56 | 2014-06-09 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00120-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 483 | 2016-11-03
8043 | 473 | 167 |  | 167-01-00131-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00142-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-04 | 60 | 2015-01-03 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 483 | 2016-11-03
8043 | 473 | 167 |  | 167-01-00146-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-05-01 | 60 | 2015-03-02 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 469 | 2012-07-02
8043 | 473 | 167 |  | 167-01-00147-L08 | -L08 | DRAWINGS, PRELIMINARY | 1 | 1 | 2015-05-01 | 60 | 2015-03-02 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00147-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2015-05-01 | 60 | 2015-03-02 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00147-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2015-05-01 | 60 | 2015-03-02 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00147-L34 | -L34 | PROVISIONING TECH DOC. | 1 | 1 | 2015-05-01 | 60 | 2015-03-02 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00147-L48 | -L48 | TESTING, SHOCK, IAW APPENDIX | 1 | 1 | 2015-05-01 | 60 | 2015-03-02 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00147-L48 | -L48 | TESTING, SHOCK, IAW APPENDIX | 1 | 1 | 2015-05-01 | 60 | 2015-03-02 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00175-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 469 | 2012-07-02
8043 | 473 | 167 |  | 167-01-00197-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-17 | 60 | 2015-01-16 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-03
8043 | 473 | 167 |  | 167-01-00201-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00202-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00203-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00204-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00205-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 481 | 2016-06-07
8043 | 473 | 167 |  | 167-01-00207-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-10 | 60 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00208-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00211-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00214-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00215-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00216-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00218-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00219-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00224-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00226-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00231-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-10 | 60 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00232-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-10 | 60 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00236-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00237-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00243-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00244-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00271-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00284-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00286-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00287-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00288-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 0 | 0 | 483 | 2016-10-20
8043 | 473 | 167 |  | 167-01-00300-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00302-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-10 | 60 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00303-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00304-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00305-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00310-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-04-24 | 60 | 2015-02-23 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00313-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00349-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-06-02 | 60 | 2015-04-03 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00357-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00364-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00365-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00366-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-17 | 60 | 2015-01-16 | EA | 0 | 0 | 1 | No | 2014-02-11 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00369-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00370-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-10 | 60 | 2014-08-11 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00371-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00372-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-17 | 60 | 2015-01-16 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 471 | 2012-07-03
8043 | 473 | 167 |  | 167-01-00380-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00381-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 469 | 2015-10-26
8043 | 473 | 167 |  | 167-01-00383-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-12 | 60 | 2014-12-14 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00384-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00385-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-24 | 60 | 2014-04-25 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0 | 483 | 2016-11-01
8043 | 473 | 167 |  | 167-01-00401-S00 | -S00 | SRVC, HATCH, WELD, HASP & PI | 1 | 1 | 2017-03-23 | 123 | 2016-11-20 | EA | 0 | 0 | 1 | No | 2017-03-23 | 2017-03-23 | 0 | 0
8043 | 473 | 167 |  | 167-01-00410-804 | 611100-000000006 | GASKET | 2 | 1 | 2014-11-19 | 156 | 2014-06-16 | EA | 0 | 0 | 1 | No | 2014-04-09 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00425-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00426-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00426-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00427-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00430-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00432-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00439-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 469 | 2012-12-13
8043 | 473 | 167 |  | 167-01-00444-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00449-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00472-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-25 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00473-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00474-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-01-00499-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 471 | 2013-08-01
8043 | 473 | 167 |  | 167-01-00970-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 467 | 2011-10-17
8043 | 473 | 167 |  | 167-01-00973-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 467 | 2011-10-17
8043 | 473 | 167 |  | 167-01-INC01-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8043 | 473 | 167 |  | 167-03-00062-S00 | -S00 | WIRE ROPE, 1/8" DIA, CRES 31 | 4 | 4 | 2015-07-03 | 123 | 2015-03-02 | EA | 0 | 0 | 4 | No | 2017-04-19 | 2017-10-27 | 0 | 0
8043 | 473 | 169 |  | 169-01-00001-203 | 610315-000000005 | PROXIMITY SENSOR | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-204 | 610315-000000006 | SEAL KIT | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-205 | 610315-000000007 | SEAL KIT | 3 | 3 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 3 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-206 | 610315-000000008 | PRESSURE GAUGE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-207 | 610315-000000009 | DISCONNECT SWITCH | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-208 | 610315-000000010 | O-RING | 4 | 4 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 4 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-209 | 610315-000000011 | PRESSURE SWITCH | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-210 | 610315-000000012 | PRESSURE SWITCH | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-211 | 610315-000000013 | O-RING | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-212 | 610315-000000014 | O-RING | 2 | 2 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 2 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-213 | 610315-000000015 | BALL VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-214 | 610315-000000016 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-215 | 610315-000000017 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-216 | 610315-000000018 | SOLENOID VALVE | 2 | 2 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 2 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-217 | 610315-000000019 | CONTROL VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-218 | 610315-000000020 | CARTRIDGE VALVE | 3 | 3 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 3 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-219 | 610315-000000021 | FUSE (3 AMP) | 3 | 3 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 3 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-220 | 610315-000000022 | FUSE (50 AMP) | 3 | 3 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 3 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-221 | 610315-000000023 | SWITCH | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-222 | 610315-000000024 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-223 | 610315-000000025 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-224 | 610315-000000026 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-225 | 610315-000000027 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-226 | 610315-000000028 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-227 | 610315-000000029 | CARTRIDGE VALVE | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-228 | 610315-000000030 | SEAL KIT | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00001-229 | 610315-000000031 | THERMOSTAT | 1 | 1 | 2015-07-16 | 123 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 0 | 0 | 465 | 2014-09-29
8043 | 473 | 169 |  | 169-01-00006-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-03-12
8043 | 473 | 169 |  | 169-01-00006-L51 | -L51 | DATA, FOR WEIGHT CRITICAL IT | 1 | 1 | 2014-06-11 | 60 | 2014-04-12 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-03-12
8043 | 473 | 169 |  | 169-01-00006-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-06-11 | 123 | 2014-02-08 | LO | 0 | 0 | 1 | No | 2014-05-12 | 2017-10-27 | 0 | 0 | 485 | 2017-09-06
8043 | 473 | 169 |  | 169-01-00007-871 | 610312-000000106 | HANGAR DOOR, ROPE GUARD HRDW | 28 | 0 | 2015-03-17 | 180 | 2014-09-18 | EA | 0 | 26 | 26 | No | 2013-06-03 | 2017-10-27 | 0 | 0
8043 | 473 | 169 |  | 169-01-00007-873 | 610312-000000108 | HANGAR DOOR, CONTROL STATION | 2 | 1 | 2015-03-17 | 180 | 2014-09-18 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0
8043 | 473 | 169 |  | 169-01-00007-877 | 610312-000000112 | HANGAR DOOR, SIDE THRESHOLD | 2 | 0 | 2015-03-17 | 180 | 2014-09-18 | EA | 0 | 1 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0
8043 | 473 | 169 |  | 169-01-00010-L02 | -L02 | MANUALS, TECHNICAL, PRELIMIN | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L04 | -L04 | PROCEDURES, IN-PLANT TEST | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L07 | -L07 | REPORT, SHIPBOARD TEST, IAW | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | LO | 0 | 0 | 1 | No | 2013-06-04 | 2017-10-27 | 0 | 0 | 485 | 2017-09-06
8043 | 473 | 169 |  | 169-01-00010-L08 | -L08 | DRAWINGS, PRELIMINARY | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | LO | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2017-06-07
8043 | 473 | 169 |  | 169-01-00010-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L13 | -L13 | LIST, PREVENTATIVE MAINTENAN | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L32 | -L32 | FACTORY TRAINING | 1 | 1 | 2015-03-31 | 60 | 2015-01-30 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 465 | 2011-05-23
8043 | 473 | 169 |  | 169-01-00010-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-03-31 | 123 | 2014-11-28 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 202 |  | 202-01-00004-810 | 411500-000000011 | GEMS SENSOR P/N: 143020 - JU | 1 | 1 | 2015-05-14 | 123 | 2015-01-11 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 660 | 660
8043 | 473 | 202 |  | 202-01-00004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-03-17 | 2017-10-27 | 0 | 0 | 481 | 2017-04-17
8043 | 473 | 202 |  | 202-01-00005-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 469 | 2013-02-15
8043 | 473 | 202 |  | 202-01-00005-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 469 | 2013-02-15
8043 | 473 | 202 |  | 202-01-00005-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 469 | 2013-02-15
8043 | 473 | 202 |  | 202-01-00008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 477 | 2015-10-12
8043 | 473 | 202 |  | 202-01-00208-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 471 | 2013-08-02
8043 | 473 | 233 |  | 233-01-00001-869 | 230200-000000115 | ADAPTOR, P/N PA12652091 | 4 | 4 | 2015-01-05 | 45 | 2014-11-21 | EA | 0 | 0 | 4 | No | 2015-02-05 | 2017-10-27 | 0 | 0 | 477 | 2017-05-16
8043 | 473 | 233 |  | 233-01-00001-895 | 230200-000000133 | HEATER, OVERLOAD | 4 | 3 | 2015-01-05 | 105 | 2014-09-22 | EA | 0 | 0 | 3 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8043 | 473 | 233 |  | 233-01-00001-896 | 230200-000000134 | HEATER, OVERLOAD | 8 | 7 | 2015-01-05 | 105 | 2014-09-22 | EA | 0 | 0 | 7 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8043 | 473 | 234 |  | 234-01-00001-8K6 | 230100-000000224 | MOUNTING PLATE | 8 | 8 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 8 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8K7 | 230100-000000225 | SCREW | 32 | 32 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 32 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8K8 | 230100-000000226 | BOLT | 32 | 32 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 32 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8K9 | 230100-000000227 | WASHER, FLAT | 32 | 32 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 32 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8L0 | 230100-000000228 | WASHER, SPLIT LOCK | 32 | 32 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 32 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8L2 | 230100-000000230 | LIFTING EYE | 4 | 4 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 4 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8L6 | 230100-000000234 | PERFORATED SHEET | 4 | 4 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 4 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8M0 | 230100-000000238 | PERFORATED SHEET | 4 | 4 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 4 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-00001-8M1 | 230100-000000239 | COLLAR | 4 | 4 | 2014-11-19 | 123 | 2014-07-19 | EA | 0 | 0 | 4 | No | 2015-03-26 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-000A1-L07 | -L07 | REPORT, SHIPBOARD TEST, IAW | 1 | 1 | 2014-02-03 | 60 | 2013-12-05 | LO | 0 | 0 | 1 | No | 2014-07-17 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 234 |  | 234-01-004H1-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | LO | 0 | 0 | 1 | No | 2014-07-17 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 241 |  | 241-01-00001-820 | 202800-000000070 | LUBRICATION OIL LINE 12, BUS | 1 | 1 | 2014-10-16 | 123 | 2014-06-15 | EA | 0 | 0 | 1 | No | 2013-11-20 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 241 |  | 241-01-00001-864 | 202800-000000115 | TOOL SSS 170 T-LOGOUT (TOOLI | 2 | 2 | 2014-10-16 | 123 | 2014-06-15 | EA | 1 | 0 | 1 | No | 2013-11-20 | 2017-10-27 | 0 | 0
8043 | 473 | 241 |  | 241-01-00001-8B5 | 202800-000000166 | SCREW, HEX, M24 X 120MM LONG | 24 | 24 | 2014-10-23 | 123 | 2014-06-22 | EA | 0 | 0 | 24 | No | 2013-09-12 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 241 |  | 241-01-00001-8B6 | 202800-000000167 | NUT, HEX, M24-10 | 24 | 24 | 2014-10-23 | 123 | 2014-06-22 | EA | 0 | 0 | 24 | No | 2013-09-12 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 241 |  | 241-01-00001-8B7 | 202800-000000168 | O-RING, 330MM X 5MM THK, MAI | 8 | 8 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 8 | No | 2015-04-27 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 241 |  | 241-01-00001-8B8 | 202800-000000169 | O-RING, 115MM X 3MM, CONTROL | 8 | 8 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 8 | No | 2015-04-27 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 241 |  | 241-01-00001-8B9 | 202800-000000170 | O-RING, 185MM X 4MM, CONTROL | 4 | 4 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 4 | No | 2015-04-27 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 241 |  | 241-01-00001-913 | 202800-000000184 | TOOLING, SOCKET, 14MM, 12 PO | 4 | 4 | 2014-10-16 | 123 | 2014-06-15 | EA | 0 | 0 | 4 | No | 2013-09-12 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 241 |  | 241-01-00001-914 | 202800-000000185 | TOOLING, SOCKET, 14MM, 6 POI | 4 | 4 | 2014-10-16 | 123 | 2014-06-15 | EA | 0 | 0 | 4 | No | 2013-09-12 | 2017-10-27 | 0 | 0 | 481 | 2017-06-09
8043 | 473 | 243 |  | 243-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-05 | 60 | 2014-11-06 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 469 | 2013-06-11
8043 | 473 | 243 |  | 243-01-00002-800 | 204100-000000002 | BRAKE DISC, RENK ID #6479204 | 2 | 2 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 2 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00002-801 | 204100-000000003 | BRAKE CALIPER, LEFT W/HOSE | 2 | 2 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 2 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00002-802 | 204100-000000004 | BRAKE CALIPER, RIGHT W/HOSE | 2 | 2 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 2 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00002-803 | 204100-000000005 | VALVE BLOCK, RENK ID #683733 | 2 | 2 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 2 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00003-800 | 204100-000000007 | NUT, M33 X 2, JAURE | 32 | 32 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 32 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00003-801 | 204100-000000008 | SCREW, M30 X 180, JAURE | 24 | 24 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 24 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00003-802 | 204100-000000009 | SPLITTED FLANGE, JAURE | 2 | 2 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 2 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00003-803 | 204100-000000010 | WASHER A30, JAURE | 24 | 24 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 24 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00003-804 | 204100-000000011 | BOLT, M33 X 2, JAURE | 32 | 32 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 32 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00003-805 | 204100-000000012 | PIN, A20M6 X 60, DIN-7979 | 4 | 4 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 4 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 243 |  | 243-01-00003-806 | 204100-000000013 | PIN, A10M6 X 37, DIN-7979 | 8 | 8 | 2015-01-16 | 180 | 2014-07-20 | EA | 0 | 0 | 8 | No | 2016-03-16 | 2017-10-27 | 0 | 0
8043 | 473 | 247 |  | 247-01-00001-884 | 230800-000000113 | CABLE ASSY, FEEDBACK STEERIN | 2 | 2 | 2014-11-26 | 240 | 2014-03-31 | EA | 0 | 0 | 2 | No | 2013-11-22 | 2017-10-27 | 0 | 0
8043 | 473 | 247 |  | 247-01-00001-8B1 | 230800-000000140 | HOUSING, SEAL, OIL, WJ THRUS | 8 | 8 | 2014-11-26 | 123 | 2014-07-26 | EA | 0 | 0 | 8 | No | 2013-11-22 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 247 |  | 247-01-00001-L20 | -L20 | SUPPORT, VENDOR | 1 | 1 | 2014-11-26 | 60 | 2014-09-27 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 247 |  | 247-01-MS001-R02 | SRV524-011600001 | ADDED WORK, MOVE SPLITTERS/C | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2016-04-21 | 2017-10-27 | 0 | 0
8043 | 473 | 247 |  | 247-01-MS002-L07 | -L07 | REPORT, SHIPBOARD TEST, IAW | 1 | 1 | 2014-11-26 | 60 | 2014-09-27 | LO | 0 | 0 | 1 | No | 2013-12-11 | 2017-10-27 | 0 | 0 | 475 | 2015-02-12
8043 | 473 | 247 |  | 247-01-MS002-L20 | -L20 | SUPPORT, VENDOR | 1 | 1 | 2014-11-26 | 60 | 2014-09-27 | LO | 0 | 0 | 1 | No | 2013-12-11 | 2017-10-27 | 0 | 0 | 469 | 2013-06-11
8043 | 473 | 252 |  | 252-01-00001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-01-12 | 123 | 2014-09-11 | LO | 0 | 0 | 1 | No | 2014-08-07 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 252 |  | 252-01-00001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-01-12 | 123 | 2014-09-11 | LO | 0 | 0 | 1 | No | 2014-08-07 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8043 | 473 | 256 |  | 256-01-7S13A-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-06-16 | 60 | 2015-04-17 | EA | 0 | 0 | 1 | No | 2016-02-26 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8043 | 473 | 256 |  | 256-01-7S13A-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 2 | 2 | 2015-06-16 | 60 | 2015-04-17 | EA | 0 | 0 | 2 | No | 2016-02-26 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8043 | 473 | 259 |  | 259-01-17D21-L12 | -L12 | LIST, CALIBRATABLE COMPONENT | 1 | 1 | 2015-05-14 | 60 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-09-04 | 2017-10-27 | 0 | 0 | 467 | 2011-10-26
8043 | 473 | 259 |  | 259-05-00520-S00 | -S00 | GASKET MATERIAL, 12"X39" | 2 | 2 | 2014-05-28 | 123 | 2014-01-25 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 92.59 | 185.18
8043 | 473 | 259 |  | 259-05-00520-S01 | -S00 | GASKET MATERIAL, 12"X39" | 2 | 2 | 2014-05-28 | 123 | 2014-01-25 | EA | 0 | 0 | 2 | No | 2017-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 259 |  | 259-05-00548-S00 | -S00 | MOUNT, MACHINERY, TYPE 6E900 | 1 | 1 | 2015-02-25 | 123 | 2014-10-25 | EA | 0 | 0 | 1 | No | 2017-06-14 | 2017-10-27 | 342.99 | 342.99
8043 | 473 | 259 |  | 259-05-00562-S00 | -S00 | MOUNT SUPPORT LUG, CRES 321, | 2 | 2 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 70 | 140
8043 | 473 | 259 |  | 259-05-01000-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-08-23 | 2017-10-27 | 0 | 0
8043 | 473 | 259 |  | 259-05-01000-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2013-08-23 | 2017-10-27 | 0 | 0
8043 | 473 | 259 |  | 259-07-01000-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | LO | 0 | 0 | 1 | No | 2013-08-23 | 2017-10-27 | 0 | 0
8043 | 473 | 259 |  | 259-07-01000-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2013-08-23 | 2017-10-27 | 0 | 0
8043 | 473 | 261 |  | 261-01-E0001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-12-09 | 35 | 2014-11-04 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 469 | 2013-04-05
8043 | 473 | 261 |  | 261-01-E0005-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-01-12 | 123 | 2014-09-11 | LO | 0 | 0 | 1 | No | 2013-06-11 | 2017-10-27 | 0 | 0 | 481 | 2015-12-10
8043 | 473 | 262 |  | 262-01-E0003-800 | 680200-000000007 | SIGHT GLASS, REPLACEMENT | 1 | 1 | 2014-10-16 | 123 | 2014-06-15 | EA | 0 | 0 | 1 | No | 2014-10-06 | 2017-10-27 | 26.98 | 26.98 | 471 | 2015-09-22
8043 | 473 | 311 |  | 311-01-00001-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-03-17 | 2017-10-27 | 0 | 0 | 483 | 2015-12-02
8043 | 473 | 313 |  | 313-01-00001-804 | 414700-000000006 | CONNECTOR, CIRCULAR FOR 0.8 | 5 | 0 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 1 | 1 | No | 2013-06-05 | 2017-10-27 | 51 | 51
8043 | 473 | 313 |  | 313-01-00001-806 | 414700-000000008 | CONNECTOR, CIRCULAR FOR 2.4 | 4 | 0 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 1 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0
8043 | 473 | 313 |  | 313-01-00001-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2014-03-17 | 2017-10-27 | 0 | 0 | 450 | 2009-06-15
8043 | 473 | 313 |  | 313-01-00001-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-03-17 | 2017-10-27 | 0 | 0 | 450 | 2009-06-15
8043 | 473 | 313 |  | 313-01-00001-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 471 | 2015-03-09
8043 | 473 | 314 |  | 314-01-00002-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 481 | 2016-12-01
8043 | 473 | 314 |  | 314-01-00003-L20 | -L20 | SUPPORT, VENDOR | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2014-05-30 | 2017-10-27 | 1742.77 | 1742.77 | 471 | 2017-01-23
8043 | 473 | 314 |  | 314-01-00004-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 403 | 2005-05-12
8043 | 473 | 314 |  | 314-01-00005-801 | 415200-000000007 | CONNECTOR, CIRCULAR PART | 3 | 3 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 3 | No | 2017-07-05 | 2017-10-27 | 0 | 0
8043 | 473 | 314 |  | 314-01-00005-802 | 415200-000000008 | CONNECTOR, CIRCULAR REMOVABL | 12 | 12 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 12 | No | 2017-07-05 | 2017-10-27 | 0 | 0
8043 | 473 | 314 |  | 314-01-00005-803 | 415200-000000009 | CONNECTOR, CIRCULAR PART | 3 | 3 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 3 | No | 2017-07-05 | 2017-10-27 | 0 | 0
8043 | 473 | 324 |  | 324-01-00001-L04 | -L04 | PROCEDURES, IN-PLANT TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2014-06-20 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-01-00001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2014-03-10 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-01-00002-L04 | -L04 | PROCEDURES, IN-PLANT TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-01-00002-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-01-00002-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-01-00002-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-25
8043 | 473 | 324 |  | 324-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-25
8043 | 473 | 324 |  | 324-01-00002-L63 | -L63 | COMPUTER SOFTWARE/PROGRAM | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0
8043 | 473 | 324 |  | 324-01-00002-L64 | -L64 | COMPUTER SOFTWARE/PROGRAM | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-25
8043 | 473 | 324 |  | 324-01-00003-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-26
8043 | 473 | 324 |  | 324-01-00003-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-26
8043 | 473 | 324 |  | 324-01-00003-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 485 | 2017-10-26
8043 | 473 | 324 |  | 324-01-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-05-30 | 2017-10-27 | 0 | 0 | 465 | 2012-02-14
8043 | 473 | 324 |  | 324-01-00066-L66 | -L66 | TECHNOLOGY REFRESH AND OBSOL | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 450 | 2011-09-23
8043 | 473 | 324 |  | 324-02-00001-L04 | -L04 | PROCEDURES, IN-PLANT TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00001-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00001-L20 | -L20 | SUPPORT, VENDOR | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00001-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00002-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00002-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00002-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00003-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00003-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00003-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00004-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00004-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00004-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-17
8043 | 473 | 324 |  | 324-02-00004-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8043 | 473 | 324 |  | 324-02-00004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 485 | 2017-10-23
8043 | 473 | 324 |  | 324-02-00005-808 | 415900-000000013 | SERVICE PANEL, STAND ALONE | 1 | 1 | 2015-06-16 | 120 | 2015-02-16 | EA | 0 | 0 | 1 | No | 2017-08-01 | 2017-10-27 | 2746 | 2746 | 403 | 2005-06-14
8043 | 473 | 324 |  | 324-02-00005-813 | 415900-000000012 | MISSION MODULE PANELS IP54 K | 1 | 1 | 2014-01-20 | 120 | 2013-09-22 | LO | 0 | 0 | 1 | No | 2017-07-05 | 2017-10-27 | 0 | 0
8043 | 473 | 324 |  | 324-22-00003-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 465 | 2012-02-01
8043 | 473 | 324 |  | 324-22-00003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-03 | 2017-10-27 | 0 | 0 | 465 | 2012-02-01
8043 | 473 | 324 |  | 324-22-00004-S00 | -S00 | SOFTWARE UPGRADES, CF 2353 | 1 | 1 | 2017-02-24 | 123 | 2016-10-24 | EA | 0 | 0 | 1 | No | 2017-02-24 | 2017-02-24 | 5400 | 5400 | 477 | 2017-07-10
8043 | 473 | 324 |  | 324-22-00006-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-01-12 | 60 | 2014-11-13 | LO | 0 | 0 | 1 | No | 2017-04-12 | 2017-10-27 | 0 | 0 | 467 | 2017-06-05
8043 | 473 | 422 |  | 422-02-00001-800 | 330300560000-002 | BOX, STORAGE WITH FILTERS | 4 | 4 | 2015-02-12 | 123 | 2014-10-12 | EA | 0 | 0 | 4 | No | 2013-06-05 | 2017-10-27 | 385 | 1540 | 465 | 2011-10-20
8043 | 473 | 422 |  | 422-02-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 403 | 2005-11-11
8043 | 473 | 430 |  | 430-01-00001-811 | 400928-000000011 | MANUAL PULL STATION/METAL | 23 | 1 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0
8043 | 473 | 430 |  | 430-01-00001-856 | 410900-000000027 | COMPONENTS FOR MXL FIRE ALAR | 1 | 1 | 2014-01-20 | 42 | 2013-12-09 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0
8043 | 473 | 430 |  | 430-01-00001-857 | 410900-000000028 | COMPONENTS FOR MXL DC POWER | 1 | 1 | 2014-01-20 | 42 | 2013-12-09 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0
8043 | 473 | 430 |  | 430-01-00001-L64 | -L64 | COMPUTER SOFTWARE/PROGRAM | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 467 | 2012-02-14
8043 | 473 | 433 |  | 433-01-00001-804 | 410700-000000005 | CNTRLSTA, MICROPHONE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-02-07 | 2017-10-27 | 2250 | 2250 | 485 | 2017-05-02
8043 | 473 | 433 |  | 433-01-00001-840 | 410700-000000022 | BATTERY UPS DIAS ANNOUNCING | 2 | 2 | 2015-01-19 | 48 | 2014-12-02 | EA | 0 | 0 | 2 | No | 2015-08-18 | 2017-10-27 | 0 | 0
8043 | 473 | 436 |  | 436-03-00009-800 | 411400-000000002 | KEYPAD,WEATHER-PROOF 10 BUTT | 24 | 6 | 2014-01-20 | 120 | 2013-09-22 | EA | 3 | 0 | 3 | No | 2014-02-11 | 2017-10-27 | 418.28 | 1254.84
8043 | 473 | 436 |  | 436-08-00036-803 | 414000-000000005 | TUBING, POLYETHYLENE 6MM | 600 | 598 | 2015-02-19 | 49 | 2015-01-01 | FT | 0 | 0 | 598 | No | 2014-02-15 | 2017-10-27 | 247 | 147706
8043 | 473 | 436 |  | 436-08-00036-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0.01 | 0.01 | 403 | 2006-05-09
8043 | 473 | 436 |  | 436-08-00036-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0.01 | 0.01 | 403 | 2006-05-09
8043 | 473 | 436 |  | 436-08-00036-L22 | -L22 | MANUALS, TECHNICAL, FINAL | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 450 | 2009-11-11
8043 | 473 | 436 |  | 436-08-00036-L35 | -L35 | LIST OF VENDOR DRAWINGS | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0.01 | 0.01 | 403 | 2006-05-09
8043 | 473 | 436 |  | 436-08-00036-L39 | -L39 | PROCEDURE, SHIPBOARD TEST | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0.01 | 0.01 | 403 | 2006-05-09
8043 | 473 | 436 |  | 436-08-00036-L48 | -L48 | TESTING, SHOCK, IAW APPENDIX | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 436 |  | 436-08-00036-L52 | -L52 | TESTING, NOISE AND VIBRATION | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 436 |  | 436-08-00036-L54 | -L54 | TESTING EMI | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 436 |  | 436-08-00080-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-15 | 2017-10-27 | 0 | 0
8043 | 473 | 437 |  | 437-03-00043-L34 | -L34 | PROVISIONING TECH DOC. | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8043 | 473 | 437 |  | 437-05-00200-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 467 | 2012-06-12
8043 | 473 | 437 |  | 437-05-00201-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8043 | 473 | 437 |  | 437-11-00001-807 | 414100-000000010 | ASSEMBLY, BELL VIBRATION | 4 | 2 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 2 | No | 2013-06-05 | 2017-10-27 | 2500 | 5000
8043 | 473 | 437 |  | 437-11-00001-L09 | -L09 | DRAWINGS, FINAL, CERTIFIED | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 483 | 2017-04-04
8043 | 473 | 437 |  | 437-11-00001-S00 | -S00 | EDT SHOCK MODS PER CF 2397 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-06-02 | 2017-10-27 | 0 | 0
8043 | 473 | 439 |  | 439-01-00001-810 | 412100-000000012 | CAMERA, FIBER OPTIC | 4 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 3 | No | 2013-06-05 | 2017-10-27 | 0 | 0
8043 | 473 | 439 |  | 439-01-00001-811 | 412100-000000013 | LENS, FIBER OPTIC, FWD | 2 | 2 | 2014-11-26 | 56 | 2014-10-01 | EA | 0 | 0 | 2 | No | 2015-08-19 | 2017-10-27 | 0 | 0 | 120 | 2011-03-08
8043 | 473 | 439 |  | 439-01-00001-812 | 412100-000000014 | LENS, FIBER OPTIC, AFT | 2 | 2 | 2014-11-26 | 56 | 2014-10-01 | EA | 0 | 0 | 2 | No | 2015-08-19 | 2017-10-27 | 0 | 0 | 120 | 2011-03-08
8043 | 473 | 441 |  | 441-01-00016-823 | 410600-000000076 | KIT, FLUSH MOUNTING, FM 8900 | 1 | 1 | 2015-04-27 | 120 | 2014-12-28 | EA | 0 | 0 | 1 | No | 2016-10-13 | 2017-10-27 | 0 | 0 | 485 | 2017-07-26
8043 | 473 | 441 |  | 441-01-00016-824 | 410600-000000077 | REMOTE STATION, WALL MOUNT | 1 | 1 | 2014-10-17 | 120 | 2014-06-19 | EA | 0 | 0 | 1 | No | 2016-10-13 | 2017-10-27 | 0 | 0 | 485 | 2017-07-26
8043 | 473 | 474 |  | 474-01-00003-880 | 320002030000-001 | ALEX UPS BALLAST | 1 | 1 | 2015-09-04 | 42 | 2015-07-24 | EA | 0 | 0 | 1 | No | 2016-11-08 | 2017-10-27 | 0 | 0 | 485 | 2017-07-26
8043 | 473 | 494 |  | 494-01-00001-839 | 413800-000000016 | POWER SUPPLY, UNINTERRUPTIBL | 2 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 5501.4 | 5501.4
8043 | 473 | 494 |  | 494-01-00001-S16 | -S00 | KEYPAD, REMOTE, HED, MORIAH | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | EA | 0 | 0 | 1 | No | 2017-05-18 | 2017-10-27 | 0 | 0
8043 | 473 | 533 |  | 533-01-TH001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-05-14 | 60 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0
8043 | 473 | 533 |  | 533-01-V0008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-21 | 60 | 2014-03-22 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 481 | 2016-03-23
8043 | 473 | 533 |  | 533-03-HA004-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-07-22 | 60 | 2014-05-23 | LO | 0 | 0 | 1 | No | 2017-05-12 | 2017-10-27 | 0 | 0
8043 | 473 | 541 |  | 541-01-06P13-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-09-11 | 60 | 2015-07-13 | EA | 0 | 0 | 1 | No | 2016-02-26 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8043 | 473 | 551 |  | 551-01-E0001-S01 | SRV650-032200005 | SRVC, LIGHT OFF AIR COMPRESS | 1 | 1 | 2017-02-27 | 123 | 2016-10-27 | LO | 0 | 0 | 1 | No | 2017-02-13 | 2017-02-13 | 0 | 0
8043 | 473 | 551 |  | 551-01-E0009-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 469 | 2012-05-22
8043 | 473 | 551 |  | 551-01-E0009-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 469 | 2012-05-22
8043 | 473 | 555 |  | 555-01-E0001-805 | 760129-000000007 | HFP CYLINDERS, 62LB | 3 | 1 | 2014-02-24 | 123 | 2013-10-24 | EA | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0
8043 | 473 | 555 |  | 555-01-E0001-806 | 760129-000000008 | HFP CYLINDERS BRACKETS, 62LB | 6 | 4 | 2014-02-24 | 123 | 2013-10-24 | EA | 2 | 0 | 2 | No | 2013-06-27 | 2017-10-27 | 0 | 0
8043 | 473 | 555 |  | 555-01-E0001-819 | 760129-000000021 | MAIN REMOTE ACTUATOR PANEL | 2 | 2 | 2014-06-18 | 21 | 2014-05-28 | EA | 0 | 0 | 2 | No | 2017-08-09 | 2017-10-27 | 0 | 0 | 467 | 2017-08-11
8043 | 473 | 555 |  | 555-01-E0001-820 | 760129-000000022 | MAIN SECONDARY REMOTE PANEL | 3 | 3 | 2014-02-24 | 21 | 2014-02-03 | EA | 0 | 0 | 3 | No | 2017-08-09 | 2017-10-27 | 0 | 0 | 469 | 2017-08-17
8043 | 473 | 555 |  | 555-01-E0001-820 | 760129-000000022 | MAIN SECONDARY REMOTE PANEL | 3 | 3 | 2014-02-24 | 21 | 2014-02-03 | EA | 0 | 0 | 3 | No | 2017-08-09 | 2017-10-27 | 0 | 0 | 469 | 2017-08-17
8043 | 473 | 555 |  | 555-01-E0001-821 | 760129-000000023 | SECONDARY REMOTE ACTUATOR PA | 5 | 5 | 2014-02-24 | 21 | 2014-02-03 | EA | 0 | 0 | 5 | No | 2017-08-09 | 2017-10-27 | 0 | 0 | 469 | 2017-08-17
8043 | 473 | 555 |  | 555-01-E0001-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 2 | 2 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 1 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0
8043 | 473 | 555 |  | 555-01-E0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 2 | 2 | 2014-01-20 | 60 | 2013-11-21 | EA | 1 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0
8043 | 473 | 555 |  | 555-01-E0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-02-24 | 60 | 2013-12-26 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0 | 481 | 2017-01-10
8043 | 473 | 555 |  | 555-02-E0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2016-03-22 | 2017-10-27 | 0 | 0 | 403 | 2005-02-01
8043 | 473 | 555 |  | 555-02-E0001-S00 | -S00 | SRVC, MODIFY AFFF SKID, CF24 | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-10-03 | 2017-10-27 | 0 | 0
8043 | 473 | 555 |  | 555-02-V0001-800 | 805900-000000008 | TEST FITTING, ASSEMBLY NO. 8 | 2 | 2 | 2014-04-17 | 180 | 2013-10-19 | EA | 1 | 0 | 1 | No | 2014-07-18 | 2017-10-27 | 0 | 0
8043 | 473 | 555 |  | 555-02-V0015-800 | 533700-000000001 | TEST FTG, REMOVABLE, FOR 1" | 1 | 1 | 2014-10-03 | 180 | 2014-04-06 | EA | 0 | 0 | 1 | No | 2015-02-24 | 2017-10-27 | 0 | 0 | 481 | 2017-09-25
8043 | 473 | 555 |  | 555-07-E0002-801 | 681014-000000002 | NOZZLE, SPRAY, 1" FPT | 169 | 34 | 2014-08-04 | 30 | 2014-07-05 | EA | 11 | 0 | 23 | No | 2013-06-27 | 2017-10-27 | 691.08 | 15894.84
8043 | 473 | 555 |  | 555-07-E0002-802 | 681014-000000003 | NOZZLE STRAINER KIT | 169 | 169 | 2014-08-04 | 30 | 2014-07-05 | EA | 16 | 0 | 153 | No | 2013-06-27 | 2017-10-27 | 0 | 0
8043 | 473 | 555 |  | 555-07-M0003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-03 | 60 | 2013-12-05 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0
8043 | 473 | 565 |  | 565-01-00001-824 | 230900-000000026 | ECU, INTERCEPTOR SERVO | 2 | 1 | 2015-01-05 | 180 | 2014-07-09 | EA | 0 | 0 | 1 | No | 2013-05-10 | 2017-10-27 | 0 | 0
8043 | 473 | 583 |  | 583-01-00002-810 | 232700-000000013 | PLACARD, OPERATING INSTRUCTI | 1 | 1 | 2015-05-27 | 123 | 2015-01-24 | SE | 0 | 0 | 1 | No | 2015-06-02 | 2017-10-27 | 0.01 | 0.01 | 811 | 2006-12-08
8043 | 473 | 583 |  | 583-01-00002-811 | 232700-000000011 | PLACARD, LUBRICATION/GAS FIL | 1 | 1 | 2015-05-27 | 123 | 2015-01-24 | SE | 0 | 0 | 1 | No | 2015-06-02 | 2017-10-27 | 0 | 0 | 810 | 2007-01-29
8043 | 473 | 583 |  | 583-01-00002-815 | 232700-000000012 | BATTERY, UPS DAVIT ELECTRIC | 1 | 1 | 2015-05-27 | 30 | 2015-04-27 | EA | 0 | 0 | 1 | No | 2015-08-18 | 2017-10-27 | 26.95 | 26.95 | 467 | 2015-09-11
8043 | 473 | 583 |  | 583-01-00002-L10 | -L10 | LIST, SHIP LOOSE PARTS | 1 | 1 | 2015-04-20 | 60 | 2015-02-19 | EA | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0 | 465 | 2012-02-22
8043 | 473 | 583 |  | 583-03-00001-L34 | -L34 | PROVISIONING TECH DOC. | 1 | 1 | 2015-06-03 | 60 | 2015-04-04 | LO | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0 | 485 | 2017-03-14
8043 | 473 | 583 |  | 583-03-00001-L41 | -L41 | LIST OF RECOMMENDED SPARE PA | 1 | 1 | 2015-06-03 | 60 | 2015-04-04 | LO | 0 | 0 | 1 | No | 2013-06-07 | 2017-10-27 | 0 | 0 | 485 | 2017-03-14
8043 | 473 | 593 |  | 593-01-E0001-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | LO | 0 | 0 | 1 | No | 2013-06-18 | 2017-10-27 | 100 | 100 | 467 | 2011-09-28
8043 | 473 | 593 |  | 593-01-E0001-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | LO | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 471 | 2015-03-25
8043 | 473 | 593 |  | 593-02-06V06-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2016-02-26 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8043 | 473 | 593 |  | 593-02-08SV6-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2016-02-26 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8043 | 473 | 593 |  | 593-02-E0003-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 593 |  | 593-02-E0003-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8043 | 473 | 625 |  | 625-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0 | 477 | 2015-08-05
8043 | 473 | 625 |  | 625-01-00015-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 481 | 2016-01-08
8043 | 473 | 625 |  | 625-01-00031-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 481 | 2016-01-08
8043 | 473 | 625 |  | 625-01-00032-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-17 | 60 | 2015-01-16 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 481 | 2016-01-08
8043 | 473 | 625 |  | 625-01-00033-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-12-09 | 2017-10-27 | 0 | 0 | 481 | 2016-01-08
8043 | 473 | 625 |  | 625-01-0005P-810 | 611302-000000030 | WINDOW BOLTING/DRILLING | 1 | 1 | 2014-11-19 | 150 | 2014-06-22 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8043 | 473 | 625 |  | 625-01-0005S-810 | 611302-000000036 | WINDOW BOLTING/DRILLING | 1 | 1 | 2014-11-19 | 150 | 2014-06-22 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8043 | 473 | 633 |  | 633-01-00001-813 | 412900-000000014 | STUD/FERRULE, 28MM LG, USED | 72 | 71 | 2014-01-20 | 48 | 2013-12-03 | EA | 21 | 0 | 50 | No | 2014-07-15 | 2017-10-27 | 0 | 0
8043 | 473 | 633 |  | 633-01-00001-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | LO | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 403 | 2005-03-01
8043 | 473 | 633 |  | 633-01-00001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-05-13
8043 | 473 | 633 |  | 633-01-00001-L63 | -L63 | COMPUTER SOFTWARE/PROGRAM | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 450 | 2010-08-27
8043 | 473 | 633 |  | 633-01-00001-L64 | -L64 | COMPUTER SOFTWARE/PROGRAM | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2013-06-05 | 2017-10-27 | 0 | 0 | 450 | 2010-08-27
8043 | 473 | 780 |  | 780-01-00001-L15 | -L15 | DATA, WEIGHT | 1 | 1 | 2015-05-27 | 60 | 2015-03-28 | LO | 0 | 0 | 1 | No | 2013-05-09 | 2017-10-27 | 0 | 0 | 485 | 2017-01-03
8044 | 473 | 555 |  | 555-02-V0026 | 520123150033-002 | VALVE, BALL, 1/2" IPS, BRONZ | 20 | 6 | 2014-01-20 | 123 | 2013-09-19 | EA | 2 | 0 | 4 | No | 2013-10-24 | 2017-10-27 | 482 | 1928
8044 | 473 | 167 |  | 167-01-00478-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 465 | 2012-02-17
8044 | 473 | 167 |  | 167-01-00479-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 465 | 2012-02-17
8044 | 473 | 256 |  | 256-01-F0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-04 | 60 | 2015-01-03 | EA | 0 | 0 | 1 | No | 2013-10-21 | 2017-10-27 | 0 | 0
8044 | 473 | 256 |  | 256-01-F0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-03-04 | 60 | 2015-01-03 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8044 | 473 | 256 |  | 256-01-V0041-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 261 |  | 261-01-V0028-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-01 | 60 | 2014-03-02 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8044 | 473 | 261 |  | 261-01-V0032-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 261 |  | 261-01-V0033-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0.01 | 0.01 | 450 | 2009-04-03
8044 | 473 | 261 |  | 261-01-V0037-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 475 | 2015-03-05
8044 | 473 | 261 |  | 261-01-V0038-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 475 | 2015-03-05
8044 | 473 | 261 |  | 261-01-V0044-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2015-11-17 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 261 |  | 261-01-V0045-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2015-11-17 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 261 |  | 261-01-V0045-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2015-11-17 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 261 |  | 261-01-V0072-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 483 | 2017-08-22
8044 | 473 | 261 |  | 261-01-V0073-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 483 | 2017-08-22
8044 | 473 | 262 |  | 262-01-06P04-800 | 274400-000000001 | REPAIR KIT, MODIFY, GAUGE/TR | 4 | 4 | 2015-03-04 | 70 | 2014-12-24 | EA | 0 | 0 | 4 | No | 2015-12-09 | 2017-10-27 | 0 | 0
8044 | 473 | 262 |  | 262-01-E0004-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | EA | 0 | 0 | 1 | No | 2013-07-22 | 2017-10-27 | 0 | 0 | 471 | 2013-03-26
8044 | 473 | 262 |  | 262-01-E0007-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 1 | No | 2013-07-22 | 2017-10-27 | 0 | 0 | 469 | 2013-03-26
8044 | 473 | 262 |  | 262-01-E0007-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | LO | 0 | 0 | 1 | No | 2013-07-22 | 2017-10-27 | 0 | 0 | 469 | 2013-03-26
8044 | 473 | 262 |  | 262-01-E0010-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-01-16 | 60 | 2014-11-17 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 469 | 2013-03-26
8044 | 473 | 262 |  | 262-01-E0010-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2015-01-16 | 123 | 2014-09-15 | LO | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 481 | 2015-12-14
8044 | 473 | 262 |  | 262-01-V0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 475 | 2015-03-05
8044 | 473 | 262 |  | 262-01-V0002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 469 | 2014-04-17
8044 | 473 | 262 |  | 262-01-V0003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | EA | 0 | 0 | 1 | No | 2013-10-21 | 2017-10-27 | 0 | 0 | 471 | 2014-06-17
8044 | 473 | 262 |  | 262-01-V0006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-01 | 60 | 2014-03-02 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 475 | 2015-03-05
8044 | 473 | 262 |  | 262-01-V0072-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-01 | 60 | 2014-03-02 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-05-02
8044 | 473 | 262 |  | 262-01-V0073-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-01 | 60 | 2014-03-02 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 481 | 2016-05-02
8044 | 473 | 262 |  | 262-01-V0084-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | No | 2016-05-03 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 262 |  | 262-01-V0087-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | No | 2016-05-03 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 262 |  | 262-01-V0089-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | No | 2015-11-17 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 506 |  | 506-01-V0072-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 481 | 2016-05-02
8044 | 473 | 506 |  | 506-01-V0073-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 481 | 2016-05-02
8044 | 473 | 506 |  | 506-01-VLS01-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2013-10-21 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8044 | 473 | 514 |  | 514-01-E0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-01-05 | 60 | 2014-11-06 | EA | 0 | 0 | 1 | No | 2013-05-29 | 2017-10-27 | 0 | 0 | 469 | 2013-02-27
8044 | 473 | 514 |  | 514-01-E0001-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2015-01-05 | 60 | 2014-11-06 | LO | 0 | 0 | 1 | No | 2013-05-29 | 2017-10-27 | 0 | 0 | 469 | 2013-02-27
8044 | 473 | 514 |  | 514-01-V0017-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 477 | 2015-09-15
8044 | 473 | 514 |  | 514-01-VPR01-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 250 | 250 | 481 | 2017-05-25
8044 | 473 | 521 |  | 521-01-V0007-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-01 | 60 | 2014-03-02 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 469 | 2012-05-16
8044 | 473 | 521 |  | 521-01-V0020-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2014-04-30 | 2017-10-27 | 0 | 0 | 481 | 2015-11-04
8044 | 473 | 528 |  | 528-01-M0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-05-14 | 60 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0
8044 | 473 | 528 |  | 528-01-M0003-800 | 572300-000000001 | FLOW CONTROL FITTING, 3" NPT | 2 | 2 | 2015-05-14 | 14 | 2015-04-30 | EA | 0 | 0 | 2 | No | 2013-10-17 | 2017-10-27 | 182.95 | 365.9 | 465 | 2014-06-11
8044 | 473 | 528 |  | 528-01-M0003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-05-14 | 60 | 2015-03-15 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0
8044 | 473 | 529 |  | 529-01-E0002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | EA | 0 | 0 | 1 | No | 2013-10-22 | 2017-10-27 | 0 | 0 | 481 | 2017-04-25
8044 | 473 | 531 |  | 531-01-E0001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-07-08 | 123 | 2014-03-07 | LO | 0 | 0 | 1 | No | 2013-06-11 | 2017-10-27 | 0 | 0
8044 | 473 | 533 |  | 533-01-M0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 471 | 2016-11-09
8044 | 473 | 533 |  | 533-01-M0003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 483 | 2017-08-22
8044 | 473 | 533 |  | 533-01-M0004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 483 | 2017-08-22
8044 | 473 | 533 |  | 533-01-M0005-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 477 | 2015-05-18
8044 | 473 | 533 |  | 533-01-M0006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 483 | 2017-08-22
8044 | 473 | 533 |  | 533-01-M0008-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-03 | 60 | 2014-08-04 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 483 | 2017-08-22
8044 | 473 | 533 |  | 533-01-M0009-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 477 | 2015-05-18
8044 | 473 | 533 |  | 533-01-M0010-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0
8044 | 473 | 533 |  | 533-01-V0007-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 481 | 2016-09-15
8044 | 473 | 533 |  | 533-01-VPR03-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2012-10-18
8044 | 473 | 541 |  | 541-01-V0023-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 479 | 2015-06-04
8044 | 473 | 542 |  | 542-01-M0002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0
8044 | 473 | 542 |  | 542-01-M0004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-02 | 60 | 2014-10-03 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0 | 471 | 2015-05-11
8044 | 473 | 551 |  | 551-01-3P13A-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-09-11 | 60 | 2015-07-13 | EA | 0 | 0 | 1 | No | 2016-01-07 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8044 | 473 | 551 |  | 551-01-3P13A-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-09-11 | 60 | 2015-07-13 | EA | 0 | 0 | 1 | No | 2016-01-07 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8044 | 473 | 551 |  | 551-01-E0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-01-05 | 60 | 2014-11-06 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0 | 450 | 2009-09-11
8044 | 473 | 551 |  | 551-01-E0002-L23 | -L23 | RELEASE FOR MANUFACTURE | 1 | 1 | 2015-05-07 | 60 | 2015-03-08 | LO | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 471 | 2013-04-16
8044 | 473 | 551 |  | 551-01-E0008-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-10-16 | 60 | 2014-08-17 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 469 | 2012-05-22
8044 | 473 | 551 |  | 551-01-E0008-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-10-16 | 123 | 2014-06-15 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 469 | 2012-05-22
8044 | 473 | 551 |  | 551-01-E0010-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2014-12-09 | 60 | 2014-10-10 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 469 | 2012-05-22
8044 | 473 | 551 |  | 551-01-E0010-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-12-09 | 123 | 2014-08-08 | LO | 0 | 0 | 1 | No | 2013-06-27 | 2017-10-27 | 0 | 0 | 469 | 2012-05-22
8044 | 473 | 551 |  | 551-01-GA003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-09-04 | 60 | 2015-07-06 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 479 | 2015-06-03
8044 | 473 | 551 |  | 551-01-GA003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-09-04 | 60 | 2015-07-06 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 479 | 2015-06-03
8044 | 473 | 551 |  | 551-01-M0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-05-28 | 60 | 2014-03-29 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0
8044 | 473 | 551 |  | 551-01-M0003-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-24 | 60 | 2014-02-23 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0
8044 | 473 | 551 |  | 551-01-M0004-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-01-30 | 60 | 2014-12-01 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0
8044 | 473 | 551 |  | 551-01-M0005-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0
8044 | 473 | 551 |  | 551-01-M0006-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0
8044 | 473 | 551 |  | 551-01-M0008-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-09-08 | 60 | 2014-07-10 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0.01 | 0.01 | 403 | 2006-06-13
8044 | 473 | 551 |  | 551-01-M9176-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-19 | 60 | 2014-12-21 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0
8044 | 473 | 551 |  | 551-01-VPR01-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | EA | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 250 | 250 | 481 | 2017-06-28
8044 | 473 | 551 |  | 551-01-VPR09-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0
8044 | 473 | 551 |  | 551-01-VPR13-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | EA | 0 | 0 | 1 | No | 2014-05-12 | 2017-10-27 | 0 | 0 | 483 | 2017-04-18
8044 | 473 | 551 |  | 551-01-VPR13-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | EA | 0 | 0 | 1 | No | 2014-05-12 | 2017-10-27 | 0 | 0 | 483 | 2017-04-18
8044 | 473 | 551 |  | 551-02-M0006-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | LO | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 481 | 2016-05-12
8044 | 473 | 551 |  | 551-02-M0007-L50 | -L50 | CERTIFICATES, CONSTRUCTION | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | LO | 0 | 0 | 1 | No | 2014-03-03 | 2017-10-27 | 0 | 0 | 481 | 2016-05-12
8044 | 473 | 555 |  | 555-02-V0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-17 | 60 | 2014-02-16 | EA | 0 | 0 | 1 | No | 2014-01-22 | 2017-10-27 | 0 | 0 | 483 | 2017-10-11
8044 | 473 | 555 |  | 555-07-17D13-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-04-07 | 60 | 2015-02-06 | EA | 0 | 0 | 1 | No | 2016-01-07 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8044 | 473 | 555 |  | 555-07-17D13-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2015-04-07 | 60 | 2015-02-06 | EA | 0 | 0 | 1 | No | 2016-01-07 | 2017-10-27 | 0 | 0 | 481 | 2015-12-31
8044 | 473 | 555 |  | 555-07-S0002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-01 | 60 | 2014-07-03 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0
8044 | 473 | 555 |  | 555-07-V0013-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0
8044 | 473 | 593 |  | 593-01-E0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-07-08 | 60 | 2014-05-09 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0 | 403 | 2005-04-22
8044 | 473 | 593 |  | 593-02-E0001-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-10-23 | 60 | 2014-08-24 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0 | 483 | 2016-07-19
8044 | 473 | 593 |  | 593-02-E0002-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | EA | 0 | 0 | 1 | No | 2016-03-11 | 2017-10-27 | 0 | 0 | 481 | 2016-07-19
8044 | 473 | 593 |  | 593-02-V0002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | EA | 0 | 0 | 1 | No | 2016-05-03 | 2017-10-27 | 0 | 0 | 483 | 2017-10-10
8044 | 473 | 613 |  | 613-01-00022-801 | 701500-000000011 | CERT OF INSPECTION (MILL TES | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2015-12-15 | 2017-10-27 | 0 | 0
8044 | 473 | 625 |  | 625-01-00002-810 | 611302-000000012 | WINDOW BOLTING/DRILLING TEMP | 1 | 1 | 2015-03-17 | 150 | 2014-10-18 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8044 | 473 | 625 |  | 625-01-00002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-17 | 60 | 2015-01-16 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0 | 477 | 2015-08-05
8044 | 473 | 625 |  | 625-01-00003-810 | 611302-000000018 | WINDOW BOLTING/DRILLING TEMP | 1 | 1 | 2015-03-17 | 150 | 2014-10-18 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8044 | 473 | 625 |  | 625-01-00004-810 | 611302-000000024 | WINDOW BOLTING/DRILLING TEMP | 1 | 1 | 2015-03-17 | 150 | 2014-10-18 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8044 | 473 | 625 |  | 625-01-0005P-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0 | 477 | 2015-08-05
8044 | 473 | 625 |  | 625-01-0005S-802 | 611302-000000033 | JUNCTION BOX TO CONTROLLER | 1 | 1 | 2014-11-19 | 150 | 2014-06-22 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0
8044 | 473 | 625 |  | 625-01-0005S-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-11-19 | 60 | 2014-09-20 | EA | 0 | 0 | 1 | No | 2013-05-08 | 2017-10-27 | 0 | 0 | 477 | 2015-08-05
8045 | 473 | 110 |  | 11-13E030G08 | 11-13E030G08 | PLATE, 3/16" X 8' X 4', STEE | 6 | 0 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 1 | 1 | No | 2014-01-24 | 2017-10-27 | 213.75 | 213.75
8045 | 473 | 110 |  | 11-13E400T12 | 11-13E400T12 | PLATE, 2 1/2" STEEL ABS GRAD | 1 | 0 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 1 | 1 | No | 2014-01-24 | 2017-10-27 | 4131.12 | 4131.12 | 481 | 2016-09-26
8045 | 473 | 110 |  | 11-13M085T40 | 11-13M085T40 | PLATE, 8.5MM X 96" X 40', ST | 6 | 4 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 4 | No | 2013-06-24 | 2017-10-27 | 2109.97 | 8439.88
8045 | 473 | 110 |  | 11-13M125T40 | 11-13M125T40 | PLATE, 12.5MM X 96" X 40', S | 2 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2013-06-17 | 2017-10-27 | 2774.98 | 2774.98 | 485 | 2017-07-27
8045 | 473 | 110 |  | 11-13M140T40 | 11-13M140T40 | PLATE, 14MM X 96" X 40', STE | 2 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2013-06-17 | 2017-10-27 | 7202.99 | 7202.99 | 485 | 2017-10-09
8045 | 473 | 110 |  | 11-13M230T40 | 11-13M230T40 | PLATE, 23MM X 96" X 40', STE | 8 | 7 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 7 | No | 2013-06-17 | 2017-10-27 | 6064.41 | 42450.87
8045 | 473 | 110 |  | 11-14M055T40 | 11-14M055T40 | PLATE, 5.5MM(8.84#) X 96" X | 13 | 4 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 4 | No | 2013-07-02 | 2017-10-27 | 4089.35 | 16357.4
8045 | 473 | 110 |  | 11-14M075T40 | 11-14M075T40 | PLATE, 7.5MM(12.06#) X 96" X | 14 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2013-07-02 | 2017-10-27 | 2333.84 | 2333.84
8045 | 473 | 110 |  | 11-14M100T40 | 11-14M100T40 | PLATE, 10MM (16.08#) X 96" X | 14 | 4 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 4 | No | 2013-06-17 | 2017-10-27 | 7125.83 | 28503.32
8045 | 473 | 110 |  | 11-14M120T40 | 11-14M120T40 | PLATE, 12MM (19.3#) X 96" X | 9 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2013-06-17 | 2017-10-27 | 8550.99 | 8550.99
8045 | 473 | 110 |  | 11-14M130T40 | 11-14M130T40 | PLATE, 13MM(20.9#) X 96" X 4 | 5 | 2 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 2 | No | 2013-06-17 | 2017-10-27 | 7590.88 | 15181.76
8045 | 473 | 110 |  | 11-14M210T40 | 11-14M210T40 | PLATE, 21MM(33.77#) X 96" X | 1 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2013-06-17 | 2017-10-27 | 15287.66 | 15287.66
8045 | 473 | 110 |  | 11-14M560T26 | 11-14M560T26 | PLATE, 56MM X 96" X 26', STE | 2 | 2 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 2 | No | 2013-07-01 | 2017-10-27 | 29309.32 | 58618.64
8045 | 473 | 110 |  | 11-15M070T40 | 11-15M070T40 | PLATE, 7MM X 96" X 40', STEE | 18 | 3 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 3 | No | 2013-06-17 | 2017-10-27 | 1953.54 | 5860.62
8045 | 473 | 110 |  | 11-15M085T40 | 11-15M085T40 | PLATE, 8.5MM X 96" X 40', ST | 11 | 2 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 2 | No | 2013-06-17 | 2017-10-27 | 2328.62 | 4657.24
8045 | 473 | 110 |  | 11-15M150T40 | 11-15M150T40 | PLATE, 15MM X 96" X 40', STE | 1 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2013-06-17 | 2017-10-27 | 4723.11 | 4723.11
8045 | 473 | 110 |  | 11-15M200T40 | 11-15M200T40 | PLATE, 20MM X 96" X 40', STE | 8 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2013-06-17 | 2017-10-27 | 5479.43 | 5479.43
8045 | 473 | 150 |  | 11-32M060T20 | 11-32M060T20 | PLATE, .236(6MM) X 96" X 20' | 10 | 1 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 0 | 1 | No | 2013-09-24 | 2017-10-27 | 1205 | 1205
8045 | 473 | 150 |  | 11-33E040N12 | 11-33E040N12 | PLATE, 1/4" X 6' X 12', AL | 13 | 0 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 3 | 3 | No | 2013-12-18 | 2017-10-27 | 556.26 | 1668.78
8045 | 473 | 150 |  | 11-33E080G08 | 11-33E080G08 | PLATE, 1/2" X 4' X 8', ALUMI | 1 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2014-01-24 | 2017-10-27 | 531.1 | 531.1
8045 | 473 | 150 |  | 11-33E080G08 | 11-33E080G08 | PLATE, 1/2" X 4' X 8', ALUMI | 1 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2014-01-24 | 2017-10-27 | 531.1 | 531.1
8045 | 473 | 150 |  | 11-33M090T20 | 11-33M090T20 | PLATE, .354(9MM)X 96"X 20', | 3 | 3 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 0 | 3 | No | 2013-09-24 | 2017-10-27 | 1870.36 | 5611.08
8045 | 473 | 150 |  | 11-33M110T20 | 11-33M110T20 | PLATE, .433(11MM) X 96" X 20 | 31 | 3 | 2014-01-20 | 168 | 2013-08-05 | EA | 0 | 7 | 10 | No | 2013-09-24 | 2017-10-27 | 2287.77 | 22877.7
8045 | 473 | 150 |  | 11-33M120T20 | 11-33M120T20 | PLATE, .472(12MM) X 96" X 20 | 1 | 1 | 2014-01-20 | 168 | 2013-08-05 | EA | 0 | 0 | 1 | No | 2013-09-24 | 2017-10-27 | 2493.83 | 2493.83
8045 | 473 | 150 |  | 11-33M150T20 | 11-33M150T20 | PLATE, .591(15MM) X 96" X 20 | 18 | 5 | 2014-01-20 | 168 | 2013-08-05 | EA | 0 | 0 | 5 | No | 2013-09-24 | 2017-10-27 | 3122.57 | 15612.85
8045 | 473 | 150 |  | 11-33M250T20 | 11-33M250T20 | PLATE, 1" X 8' X 20', ALUMIN | 4 | 2 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 2 | No | 2013-09-24 | 2017-10-27 | 5689.96 | 11379.92
8045 | 473 | 150 |  | 11-35E040G10 | 11-35E040G10 | PLATE, 1/4" X 4' X 10', ALUM | 11 | 1 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 1 | No | 2014-01-24 | 2017-10-27 | 331.56 | 331.56
8045 | 473 | 110 |  | 11-42E160G04 | 11-42E160G04 | PLATE, 1" X 4'X 4', STAINLES | 1 | 1 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 0 | 1 | No | 2013-12-02 | 2017-10-27 | 1078.57 | 1078.57
8045 | 473 | 110 |  | 110-00-00001 | SRV521-012100001 | SERVICES FOR ABS TO CERTIFY | 1 | 1 | 2014-01-20 | 21 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 1 | 1 | 483 | 2017-02-10
8045 | 473 | 110 |  | 110-00-00003 | SRV521-031500001 | SURCHARGE FOR HSLA-80 AND HY | 1 | 1 | 2014-01-20 | 20 | 2013-12-31 | LO | 0 | 0 | 1 | No | 2015-04-07 | 2017-10-27 | 1 | 1 | 485 | 2017-08-27
8045 | 473 | 110 |  | 110-00-00087 | 110101-000000004 | FLATBAR, 5" X 3/4" X 20', | 1 | 1 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 0 | 1 | No | 2013-12-02 | 2017-10-27 | 186.02 | 186.02
8045 | 473 | 110 |  | 110-00-MS104 | 16-16M0400340 | TEE MT 4 X 3.25 LB X 40', ST | 6 | 4 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 0 | 4 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8045 | 473 | 110 |  | 110-00-MS207 | 16-16W0600740 | TEE WT 6X7LBX40'ABS GR. AH-3 | 1 | 1 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 0 | 1 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8045 | 473 | 110 |  | 110-00-MS405 | 16-16M0500440 | TEE, MT 5 X 4.5 LB X 40', ST | 2 | 1 | 2014-01-20 | 145 | 2013-08-28 | EA | 0 | 0 | 1 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8045 | 473 | 110 |  | 110-00-WS304 | 16-16M0400340 | TEE, MT 4 X 3.25LB X 40' LON | 136 | 9 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 8 | 1 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8045 | 473 | 110 |  | 110-00-WS605 | 16-16W0500440 | TEE, WT 5 X 4.5LB X 40' LONG | 13 | 8 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 8 | No | 2013-11-19 | 2017-10-27 | 0 | 0
8045 | 473 | 150 |  | 150-00-00012 | 100402-000000006 | PLATE, CRES 2205, 2' X 3' | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 228.19 | 228.19 | 477 | 2016-05-13
8045 | 473 | 150 |  | 150-00-00013 | 100402-000000007 | PLATE, CRES 2205, 1/2, 2 X 3 | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 360.67 | 360.67 | 477 | 2016-05-13
8045 | 473 | 150 |  | 150-00-00014 | 100402-000000010 | PLATE, CRES 2205, 3' X 4' | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 693.82 | 693.82 | 477 | 2016-05-13
8045 | 473 | 150 |  | 150-00-00015 | 100402-000000011 | PLATE, CRES 2205, 3' X 4' | 1 | 1 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 1701.24 | 1701.24 | 477 | 2016-05-13
8045 | 473 | 150 |  | 150-00-00024 | 13-3520200525 | ANGLE, ALUM, GR 5086-H111, | 2 | 2 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 2 | No | 2015-06-12 | 2017-10-27 | 250 | 500 | 485 | 2017-08-28
8045 | 473 | 150 |  | 150-03-D3SD1 | SRV521-030300323 | SRVC TO ASSEMBLE ALUM FND | 1 | 1 | 2014-10-16 | 123 | 2014-06-15 | LO | 0 | 0 | 1 | No | 2014-05-01 | 2017-10-27 | 0 | 0
8045 | 473 | 180 |  | 180-92-00056 | 710114073135-001 | BOLT, 3/4-10 UNC-2A X 6", ST | 18 | 18 | 2014-04-24 | 0 | 2014-04-24 | EA | 0 | 0 | 18 | No | 2017-10-06 | 2017-10-27 | 0 | 0
8045 | 473 | 201 |  | 201-01-00001 | 11-33M050T20-T05 | PLATE, 5' X 8', ALUM GR. 508 | 15 | 15 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 0 | 15 | No | 2016-05-24 | 2017-10-27 | 316.92 | 4753.8 | 475 | 2017-03-24
8045 | 473 | 201 |  | 201-01-00002 | 11-33M060T20-T05 | PLATE, 5' X 8', ALUM GR. 508 | 14 | 14 | 2014-01-20 | 240 | 2013-05-25 | EA | 3 | 0 | 11 | No | 2016-05-24 | 2017-10-27 | 379.66 | 4176.26 | 475 | 2017-03-24
8045 | 473 | 201 |  | 201-01-00003 | 11-33M080T20-T05 | PLATE, 5' X 8', ALUM GR. 508 | 16 | 16 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 0 | 16 | No | 2016-05-24 | 2017-10-27 | 506.77 | 8108.32 | 475 | 2017-03-24
8045 | 473 | 259 |  | 259-05-00466 | 501309-000000001 | TUBE, SQUARE, 6" X 6", 0.250 | 60 | 10 | 2014-01-20 | 56 | 2013-11-25 | LF | 0 | 5 | 10 | No | 2011-03-03 | 2017-10-27 | 10.65 | 106.5
8045 | 473 | 259 |  | 259-05-00S03 | 11-95E040G08 | PLATE, INCONEL 625, ASTM B44 | 1 | 1 | 2014-11-26 | 0 | 2014-11-26 | EA | 0 | 0 | 1 | No | 2014-05-27 | 2017-10-27 | 7425 | 7425
8045 | 473 | 259 |  | 259-05-0550A | 720223-000000007 | EYE ROD, WELDED, 1", STEEL | 8 | 4 | 2014-06-11 | 14 | 2014-05-28 | EA | 0 | 0 | 4 | No | 2014-10-22 | 2017-10-27 | 119 | 476
8045 | 473 | 259 |  | 259-05-22501 | 100401300601-001 | PLATE, 3/8", 4'X8', GR DH36 | 1 | 1 | 2014-03-21 | 180 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2017-06-20 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22503 | 100101240601-001 | SHEET, 1/8" THK, ABS GR DH36 | 0.25 | 0.25 | 2014-03-21 | 180 | 2013-09-22 | EA | 0 | 0 | 0.2 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22506 | 100401280601-001 | PLATE, 1/4" THK, STL, PL, DH | 0.5 | 0.5 | 2014-06-11 | 180 | 2013-12-13 | EA | 0 | 0 | 0.5 | No | 2017-06-20 | 2017-10-27 | 0 | 0
8045 | 473 | 321 |  | 321-99-00146 | 13-3515150225 | ANGLE, AL, 1-1/2 X 1-1/2 X 1 | 3 | 2 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 2 | No | 2015-12-07 | 2017-10-27 | 51.48 | 102.96 | 483 | 2017-05-15
8045 | 473 | 505 |  | 505-01-00002 | 670706080000-Z03 | SHIELD SPRAY, SILICONE COATE | 41 | 41 | 2014-01-20 | 35 | 2013-12-16 | EA | 40 | 0 | 1 | No | 2013-11-08 | 2017-10-27 | 175 | 175
8045 | 473 | 505 |  | 505-01-00003 | 670706080000-Z04 | SPRAY SHIELD - SILICONE COAT | 23 | 12 | 2014-01-20 | 35 | 2013-12-16 | EA | 10 | 0 | 2 | No | 2013-11-08 | 2017-10-27 | 217 | 434
8045 | 473 | 505 |  | 505-01-00115 | 13-3330200420 | ANGLE, ALUMINUM, 3"X2"X0.25" | 1 | 1 | 2014-01-20 | 7 | 2014-01-13 | EA | 0 | 0 | 1 | No | 2017-03-30 | 2017-10-27 | 3236.2 | 3236.2 | 650 | 2014-03-07
8045 | 473 | 505 |  | 505-01-00116 | 11-13M080A01 | PLATE, 8MM X 305MM X 305MM,S | 2 | 2 | 2014-06-24 | 240 | 2013-10-27 | EA | 0 | 0 | 2 | No | 2017-06-13 | 2017-10-27 | 18015 | 36030 | 650 | 2014-03-21
8045 | 473 | 505 |  | 505-01-00501 | 670706080000-Z05 | SILICONE COATED FIBERGLASS O | 6 | 6 | 2014-01-20 | 35 | 2013-12-16 | EA | 5 | 0 | 1 | No | 2013-11-08 | 2017-10-27 | 245 | 245
8045 | 473 | 505 |  | 505-99-PL015 | 11-44E060K08 | PLATE, 3/8" X 5' X 8', SST 3 | 0.11 | 0.11 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 0 | 0.1 | No | 2017-10-02 | 2017-10-27 | 0 | 0
8045 | 473 | 637 |  | 637-03-00004 | 12004-002 | SHEET, 1/8" ALUM, 4' X 8', 5 | 1 | 0 | 2014-01-20 | 30 | 2013-12-21 | EA | 0 | 1 | 1 | No | 2014-02-12 | 2017-10-27 | 194.95 | 194.95 | 361 | 2016-07-14
8045 | 473 | 656 |  | 656-01-00019 | 130202001400-001 | ANGLE, ALUMINUM, 1"X1"X.12"T | 5 | 5 | 2014-10-16 | 7 | 2014-10-09 | EA | 0 | 0 | 5 | No | 2017-08-18 | 2017-10-27 | 9.35 | 46.75 | 450 | 2009-04-16
8045 | 473 | 664 |  | 664-01-00043 | 100103-000000001 | SHEET, AL, 1/8" X 48" X 120" | 0.1 | 0.1 | 2014-01-27 | 180 | 2013-07-31 | EA | 0 | 0 | 0.1 | No | 2017-04-17 | 2017-10-27 | 0 | 0
8045 | 473 | 671 |  | 671-97-00046 | 100403265714-001 | PLATE, 3/16", AL 5456-H116 | 11 | 11 | 2014-08-25 | 180 | 2014-02-26 | SF | 0 | 0 | 11 | No | 2016-10-06 | 2017-10-27 | 468 | 5148 | 450 | 2010-11-12
8045 | 473 | 992 |  | 992-01-00214 | 840000-000000004 | WOOD, 2" X 12" X 12', PINE O | 20 | 20 | 2014-09-15 | 14 | 2014-09-01 | EA | 0 | 0 | 20 | No | 2016-08-29 | 2017-10-27 | 19.5 | 390 | 467 | 2013-03-25
8045 | 473 | 150 |  | 12-33E0404025 | 12-33E0404025 | BAR, FLAT, 4" X 1/4" X 25', | 70 | 56 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 0 | 56 | No | 2013-12-03 | 2017-10-27 | 122.2 | 6843.2
8045 | 473 | 110 |  | 13-1625200320 | 13-1625200320 | ANGLE, 2 1/2" X 2" X 3/16" X | 75 | -15 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 17 | 2 | No | 2013-11-19 | 2017-10-27 | 41.5 | 83
8045 | 473 | 110 |  | 13-1625250420 | 13-1625250420 | ANGLE, 2-1/2" X 2-1/2" X 1/4 | 35 | 2 | 2014-01-20 | 90 | 2013-10-22 | EA | 1 | 0 | 1 | No | 2013-11-19 | 2017-10-27 | 60 | 60
8045 | 473 | 110 |  | 13-1630200320 | 13-1630200320 | ANGLE, 3" X 2" X 3/16" X 20' | 56 | 5 | 2014-01-20 | 123 | 2013-09-19 | EA | 11 | 0 | 5 | No | 2013-11-19 | 2017-10-27 | 46 | 230
8045 | 473 | 110 |  | 13-1630200420 | 13-1630200420 | ANGLE, 3" X 2" X 1/4" X 20', | 53 | 1 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 11 | 12 | No | 2013-11-19 | 2017-10-27 | 56 | 672
8045 | 473 | 110 |  | 13-1630300320 | 13-1630300320 | ANGLE, 3" X 3" X 3/16" X 20' | 21 | 3 | 2014-01-20 | 123 | 2013-09-19 | EA | 1 | 0 | 2 | No | 2013-11-19 | 2017-10-27 | 58.68 | 117.36
8045 | 473 | 110 |  | 13-1640300420 | 13-1640300420 | ANGLE, 4" X 3" X 1/4" X 20' | 40 | 9 | 2014-01-20 | 123 | 2013-09-19 | EA | 6 | 0 | 6 | No | 2013-11-19 | 2017-10-27 | 75 | 450
8045 | 473 | 110 |  | 13-1640400420 | 13-1640400420 | ANGLE, 4" X 4" X 1/4" X ANGL | 4 | 0 | 2014-01-20 | 240 | 2013-05-25 | EA | 0 | 1 | 1 | No | 2013-11-19 | 2017-10-27 | 170.21 | 170.21
8045 | 473 | 110 |  | 13-1640400820 | 13-1640400820 | ANGLE, 4" X 4" X 1/2" X 20', | 12 | 4 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 4 | No | 2013-11-19 | 2017-10-27 | 228 | 912
8045 | 473 | 110 |  | 13-1650300820 | 13-1650300820 | ANGLE, 5" X 3" X 1/2" X 20', | 6 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2013-11-19 | 2017-10-27 | 267.6 | 535.2
8045 | 473 | 110 |  | 13-1650300820 | 13-1650300820 | ANGLE, 5" X 3" X 1/2" X 20', | 6 | 2 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 2 | No | 2013-11-19 | 2017-10-27 | 267.6 | 535.2
8045 | 473 | 150 |  | 13-3320200425 | 13-3320200425 | ANGLE, 2" X 2" X 1/4" X 25', | 67 | 14 | 2014-01-20 | 90 | 2013-10-22 | EA | 0 | 8 | 22 | No | 2013-12-03 | 2017-10-27 | 88.4 | 1944.8
8045 | 473 | 150 |  | 13-3525250425 | 13-3525250425 | ANGLE, 2-1/2" X 2-1/2" X 1/4 | 6 | 4 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 4 | No | 2013-12-03 | 2017-10-27 | 121.25 | 485
8045 | 473 | 110 |  | 15-16W1201440 | 15-16W1201440 | BEAM, 12" X 14# X 40', W SHA | 60 | 21 | 2014-01-20 | 145 | 2013-08-28 | EA | 0 | 0 | 21 | No | 2013-12-03 | 2017-10-27 | 218.51 | 4588.71
8045 | 473 | 110 |  | 15-16W1201640 | 15-16W1201640 | BEAM, 12" X 16# X 40', W SHA | 70 | 6 | 2014-01-20 | 145 | 2013-08-28 | EA | 0 | 0 | 6 | No | 2013-12-03 | 2017-10-27 | 230.4 | 1382.4
8045 | 473 | 110 |  | 18-120006HR12 | 18-120006HR12 | BAR, ROUND, 3/8" DIA, STEEL | 24 | 4 | 2014-01-20 | 15 | 2014-01-05 | LF | 0 | 0 | 4 | No | 2013-11-19 | 2017-10-27 | 0.24 | 0.96
8045 | 473 | 259 |  | 259-05-00551-S00 | -S00 | INSULATING SHEET, THERMICULI | 2 | 2 | 2014-06-11 | 123 | 2014-02-08 | EA | 0 | 0 | 2 | No | 2017-06-14 | 2017-10-27 | 37.04 | 74.08
8045 | 473 | 259 |  | 259-05-22501-S00 | -S00 | PLATE, 3/8", 4'X8', GR DH36 | 0.5 | 0.5 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.5 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22501-S01 | -S00 | PLATE, 3/8", 4'X8', GR DH36 | 0.5 | 0.5 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.5 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22502-S00 | -S00 | PLATE, 1/2", 4'X8', DH36 | 0.5 | 0.5 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.5 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22502-S01 | -S00 | PLATE, 1/2", 4'X8', DH36 | 0.5 | 0.5 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.5 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22503-S00 | -S00 | SHEET, 1/8" THK, ABS GR DH36 | 0.25 | 0.25 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.2 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22506-S00 | -S00 | PLATE, 1/4" THK, STL, PL, DH | 0.25 | 0.25 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.2 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22506-S01 | -S00 | PLATE, 1/4" THK, STL, PL, DH | 0.25 | 0.25 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.2 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22507-S00 | -S00 | PLATE, 13MM THK, 321 CRES,4X | 0.25 | 0.25 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.2 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-05-22508-S00 | -S00 | PLATE, 1/4" THK, 321 CRES,4X | 0.25 | 0.25 | 2014-01-20 | 180 | 2013-07-24 | EA | 0 | 0 | 0.2 | No | 2017-06-21 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-07-00S01-S00 | -S00 | PLATE, CRES 321, 3/8"THK | 0.5 | 0.5 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 0.5 | No | 2017-06-14 | 2017-10-27 | 0 | 0
8045 | 473 | 259 |  | 259-07-00S01-S01 | -S00 | PLATE, CRES 321, 3/8"THK | 0.5 | 0.5 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 0.5 | No | 2017-06-12 | 2017-10-27 | 0 | 0
8045 | 473 | 581 |  | 581-01-00010-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-02-26 | 60 | 2014-12-28 | LO | 0 | 0 | 1 | No | 2014-05-15 | 2017-10-27 | 0 | 0 | 485 | 2017-06-09
8048 | 473 | 256 |  | 256-01-V0039 | 522013130731-002 | VALVE, GLOBE, 1/2" IPS, BRON | 12 | 2 | 2014-06-11 | 90 | 2014-03-13 | EA | 0 | 0 | 2 | No | 2013-10-14 | 2017-10-27 | 130 | 260
8048 | 473 | 261 |  | 261-01-V0045 | 520128150033-001 | VALVE, BALL, 1/4", SSTL BODY | 4 | 4 | 2014-04-10 | 180 | 2013-10-12 | EA | 2 | 0 | 2 | No | 2015-11-17 | 2017-10-27 | 630 | 1260
8048 | 473 | 262 |  | 262-01-V0084 | 520128150033-001 | VALVE, BALL, 1/4" IPS, SS BO | 2 | 2 | 2014-09-15 | 180 | 2014-03-19 | EA | 0 | 0 | 2 | No | 2016-03-30 | 2017-10-27 | 436 | 872 | 475 | 2017-09-15
8048 | 473 | 262 |  | 262-01-V0087 | 520128150033-006 | VALVE, BALL, 1-1/2" IPS, SST | 2 | 2 | 2014-09-15 | 180 | 2014-03-19 | EA | 0 | 0 | 2 | No | 2016-03-30 | 2017-10-27 | 1268 | 2536 | 485 | 2017-09-15
8048 | 473 | 262 |  | 262-01-V0089 | 520120290017-009 | VALVE, BALL, 3" IPS, CS BODY | 6 | 6 | 2014-09-15 | 180 | 2014-03-19 | EA | 0 | 0 | 6 | No | 2015-11-17 | 2017-10-27 | 3705 | 22230 | 485 | 2017-09-15
8048 | 473 | 304 |  | 304-00-00002 | 301306010101-001 | CABLE, ELECTRIC, 2XSAOW-3 | 1051 | 1051 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 1 | 1050 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00003 | 301314010101-001 | CABLE, ELECTRIC, 2XSAOW-7 | 280 | 280 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 1 | 279 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00004 | 308401151814-155 | CABLE, ELECTRIC, COAXIAL | 50 | 50 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 0 | 50 | No | 2016-03-04 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00007 | 301909010101-001 | CABLE, ELECTRIC, 3XSOW-3 | 100 | 100 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 1 | 99 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00009 | 302207020101-001 | CABLE, ELECTRIC, 7XW-3 | 870 | 297 | 2014-01-20 | 160 | 2013-08-13 | LF | 277 | 0 | 20 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00013 | 309804001400-001 | CABLE, FIBER OPTIC, M85045/1 | 40000 | 40000 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 37500 | 2500 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00019 | 302902020101-002 | CABLE, ELECTRIC, DXW-4, | 1213 | 1213 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 1200 | 13 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00025 | 304702080101-003 | CABLE, ELECTRIC, LS2SJ-20, | 1630 | 1055 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 0 | 1055 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00070 | 306602090102-003 | CABLE, ELECTRIC, LSDSGU-9, | 230 | 230 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 1 | 229 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00111 | 308103080102-003 | CABLE, ELECTRIC, LSTNW-9 | 70 | 70 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 0 | 70 | No | 2014-02-11 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00114 | 308303080102-004 | CABLE, ELECTRIC, LSTSGU-14, | 560 | 560 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 390 | 170 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00138 | 301L03020101-001 | CABLE, ELECTRIC, TXOW-3, | 824 | 824 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 650 | 174 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00148 | 303804020101-001 | CABLE, ELECTRIC, FXOW-3, | 180 | 180 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 1 | 179 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00180 | 304906200101-001 | CABLE, ELECTRIC, LS2SUS-3, | 2820 | 2820 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 2546 | 274 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00185 | 301514010101-001 | CABLE, ELECTRIC, 2XSOW-7 | 620 | 620 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 1 | 619 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00196 | 309001141008-001 | CABLE, ELECTRIC, M17/183-000 | 650 | 650 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 1 | 649 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00234 | 302301040300-001 | CABLE, HELIAX, AVA5RK-50, | 1562 | 385 | 2014-01-20 | 160 | 2013-08-13 | LF | 293 | 0 | 92 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00327 | 304702080101-002 | CABLE, ELECTRIC, LS2SJ-12, | 300 | 300 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 1 | 299 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00338 | 302409140500-001 | CABLE, ELECTRIC, CSLSZH09 | 32 | 32 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 0 | 32 | No | 2014-02-11 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00368 | 308401041006-228 | CABLE, ELECTRIC, M17/229-000 | 262 | 262 | 2014-01-20 | 123 | 2013-09-19 | LF | 0 | 0 | 262 | No | 2015-03-20 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-00-00375 | 303Y05080100-001 | CABLE, ELECTRIC, LSMMOP-5 | 8 | 8 | 2014-10-10 | 160 | 2014-05-03 | FT | 0 | 0 | 8 | No | 2017-09-11 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-01-00003 | 301314010101-001 | CABLE, ELECTRIC, 2XSAOW-7 | 2226 | 354 | 2014-01-20 | 40 | 2013-12-11 | FT | 178 | 0 | 176 | No | 2014-02-11 | 2017-10-27 | 2.68 | 471.68
8048 | 473 | 304 |  | 304-01-00009 | 302207020101-001 | CABLE, ELECTRIC, 7XW-3 | 2444 | 44 | 2014-01-20 | 40 | 2013-12-11 | LF | 0 | 0 | 44 | No | 2014-04-17 | 2017-10-27 | 2.15 | 94.6
8048 | 473 | 304 |  | 304-01-00013 | 309804001400-001 | CABLE, FIBER OPTIC | 9576 | 205 | 2014-01-20 | 120 | 2013-09-22 | LF | 0 | 0 | 205 | No | 2014-02-11 | 2017-10-27 | 2.31 | 473.55
8048 | 473 | 304 |  | 304-01-00021 | 303704010101-001 | CABLE, ELECTRIC, FX-3 | 10333 | 873 | 2014-01-20 | 40 | 2013-12-11 | FT | 0 | 0 | 873 | No | 2014-02-11 | 2017-10-27 | 0.59 | 515.07
8048 | 473 | 304 |  | 304-01-00025 | 304702080101-003 | ELEC CABLE,LS2SJ-20, LOW SMO | 550 | 200 | 2014-01-20 | 84 | 2013-10-28 | LF | 0 | 0 | 200 | No | 2014-02-21 | 2017-10-27 | 1.01 | 202
8048 | 473 | 304 |  | 304-01-00036 | 305621080101-001 | CABLE, LS3SWUS-7 | 355 | 80 | 2014-01-20 | 140 | 2013-09-02 | LF | 0 | 0 | 80 | No | 2014-02-11 | 2017-10-27 | 7.59 | 607.2
8048 | 473 | 304 |  | 304-01-00036 | 305621080101-001 | CABLE, LS3SWUS-7 | 355 | 80 | 2014-01-20 | 140 | 2013-09-02 | LF | 0 | 0 | 80 | No | 2014-02-11 | 2017-10-27 | 7.59 | 607.2
8048 | 473 | 304 |  | 304-01-00060 | 306402200102-003 | CABLE, ELECTRICAL, LSDNW-9, | 1886 | 195 | 2014-01-20 | 40 | 2013-12-11 | FT | 9 | 0 | 186 | No | 2014-02-11 | 2017-10-27 | 1.41 | 262.26
8048 | 473 | 304 |  | 304-01-00067 | 306602200102-002 | CABLE,ELEC,LSDSGU-4, LOW SMO | 2922 | 147 | 2014-01-20 | 80 | 2013-11-01 | FT | 125 | 0 | 22 | No | 2014-02-11 | 2017-10-27 | 0.78 | 17.16
8048 | 473 | 304 |  | 304-01-00070 | 306602090102-003 | CABLE,ELEC,LSDSGU-9, LOW SMO | 6958 | 213 | 2014-01-20 | 40 | 2013-12-11 | LF | 155 | 0 | 58 | No | 2014-02-11 | 2017-10-27 | 1.141 | 66.178
8048 | 473 | 304 |  | 304-01-00072 | 303B04200101-003 | ELEC CABLE, LSFHOF-9, LOW SM | 250 | 250 | 2014-01-20 | 40 | 2013-12-11 | LF | 175 | 0 | 75 | No | 2014-07-23 | 2017-10-27 | 2.11 | 158.25
8048 | 473 | 304 |  | 304-01-00076 | 306704200102-004 | CABLE, ELECTRICAL, LSFNW-23, | 519 | 140 | 2014-01-20 | 84 | 2013-10-28 | FT | 121 | 0 | 19 | No | 2014-02-11 | 2017-10-27 | 3.35 | 63.65
8048 | 473 | 304 |  | 304-01-00085 | 306904200102-006 | CABLE,ELEC,LSFSGU-75,LOW SMO | 150 | 150 | 2014-01-20 | 40 | 2013-12-11 | LF | 25 | 0 | 125 | No | 2014-02-11 | 2017-10-27 | 14.68 | 1835
8048 | 473 | 304 |  | 304-01-00094 | 308003200101-001 | ELEC CABLE,LSTHOF-3, LOW SMO | 125 | 25 | 2014-01-20 | 40 | 2013-12-11 | LF | 0 | 0 | 25 | No | 2014-02-11 | 2017-10-27 | 0.96 | 24
8048 | 473 | 304 |  | 304-01-00100 | 308103200102-008 | CABLE, ELECTRICAL, LSTNW-100 | 160 | 85 | 2014-01-20 | 80 | 2013-11-01 | FT | 40 | 0 | 45 | No | 2014-02-23 | 2017-10-27 | 11.52 | 518.4
8048 | 473 | 304 |  | 304-01-00101 | 308103080102-004 | CABLE, ELECTRICAL, LSTNW-14, | 1290 | 812 | 2014-01-20 | 84 | 2013-10-28 | FT | 22 | 0 | 790 | No | 2014-05-16 | 2017-10-27 | 2.15 | 1698.5
8048 | 473 | 304 |  | 304-01-00109 | 308103200102-006 | CABLE, ELECTRICAL, LSTNW-50, | 2850 | 100 | 2014-01-20 | 84 | 2013-10-28 | FT | 0 | 0 | 100 | No | 2014-02-23 | 2017-10-27 | 5.114 | 511.4
8048 | 473 | 304 |  | 304-01-00111 | 308103080102-003 | CABLE, ELECTRICAL, LSTNW-9, | 4300 | 264 | 2014-01-20 | 40 | 2013-12-11 | FT | 214 | 0 | 50 | No | 2014-02-23 | 2017-10-27 | 1.66 | 83
8048 | 473 | 304 |  | 304-01-00118 | 308303200102-001 | ELEC CABLE,LSTSGU-3, LOW SMO | 380 | 105 | 2014-01-20 | 84 | 2013-10-28 | FT | 0 | 0 | 105 | No | 2014-02-23 | 2017-10-27 | 0.9 | 94.5
8048 | 473 | 304 |  | 304-01-00120 | 308303200102-002 | CABLE,ELEC,LSTSGU-4, LOW SMO | 1689 | 223 | 2014-01-20 | 40 | 2013-12-11 | FT | 164 | 0 | 59 | No | 2014-02-23 | 2017-10-27 | 0.82 | 48.38
8048 | 473 | 304 |  | 304-01-00122 | 308303200102-008 | CABLE,ELEC,LSTSGU-50,LOW SMO | 13881 | 6799 | 2014-01-20 | 80 | 2013-11-01 | FT | 6508 | 0 | 291 | No | 2014-02-23 | 2017-10-27 | 6.24 | 1815.84
8048 | 473 | 304 |  | 304-01-00124 | 308303080102-003 | CABLE,ELEC,LSTSGU-9, LOW SMO | 12850 | 307 | 2014-01-20 | 40 | 2013-12-11 | FT | 117 | 0 | 190 | No | 2014-02-23 | 2017-10-27 | 1.93 | 366.7
8048 | 473 | 304 |  | 304-01-00132 | 301K03010101-001 | CABLE, ELECTRIC, TX-3 | 16898 | 763 | 2014-01-20 | 40 | 2013-12-11 | FT | 0 | 0 | 763 | No | 2014-02-23 | 2017-10-27 | 0.44 | 335.72
8048 | 473 | 304 |  | 304-01-00133 | 301K03010101-002 | CABLE, ELECTRIC, TX-4 | 9550 | 450 | 2014-01-20 | 40 | 2013-12-11 | FT | 0 | 0 | 450 | No | 2014-02-23 | 2017-10-27 | 0.94 | 423
8048 | 473 | 304 |  | 304-01-00138 | 301L03020101-001 | CABLE ELEC TXOW-3 WTRTT 16 A | 26911 | 355 | 2014-01-20 | 40 | 2013-12-11 | FT | 0 | 0 | 355 | No | 2014-05-15 | 2017-10-27 | 1.12 | 397.6
8048 | 473 | 304 |  | 304-01-00139 | 302802020101-001 | CABLE, ELECTRIC, DXOW-3 | 16875 | 2375 | 2014-01-20 | 40 | 2013-12-11 | LF | 0 | 0 | 2375 | No | 2014-02-23 | 2017-10-27 | 1.05 | 2493.75
8048 | 473 | 304 |  | 304-01-00141 | 301602010101-001 | CABLE, ELECTRICAL, 2XSW-1, | 94300 | 249 | 2014-01-20 | 84 | 2013-10-28 | FT | 75 | 0 | 174 | No | 2014-02-23 | 2017-10-27 | 0.39 | 67.86
8048 | 473 | 304 |  | 304-01-00151 | 306904090102-002 | ELEC CABLE, LSFSGU-23,LOW SM | 60 | 60 | 2014-01-20 | 80 | 2013-11-01 | LF | 0 | 0 | 60 | No | 2014-02-23 | 2017-10-27 | 3.59 | 215.4 | 471 | 2015-01-06
8048 | 473 | 304 |  | 304-01-00154 | 307202202000-001 | CABLE, ELECTRIC, LSMRI-D-1 | 500 | 202 | 2014-01-20 | 160 | 2013-08-13 | LF | 52 | 0 | 150 | No | 2014-02-23 | 2017-10-27 | 0.31 | 46.5
8048 | 473 | 304 |  | 304-01-00166 | 303804020101-002 | CABLE, ELECTRIC, FXOW-4 | 22500 | 3536 | 2014-01-20 | 40 | 2013-12-11 | FT | 1156 | 198 | 2182 | No | 2014-02-23 | 2017-10-27 | 0.2723 | 594.1586
8048 | 473 | 304 |  | 304-01-00168 | 301104010101-002 | CABLE, ELECTRIC, 2XAO-2, | 140 | 140 | 2014-01-20 | 120 | 2013-09-22 | FT | 0 | 0 | 140 | No | 2017-10-05 | 2017-10-27 | 0.89 | 124.6 | 450 | 2009-04-16
8048 | 473 | 304 |  | 304-01-00169 | 301114010101-001 | CABLE, ELECTRIC, 2XAO-7 | 400 | 50 | 2014-01-20 | 40 | 2013-12-11 | LF | 0 | 0 | 50 | No | 2014-02-23 | 2017-10-27 | 1.66 | 83
8048 | 473 | 304 |  | 304-01-00175 | 301406010101-001 | CABLE, ELECTRICAL, 2XSO-3, | 3111 | 111 | 2014-01-20 | 84 | 2013-10-28 | LF | 0 | 0 | 111 | No | 2014-02-23 | 2017-10-27 | 1.22 | 135.42
8048 | 473 | 304 |  | 304-01-00181 | 307307201002-001 | ELEC CABLE,LSMSCS-7 LOW SMOK | 1250 | 450 | 2014-01-20 | 84 | 2013-10-28 | LF | 385 | 0 | 65 | No | 2014-02-23 | 2017-10-27 | 3.59 | 233.35
8048 | 473 | 304 |  | 304-01-00193 | 309907020101-001 | CABLE, ELECTRICAL, MXCOW-7, | 6200 | 1200 | 2014-01-20 | 60 | 2013-11-21 | LF | 0 | 0 | 1200 | No | 2014-02-23 | 2017-10-27 | 2.05 | 2460
8048 | 473 | 304 |  | 304-01-00199 | 301606010101-001 | CABLE, ELECTRICAL, 2XSW-3, | 12410 | 314 | 2014-01-20 | 84 | 2013-10-28 | LF | 179 | 0 | 135 | No | 2014-02-23 | 2017-10-27 | 1.39 | 187.65
8048 | 473 | 304 |  | 304-01-00206 | 301560010101-001 | CABLE, ELECTRICAL, 2XSOW-30, | 350 | 195 | 2014-01-20 | 60 | 2013-11-21 | LF | 185 | 0 | 10 | No | 2014-02-23 | 2017-10-27 | 14.94 | 149.4
8048 | 473 | 304 |  | 304-01-00211 | 302802020101-002 | CABLE, ELEC, DXOW-4, WTRTT, | 17410 | 678 | 2014-01-20 | 40 | 2013-12-11 | FT | 0 | 0 | 678 | No | 2014-02-23 | 2017-10-27 | 1.24 | 840.72
8048 | 473 | 304 |  | 304-01-00220 | 304401040500-001 | CABLE, HELIAX, LDF4RN-50A | 100 | 25 | 2014-01-20 | 80 | 2013-11-01 | FT | 0 | 0 | 25 | No | 2014-02-23 | 2017-10-27 | 2.71 | 67.75
8048 | 473 | 304 |  | 304-01-00227 | 301C37010101-001 | CABLE, ELECTRIC, MXSO-37 | 45 | 10 | 2014-01-20 | 40 | 2013-12-11 | LF | 5 | 0 | 5 | No | 2014-05-21 | 2017-10-27 | 9.953 | 49.765
8048 | 473 | 304 |  | 304-01-00240 | 306402200102-004 | CABLE, ELECTRICAL, LSDNW-14, | 860 | 152 | 2014-01-20 | 84 | 2013-10-28 | FT | 17 | 0 | 135 | No | 2012-05-22 | 2017-10-27 | 1.17 | 157.95
8048 | 473 | 304 |  | 304-01-00266 | 302021010101-001 | CABLE, ELECTRIC 3XSW-7 | 560 | 375 | 2014-01-20 | 160 | 2013-08-13 | LF | 325 | 0 | 50 | No | 2012-10-26 | 2017-10-27 | 5.47 | 273.5
8048 | 473 | 304 |  | 304-01-00278 | 308901140113-001 | CABLE, ELECTRIC, M17/189-000 | 25 | 25 | 2014-01-20 | 160 | 2013-08-13 | LF | 5 | 0 | 20 | No | 2012-12-13 | 2017-10-27 | 2.2 | 44
8048 | 473 | 304 |  | 304-01-00279 | 307502030115-001 | CABLE, PROFIBUS LSPB2SDOSW-1 | 23520 | 6260 | 2014-01-20 | 120 | 2013-09-22 | FT | 4045 | 0 | 2215 | No | 2012-05-22 | 2017-10-27 | 2.72 | 6024.8
8048 | 473 | 304 |  | 304-01-00284 | 309924020101-001 | CABLE, ELECTRIC, MXCOW-24 | 1885 | 35 | 2014-01-20 | 120 | 2013-09-22 | LF | 0 | 0 | 35 | No | 2012-05-22 | 2017-10-27 | 6.58 | 230.3
8048 | 473 | 304 |  | 304-01-00301 | 301002010101-001 | CABLE, ELECTRIC, 1XSOW-2 | 160 | 60 | 2014-01-20 | 90 | 2013-10-22 | FT | 0 | 0 | 60 | No | 2012-05-22 | 2017-10-27 | 1.22 | 73.2
8048 | 473 | 304 |  | 304-01-00305 | 307806090800-001 | CABLE, ELECTRIC, LSTCJX-3 | 750 | 750 | 2014-01-20 | 90 | 2013-10-22 | FT | 0 | 0 | 750 | No | 2016-06-17 | 2017-10-27 | 13.8 | 10350 | 481 | 2017-09-11
8048 | 473 | 304 |  | 304-01-00333 | 306602200102-006 | CABLE, LSDSGU-50 | 290 | 290 | 2014-01-20 | 80 | 2013-11-01 | FT | 0 | 0 | 290 | No | 2012-05-22 | 2017-10-27 | 5.28 | 1531.2 | 479 | 2017-09-11
8048 | 473 | 304 |  | 304-01-00336 | 301J04010101-001 | CABLE, ELECTRIC, TTXSO-2, 2 | 450 | 25 | 2014-01-20 | 100 | 2013-10-12 | FT | 0 | 0 | 25 | No | 2012-05-22 | 2017-10-27 | 1.62 | 40.5
8048 | 473 | 304 |  | 304-01-00337 | 305220080103-001 | CABLE, LS2U-10 | 732 | 642 | 2014-01-20 | 84 | 2013-10-28 | LF | 145 | 0 | 497 | No | 2012-10-26 | 2017-10-27 | 2.29 | 1138.13
8048 | 473 | 304 |  | 304-01-00352 | 306502090102-006 | CABLE, ELECTRIC, LS2OW-50 | 250 | 135 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 0 | 135 | No | 2012-05-22 | 2017-10-27 | 8.02 | 1082.7
8048 | 473 | 304 |  | 304-01-00353 | 304928200101-004 | CABLE, ELECTRIC, LS2SUS-14 | 276 | 12 | 2014-01-20 | 160 | 2013-08-13 | LF | 11 | 0 | 1 | No | 2012-05-22 | 2017-10-27 | 8.69 | 8.69
8048 | 473 | 304 |  | 304-01-00373 | 302X02040503-001 | CABLE, FOUR-CONDUCTOR, SHIEL | 100 | 100 | 2014-01-20 | 42 | 2013-12-09 | FT | 0 | 0 | 100 | No | 2017-06-01 | 2017-10-27 | 7.88 | 788 | 481 | 2017-09-11
8048 | 473 | 304 |  | 304-01-00374 | 302V01200101-006 | CABLE, LOW-SMOKE, ZERO-HALOG | 300 | 300 | 2014-01-20 | 42 | 2013-12-09 | FT | 0 | 0 | 300 | No | 2017-06-01 | 2017-10-27 | 4.12 | 1236 | 477 | 2017-05-05
8048 | 473 | 304 |  | 304-01-00503 | 305303200102-005 | CABLE, LS3OW-23 | 360 | 360 | 2014-01-20 | 42 | 2013-12-09 | FT | 0 | 0 | 360 | No | 2017-05-19 | 2017-10-27 | 5.03 | 1810.8 | 477 | 2017-09-11
8048 | 473 | 304 |  | 304-01-00509 | 306402200102-007 | CABLE, ELECTRICAL, LSDNW-75 | 250 | 250 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 0 | 250 | No | 2017-05-18 | 2017-10-27 | 5.59 | 1397.5 | 479 | 2017-09-11
8048 | 473 | 304 |  | 304-01-00510 | 306502090102-007 | CABLE, ELECTRICAL, LS20W-75 | 100 | 100 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 0 | 100 | No | 2017-05-18 | 2017-10-27 | 9.84 | 984 | 479 | 2017-09-11
8048 | 473 | 304 |  | 304-01-00511 | 306602090102-005 | CABLE, ELECTRICAL, LSDSGU-75 | 1075 | 1075 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 0 | 1075 | No | 2017-05-18 | 2017-10-27 | 8.45 | 9083.75 | 479 | 2017-09-11
8048 | 473 | 304 |  | 304-51-00809 | 300000-000003009 | KIT, CABLE, LCS CHANGE NOTIC | 1 | 1 | 2014-07-08 | 42 | 2014-05-27 | EA | 0 | 0 | 1 | No | 2016-05-11 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-51-00813 | 300000-000003008 | KIT, CABLE, LCS CHANGE NOTIC | 1 | 1 | 2014-07-08 | 42 | 2014-05-27 | EA | 0 | 0 | 1 | No | 2016-05-11 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-51-00813 | 300000-000003008 | KIT, CABLE, LCS CHANGE NOTIC | 1 | 1 | 2014-07-08 | 42 | 2014-05-27 | EA | 0 | 0 | 1 | No | 2016-05-11 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-51-00816 | 300000-000003017 | KIT, CABLE, LCS CHANGE NOTIC | 1 | 1 | 2014-07-08 | 42 | 2014-05-27 | EA | 0 | 0 | 1 | No | 2016-05-20 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-51-00818 | 300000-000003099 | KIT, CABLE - LCS CHANGE NOTI | 1 | 1 | 2014-07-08 | 160 | 2014-01-29 | LF | 0 | 0 | 1 | No | 2016-06-15 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-51-00819 | 300000-000003100 | KIT, CABLE - LCS CHANGE NOTI | 1 | 1 | 2014-07-08 | 160 | 2014-01-29 | LF | 0 | 0 | 1 | No | 2016-06-15 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-51-00820 | 300000-000003101 | KIT, CABLE - LCS CHANGE NOTI | 1 | 1 | 2014-07-08 | 160 | 2014-01-29 | LF | 0 | 0 | 1 | No | 2016-06-15 | 2017-10-27 | 0 | 0
8048 | 473 | 304 |  | 304-51-00821 | 300000-000003102 | KIT, CABLE - LCS CHANGE NOTI | 1 | 1 | 2014-07-08 | 160 | 2014-01-29 | LF | 0 | 0 | 1 | No | 2016-06-15 | 2017-10-27 | 0 | 0
8048 | 473 | 432 |  | 432-01-00015 | 370400000005-002 | HANDSET, COMMUNICATION EQUIP | 10 | 2 | 2014-10-10 | 60 | 2014-08-11 | EA | 0 | 0 | 2 |  | 2014-02-07 | 2017-10-27 | 1523 | 3046
8048 | 473 | 505 |  | 505-01-00010 | 807234-000000001 | VITON PER MIL-R-83248 TYPE I | 102 | 102 | 2014-01-20 | 30 | 2013-12-21 | LF | 100 | 0 | 2 | No | 2013-11-08 | 2017-10-27 | 5.44 | 10.88
8048 | 473 | 505 |  | 505-03-K0002 | 810116171100-04G | GASKET, GARLOCK G9900, HIGH | 7 | 2 | 2014-03-07 | 28 | 2014-02-07 | EA | 0 | 0 | 2 | No | 2013-11-19 | 2017-10-27 | 11.72 | 23.44
8048 | 473 | 505 |  | 505-03-K9098 | 810100191900-007 | GASKET, 2" SPIRAL WOUND | 4 | 2 | 2014-09-08 | 60 | 2014-07-10 | EA | 0 | 0 | 2 | No | 2015-08-14 | 2017-10-27 | 8.9 | 17.8
8048 | 473 | 505 |  | 505-03-K9153 | 810112182100-00A | GASKET, RING TYPE, DN100, PN | 16 | 16 | 2014-01-20 | 45 | 2013-12-06 | EA | 0 | 0 | 16 | No | 2016-07-12 | 2017-10-27 | 2.83 | 45.28 | 481 | 2017-05-04
8048 | 473 | 506 |  | 506-01-V0913 | 521907280002-006 | VALVE, QUICK ACTING, SELF CL | 29 | 14 | 2014-03-28 | 84 | 2014-01-03 | EA | 0 | 0 | 14 | No | 2013-10-16 | 2017-10-27 | 205 | 2870
8048 | 473 | 512 |  | 512-88-01591 | 681200000300-001 | PROBE, STATIC PRESSURE | 6 | 6 | 2014-08-18 | 105 | 2014-05-05 | EA | 0 | 0 | 6 | No | 2017-06-19 | 2017-10-27 | 0 | 0
8048 | 473 | 514 |  | 514-01-V0016 | 520914282512-00B | VALVE, BTRFLY, 5 IPS, BRONZE | 13 | 1 | 2014-06-18 | 90 | 2014-03-20 | EA | 0 | 0 | 1 | No | 2013-09-16 | 2017-10-27 | 217 | 217
8048 | 473 | 514 |  | 514-01-V0101 | 521707240025-002 | VALVE, GATE, 1/2" | 58 | 5 | 2014-04-17 | 84 | 2014-01-23 | EA | 0 | 0 | 5 | No | 2013-10-16 | 2017-10-27 | 26.5 | 132.5
8048 | 473 | 526 |  | 526-01-V0001 | 521607040612-009 | VALVE, GAGGED SCUPPER, 3" IP | 7 | 1 | 2014-05-28 | 90 | 2014-02-27 | EA | 0 | 0 | 1 | No | 2013-10-17 | 2017-10-27 | 955 | 955
8048 | 473 | 533 |  | 533-01-V0005 | 522304000207-002 | VALVE, GLOBE STOP, 1/2" F.I. | 23 | 1 | 2014-07-29 | 90 | 2014-04-30 | EA | 0 | 0 | 1 | No | 2013-10-17 | 2017-10-27 | 13.25 | 13.25
8048 | 473 | 542 |  | 542-01-V9002 | 521713130127-002 | VALVE, GATE,1/2" IPS, 400 PS | 15 | 1 | 2014-05-01 | 120 | 2014-01-01 | EA | 0 | 0 | 1 | No | 2013-10-18 | 2017-10-27 | 285 | 285
8048 | 473 | 551 |  | 551-01-V0003 | 522016210730-002 | VALVE, GLOBE, 1/2", NICKEL | 50 | 12 | 2014-03-28 | 90 | 2013-12-28 | EA | 0 | 0 | 12 | No | 2013-10-23 | 2017-10-27 | 616.95 | 7403.4
8048 | 473 | 551 |  | 551-01-V0082 | 522213130730-002 | VALVE, GLOBE STOP CH, 1/2" I | 9 | 2 | 2014-06-18 | 180 | 2013-12-20 | EA | 0 | 0 | 2 | No | 2014-07-17 | 2017-10-27 | 265 | 530
8048 | 473 | 555 |  | 555-02-V012A | 520123150033-006 | VALVE, BALL, 1-1/2"IPS, | 22 | 2 | 2014-05-28 | 90 | 2014-02-27 | EA | 0 | 0 | 2 | No | 2013-10-24 | 2017-10-27 | 1010 | 2020
8048 | 473 | 555 |  | 555-02-V9000 | 521713130127-00H | VALVE, GATE, 3/8" IPS, 400 P | 12 | 4 | 2014-01-20 | 180 | 2013-07-24 | EA | 2 | 0 | 2 | No | 2014-03-14 | 2017-10-27 | 215 | 430
8048 | 473 | 555 |  | 555-02-V9002 | 521713130127-002 | VALVE, GATE,1/2" IPS, 400 PS | 48 | 1 | 2014-01-20 | 120 | 2013-09-22 | EA | 0 | 0 | 1 | No | 2013-10-24 | 2017-10-27 | 285 | 285
8048 | 473 | 565 |  | 565-02-00020 | 201800010000-002 | MOUNT RESILIENT, TYPE 7E450 | 4 | 4 | 2014-12-09 | 60 | 2014-10-10 | EA | 0 | 0 | 4 | No | 2016-02-24 | 2017-10-27 | 153.67 | 614.68 | 483 | 2017-04-05
8048 | 473 | 602 |  | 602-02-00011 | 790300-000000003 | SHIP DATA PLAQUE, 467W X 305 | 1 | 1 | 2014-06-04 | 14 | 2014-05-21 | EA | 0 | 0 | 1 | No | 2015-09-30 | 2017-10-27 | 1345 | 1345 | 469 | 2017-10-25
8048 | 473 | 602 |  | 602-02-00012 | 790300-000000002 | SHIP DATA PLAQUE, 406W X 230 | 1 | 1 | 2014-07-08 | 14 | 2014-06-24 | EA | 0 | 0 | 1 | No | 2015-09-30 | 2017-10-27 | 995 | 995 | 469 | 2017-10-25
8048 | 473 | 651 |  | 651-01-00131 | 712400-000000003 | STUD, WELD, 1/2"-13UNC, CRES | 4 | 4 | 2014-01-20 | 14 | 2014-01-06 | EA | 0 | 0 | 4 | No | 2014-12-03 | 2017-10-27 | 16 | 64 | 465 | 2014-06-05
8048 | 473 | 256 |  | 256-01-V699A-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 475 | 2016-03-15
8048 | 473 | 259 |  | 259-01-00001-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-03-28 | 123 | 2013-11-25 | LO | 0 | 0 | 1 | No | 2013-08-29 | 2017-10-27 | 0 | 0
8048 | 473 | 259 |  | 259-05-22020-S00 | -S00 | GASKET, 6" IPS, FLEXITALIC | 2 | 2 | 2014-03-07 | 45 | 2014-01-21 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 482.1 | 964.2
8048 | 473 | 259 |  | 259-05-22020-S01 | -S00 | GASKET, 6" IPS, FLEXITALIC | 2 | 2 | 2014-03-07 | 45 | 2014-01-21 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 482.1 | 964.2
8048 | 473 | 259 |  | 259-05-22021-S00 | -S00 | GASKET, 8" IPS, FLEXITALIC | 2 | 2 | 2014-03-07 | 45 | 2014-01-21 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 715.68 | 1431.36
8048 | 473 | 259 |  | 259-05-22021-S01 | -S00 | GASKET, 8" IPS, FLEXITALIC | 2 | 2 | 2014-03-07 | 45 | 2014-01-21 | EA | 0 | 0 | 2 | No | 2017-06-21 | 2017-10-27 | 715.68 | 1431.36
8048 | 473 | 259 |  | 259-05-22025-S00 | -S00 | INSULATING SHEET, THERMICULI | 2 | 2 | 2014-03-07 | 45 | 2014-01-21 | EA | 0 | 0 | 2 | No | 2017-10-16 | 2017-10-27 | 25.25 | 50.5
8048 | 473 | 259 |  | 259-05-22034-S00 | -S00 | GASKET, BOLT SIZE 3/4", 321S | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-27 | 2017-10-27 | 246.48 | 492.96
8048 | 473 | 259 |  | 259-05-22034-S01 | -S00 | GASKET, BOLT SIZE 3/4", 321S | 2 | 2 | 2014-03-21 | 123 | 2013-11-18 | EA | 0 | 0 | 2 | No | 2017-06-27 | 2017-10-27 | 246.48 | 492.96
8048 | 473 | 261 |  | 261-01-V0006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-28 | 60 | 2014-01-27 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 475 | 2015-03-05
8048 | 473 | 261 |  | 261-01-V0010-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0 | 475 | 2015-03-05
8048 | 473 | 261 |  | 261-01-V0014-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | EA | 0 | 0 | 1 | No | 2014-02-14 | 2017-10-27 | 0 | 0
8048 | 473 | 261 |  | 261-01-V0055-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-01 | 60 | 2014-03-02 | EA | 0 | 0 | 1 | No | 2017-09-05 | 2017-10-27 | 0 | 0
8048 | 473 | 262 |  | 262-01-VPR02-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0 | 481 | 2017-04-18
8048 | 473 | 437 |  | 437-05-00201-S03 | -S00 | MODIFY AFFF PUSHBUTTON STATI | 1 | 1 | 2017-04-05 | 123 | 2016-12-03 | EA | 0 | 0 | 1 | No | 2017-04-05 | 2017-04-05 | 0 | 0
8048 | 473 | 504 |  | 504-01-V0211-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2016-02-26 | 2017-10-27 | 0 | 0 | 483 | 2017-08-24
8048 | 473 | 504 |  | 504-01-V0700-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-04-29 | 2017-10-27 | 0 | 0 | 483 | 2017-08-24
8048 | 473 | 505 |  | 505-01-VF002-S00 | -S00 | VALVE FND, MFG IAW, 3", STEE | 1 | 1 | 2014-03-07 | 123 | 2013-11-04 | EA | 0 | 0 | 1 | No | 2017-05-01 | 2017-10-27 | 68.52 | 68.52
8048 | 473 | 506 |  | 506-01-V0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8048 | 473 | 512 |  | 512-01-V0166-L06 | -L06 | REPORT, IN-PLANT TEST | 1 | 1 | 2014-08-04 | 60 | 2014-06-05 | LO | 0 | 0 | 1 | No | 2013-04-30 | 2017-10-27 | 0 | 0 | 469 | 2012-05-23
8048 | 473 | 514 |  | 514-01-V0012-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2014-04-30 | 2017-10-27 | 0 | 0 | 477 | 2015-04-08
8048 | 473 | 514 |  | 514-01-V0044-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-02-05 | 60 | 2014-12-07 | EA | 0 | 0 | 1 | No | 2013-10-16 | 2017-10-27 | 0 | 0
8048 | 473 | 514 |  | 514-01-V0052-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2014-08-19 | 2017-10-27 | 0 | 0 | 483 | 2017-04-28
8048 | 473 | 514 |  | 514-01-VPR02-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 465 | 2011-11-21
8048 | 473 | 521 |  | 521-01-V0007-800 | 526000-000000001 | ACTUATOR, MS6Q, 440V, 3PH ED | 2 | 2 | 2014-05-01 | 180 | 2013-11-02 | EA | 0 | 0 | 2 | No | 2015-06-26 | 2017-10-27 | 0 | 0
8048 | 473 | 521 |  | 521-01-V0008-S01 | -S00 | VALVE ACTUATOR | 4 | 4 | 2014-02-28 | 180 | 2013-09-01 | EA | 0 | 0 | 4 | No | 2017-05-15 | 2017-10-27 | 7715 | 30860
8048 | 473 | 521 |  | 521-01-V0010-S01 | -S00 | VALVE ACTUATOR | 2 | 2 | 2014-02-28 | 180 | 2013-09-01 | EA | 0 | 0 | 2 | No | 2017-05-15 | 2017-10-27 | 7560 | 15120
8048 | 473 | 521 |  | 521-01-V0010-S01 | -S00 | VALVE ACTUATOR | 2 | 2 | 2014-02-28 | 180 | 2013-09-01 | EA | 0 | 0 | 2 | No | 2017-05-15 | 2017-10-27 | 7560 | 15120
8048 | 473 | 521 |  | 521-01-V0019-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-03-21 | 60 | 2014-01-20 | EA | 0 | 0 | 1 | No | 2014-04-30 | 2017-10-27 | 0.01 | 0.01 | 483 | 2015-11-04
8048 | 473 | 521 |  | 521-01-V0022-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | EA | 0 | 0 | 1 | No | 2015-03-17 | 2017-10-27 | 0.01 | 0.01 | 483 | 2015-11-04
8048 | 473 | 521 |  | 521-01-V0023-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-09-26 | 60 | 2014-07-28 | EA | 0 | 0 | 1 | No | 2014-04-30 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8048 | 473 | 521 |  | 521-01-VMS12-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-03 | 60 | 2014-08-04 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 475 | 2015-11-09
8048 | 473 | 521 |  | 521-01-VMS12-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-10-03 | 60 | 2014-08-04 | EA | 0 | 0 | 1 | No | 2016-03-22 | 2017-10-27 | 0 | 0
8048 | 473 | 528 |  | 528-01-E0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2015-03-11 | 60 | 2015-01-10 | EA | 0 | 0 | 1 | No | 2013-12-04 | 2017-10-27 | 0 | 0 | 481 | 2017-04-25
8048 | 473 | 529 |  | 529-01-E0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-23 | 60 | 2014-08-24 | EA | 0 | 0 | 1 | No | 2013-10-22 | 2017-10-27 | 0 | 0 | 481 | 2017-04-25
8048 | 473 | 533 |  | 533-01-V0002-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 483 | 2017-04-27
8048 | 473 | 533 |  | 533-01-V0006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-28 | 60 | 2014-03-29 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 477 | 2015-05-13
8048 | 473 | 533 |  | 533-01-VPR05-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8048 | 473 | 533 |  | 533-01-VPR05-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-02-28 | 60 | 2013-12-30 | EA | 0 | 0 | 1 | No | 2014-04-28 | 2017-10-27 | 0 | 0
8048 | 473 | 551 |  | 551-01-V0069-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 477 | 2015-03-10
8048 | 473 | 551 |  | 551-01-V0079-L34 | -L34 | PROVISIONING TECH DOC. | 1 | 1 | 2014-04-10 | 60 | 2014-02-09 | LO | 0 | 0 | 1 | Yes | 2014-07-17 | 2017-10-27 | 0 | 0
8048 | 473 | 551 |  | 551-01-V0850-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-12-22 | 60 | 2014-10-23 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 481 | 2017-08-23
8048 | 473 | 551 |  | 551-01-VPR07-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | EA | 0 | 0 | 1 | No | 2013-12-05 | 2017-10-27 | 0 | 0 | 477 | 2015-09-15
8048 | 473 | 551 |  | 551-01-VPR12-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | EA | 0 | 0 | 1 | Yes | 2014-07-17 | 2017-10-27 | 0 | 0 | 481 | 2017-04-18
8048 | 473 | 551 |  | 551-01-VPR12-L34 | -L34 | PROVISIONING TECH DOC. | 1 | 1 | 2014-09-15 | 60 | 2014-07-17 | LO | 0 | 0 | 1 | Yes | 2014-07-17 | 2017-10-27 | 0 | 0
8048 | 473 | 551 |  | 551-01-VPR14-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2014-08-08 | 2017-10-27 | 175 | 175 | 479 | 2017-03-21
8048 | 473 | 551 |  | 551-01-VPR16-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2014-09-29 | 2017-10-27 | 0 | 0 | 477 | 2017-03-21
8048 | 473 | 551 |  | 551-01-VPR16-L31 | -L31 | CERTIFICATE, CALIBRATABLE | 1 | 1 | 2014-06-18 | 60 | 2014-04-19 | EA | 0 | 0 | 1 | No | 2016-02-26 | 2017-10-27 | 175 | 175 | 477 | 2017-03-21
8048 | 473 | 555 |  | 555-01-E0001-822 | 760129-000000024 | 2" SELECTOR VALVE W/ADAPTER | 2 | 2 | 2014-06-18 | 21 | 2014-05-28 | EA | 0 | 0 | 2 | No | 2017-08-09 | 2017-10-27 | 0 | 0 | 469 | 2017-08-17
8048 | 473 | 555 |  | 555-02-V0009-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-07-29 | 60 | 2014-05-30 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 485 | 2017-10-25
8048 | 473 | 555 |  | 555-02-V0026-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-10-03 | 60 | 2014-08-04 | EA | 0 | 0 | 1 | No | 2014-05-01 | 2017-10-27 | 0 | 0 | 481 | 2015-11-04
8048 | 473 | 555 |  | 555-02-V012A-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-28 | 60 | 2014-03-29 | EA | 0 | 0 | 1 | No | 2013-11-25 | 2017-10-27 | 0 | 0 | 485 | 2017-09-15
8048 | 473 | 555 |  | 555-02-V9000-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-05-01 | 2017-10-27 | 0 | 0 | 481 | 2015-10-29
8048 | 473 | 555 |  | 555-02-V9006-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-01-20 | 60 | 2013-11-21 | EA | 0 | 0 | 1 | No | 2014-05-01 | 2017-10-27 | 0 | 0 | 481 | 2015-10-29
8048 | 473 | 555 |  | 555-07-V0014-S00 | -S00 | MOUNTING BRACKET FOR 1" VALV | 8 | 8 | 2017-02-28 | 30 | 2017-01-29 | EA | 0 | 0 | 8 | No | 2017-02-28 | 2017-02-28 | 110 | 880
8048 | 473 | 582 |  | 582-01-00201-L11 | -L11 | CERTIFICATES, REGULATORY BOD | 1 | 1 | 2015-02-26 | 60 | 2014-12-28 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 479 | 2015-08-19
8048 | 473 | 593 |  | 593-01-V0001-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-05-28 | 60 | 2014-03-29 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 483 | 2017-10-19
8048 | 473 | 593 |  | 593-01-V0686-L26 | -L26 | CERTIFICATE, IDENTICALITY | 1 | 1 | 2014-08-25 | 60 | 2014-06-26 | EA | 0 | 0 | 1 | No | 2014-02-17 | 2017-10-27 | 0 | 0 | 479 | 2016-11-02
8049 | 473 | 169 |  | 169-01-0007A | SRV521-030600009 | VENDOR SERVICES TO INSTALL | 1 | 1 | 2014-09-26 | 123 | 2014-05-26 | LO | 0 | 0 | 1 | No | 2013-12-03 | 2017-10-27 | 256764.12 | 256764.12 | 467 | 2014-01-21
8049 | 473 | 169 |  | 169-99-COCNG | SRV521-011500003 | AUTHORIZED CHANGE | 1 | 1 | 2014-09-26 | 123 | 2014-05-26 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 9324 | 9324 | 469 | 2015-08-13
8049 | 473 | 259 |  | 259-05-01000 | SRV527-030600005 | SSDG EXHAUST SYSTEM INSTALLA | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2013-08-22 | 2017-10-27 | 65000 | 65000 | 469 | 2015-05-28
8049 | 473 | 259 |  | 259-06-00998 | SRV527-030500006 | VENDOR SERVICE, WELD GT ELBO | 1 | 1 | 2014-08-04 | 123 | 2014-04-03 | LO | 0 | 0 | 1 | No | 2014-06-02 | 2017-10-27 | 19950 | 19950 | 469 | 2016-06-20
8049 | 473 | 259 |  | 259-07-01000 | SRV527-030600012 | MPDE EXHAUST SYSTEM INSTALLA | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2013-08-22 | 2017-10-27 | 130000 | 130000 | 469 | 2016-06-20
8049 | 473 | 259 |  | 259-07-SP005 | 54H409-000000001 | CUSTOM TRANSITION, 20.5-18,S | 4 | 4 | 2014-06-04 | 123 | 2014-02-01 | EA | 0 | 0 | 4 | No | 2017-07-28 | 2017-10-27 | 0 | 0
8049 | 473 | 304 |  | 304-00-00143 | 306308030100-001 | CABLE, CAT 5E, WATER BLOCKED | 50000 | 50000 | 2014-01-20 | 160 | 2013-08-13 | FT | 0 | 49272 | 728 | No | 2013-08-02 | 2017-10-27 | 0.2723 | 198.2344
8049 | 473 | 304 |  | 304-00-00325 | 304914200101-002 | CABLE, ELECTRIC, LS2SUS-7, | 4000 | 1100 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 189 | 911 | No | 2013-08-02 | 2017-10-27 | 0.2723 | 248.0653
8049 | 473 | 304 |  | 304-00-00328 | 303501040300-001 | CABLE, HELIAX, FSJ2RK-50, | 860 | 860 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 16 | 844 | No | 2013-08-02 | 2017-10-27 | 0.2723 | 229.8212
8049 | 473 | 304 |  | 304-00-00330 | 304301040700-001 | CABLE, HELIAX, LDF4RK-50A, | 4100 | 1533 | 2014-01-20 | 160 | 2013-08-13 | LF | 0 | 633 | 900 | No | 2013-08-02 | 2017-10-27 | 0 | 0
8049 | 473 | 304 |  | 304-01-00204 | 307410200102-001 | ELEC CABLE, LSMSCU-10,LOW SM | 2634 | 1227 | 2014-01-20 | 80 | 2013-11-01 | LF | 93 | 206 | 928 | No | 2014-02-23 | 2017-10-27 | 0.2723 | 252.6944
8049 | 473 | 439 |  | 439-00-00001 | SRV526-030600005 | VENDOR SRVC TO PERFORM SCOPE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2014-02-25 | 2017-10-27 | 262.96 | 262.96 | 465 | 2015-06-10
8049 | 473 | 565 |  | 565-01-00005 | SRV524-030600001 | SERVICES, HYDRAULIC SYSTEM | 1 | 1 | 2014-06-24 | 123 | 2014-02-21 | LO | 0 | 0 | 1 | No | 2016-02-24 | 2017-10-27 | 0 | 0 | 467 | 2013-07-03
8049 | 473 | 665 |  | 665-05-10007 | SRV525-030600107 | MATERIAL AND LABOR TO INSTAL | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | LO | 0 | 0 | 1 | No | 2015-03-11 | 2017-10-27 | 4620 | 4620 | 471 | 2015-04-02
8049 | 473 | 321 |  | 321-99-STUD1-BB | SRV526-030600023 | SRVC, SHOOT STUDS, LOCAL WIR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-06-13 | 2017-10-27 | 0 | 0
8049 | 473 | 321 |  | 321-99-STUD1-FT | SRV526-030600024 | SRVC, SHOOT STUDS, LOCAL WIR | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2014-06-13 | 2017-10-27 | 9 | 9 | 469 | 2015-08-12
8049 | 473 | 234 |  | 234-01-00002-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-11-19 | 123 | 2014-07-19 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0
8049 | 473 | 234 |  | 234-01-000A1-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-02-03 | 123 | 2013-10-03 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
8049 | 473 | 234 |  | 234-01-000A1-L68 | -L68 | CERTIFICATES, VENDOR WELDING | 1 | 1 | 2014-02-03 | 123 | 2013-10-03 | LO | 0 | 0 | 1 | No | 2015-06-12 | 2017-10-27 | 0 | 0 | 485 | 2016-12-12
999999 | 473 | 320 |  | 320-01-00179 | 360301030105-001 | ENCLOSURE, BRASS, 4X7X4-1/2" | 1 | 1 | 2014-01-20 | 56 | 2013-11-25 | EA | 0 | 0 | 1 | No | 2017-10-27 | 2017-10-27 | 424.43 | 424.43 | 120 | 2010-12-06
999999 | 473 | 324 |  | 324-20-00017 | SRV526-032200020 | DRS SWBD SOFTWARE UPGRADE | 1 | 1 | 2014-01-20 | 123 | 2013-09-19 | EA | 0 | 0 | 1 | No | 2017-10-27 | 2017-10-27 | 0 | 0
999999 | 473 | 571 |  | 571-01-00S22 | 780009100000-001 | SHIELD, GYPSY WINCH CONTROLL | 1 | 1 | 2015-07-29 | 123 | 2015-03-28 | EA | 0 | 0 | 1 | No | 2017-10-27 | 2017-10-27 | 805 | 805 | 450 | 2009-12-04
999999 | 473 | 415 |  | 415-01-00017-800 | 372000000000-003 | PRINTER BRACKET, SHOCK QUALI | 7 | 7 | 2014-01-20 | 48 | 2013-12-03 | EA | 0 | 0 | 7 | No | 2017-10-26 | 2017-10-27 | 0 | 0